## Slide 1
CONNECTION | ECS PARTNERSHIP
Modernizing the Core
The ServiceNow Reimplementation Strategy
An 18-week, OOTB-first reimplementation that lands a clean, AI-ready ServiceNow platform — structured as governance-led 2-week sprints.
Phase 1 · ITSM Core · CSDM · Employee Experience · AI-Ready
Prepared by ECS · Confidential · PC Connection · ServiceNow Re-implementation

## Slide 2
01 · EXECUTIVE SUMMARY
Why we're doing this — and why now
Connection's Corporate IT will fully reimplement ServiceNow on a new, dedicated instance — replacing the customized, domain-separated legacy build with an OOTB-first foundation that is ready for AI, automation, and disciplined growth.
1
OOTB-First
Lead with ServiceNow best practices. Customization is the exception, not the default.
2
CSDM-Aligned CMDB
Healthy, standardized data from day one — the prerequisite for AI ROI.
3
Modern Employee Center
Virtual Agent + AI Search to drive deflection and reduce friction.
4
Governance Built-In
Strict triage, feedback-driven backlog, MTTR & SLA tracked end-to-end.
18-WEEK PHASE 1 · 16 weeks build + 2 weeks Hypercare · Iterative agile from Day One
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
2 / 19

## Slide 3
02 · CURRENT STATE
The pain points driving the reset
LEGACY DEBT IS
blocking AI
Heavy customization, a domain-separated environment, and a legacy CMDB make it impossible to leverage modern ServiceNow capabilities or realize AI ROI.
Technical Debt
Heavy customization blocks modern features.
Low OOTB Adoption
Replicating legacy = inefficiency at scale.
Domain Separation
Operational complexity prevents expansion.
Portal Confusion
Employees unsure how or where to request.
Communication Gaps
Inconsistent updates, weak automation.
Improving CMDB Health
Resetting CI data to maximize AI use and ROI.
Underutilized SKUs
Licensed capabilities sitting idle.
Limited Reporting
No reliable view of MTTR or SLA performance.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
3 / 19

## Slide 4
03 · STRATEGIC GOALS
Where we're headed — the seven outcomes
1
Adopt OOTB Processes
Lead with best practices before iterating.
2
Modernize Change & CMDB
CSDM with CI-based risk scoring.
3
Improve Employee Experience
Modern EC, Virtual Agent, AI Search.
4
Enable AI & Analytics
Predictive Intelligence + Performance Analytics.
5
Exit Domain Separation
Move to a governed, dedicated instance.
6
Establish Governance
Triaged backlog, business-prioritized intake.
7
Optimize Licensed SKUs
Realize value from every capability paid for.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
4 / 19

## Slide 5
04 · SCOPE
Phase 1 in-scope applications & integrations
ITSM Core
Incident, Request, Knowledge, Change/CAB, Problem, Major Incident, SO Workspace.
Initial Service Catalog
Top 10–15 most impactful items with workflows, approvals; 2–3 generic to cover all services.
Employee Experience
Employee Center, Virtual Agent, AI Search, Knowledge Management.
Automation & AI
Flow Designer, Predictive Intelligence, Task Intelligence.
Analytics
Platform Analytics, Performance Analytics, Data Visualization, Benchmarks.
CMDB & CSDM
Foundational CSDM alignment, CMDB and CI relationship standards.
Discovery & Connectors
Discovery, Service Graph Connectors for SCCM and Intune.
Agile / DevOps
Agile delivery for ServiceNow; intake & triage model.
HAM + Integrations
Stockrooms, HAM Foundations, AD/SSO for seamless login.
Existing configuration will be ported where it does not introduce technical debt — the rest is greenfield.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
5 / 19

## Slide 6
05 · TECHNICAL APPROACH
The OOTB-First framework
Make customization the exception, not the default.
01
Baseline Validation
Every build starts with an OOTB demo. Any delta must be justified by documented business need and Project Sponsor sign-off.
02
Low-Code / No-Code
Configuration favors Flow Designer, Decision Tables, and UI Builder over custom Script Includes or Jelly/Angular code.
03
Upgradeability Scorecard
Every config is assessed for upgrade impact. 'Skipped Record' risk for the next release auto-flags the Governance Triage Log.
04
Core Data Integrity
Strict CSDM 5.0 adherence. Custom tables in place of standard CI classes are 'Structural Deviations' needing sponsor approval.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
6 / 19

## Slide 7
06 · GOVERNANCE
Operational Guardrails & PCR triggers
THE RULE OF THREE
If a requirement cannot be met by one of these three, it becomes a customization requiring formal review.
1
Configuration
2
UI Policy
3
Flow Designer
DEFINITION OF DONE
A story is not 'Done' unless it is proven to be upgrade-safe.
PCR TRIGGERS · CONTRACTUAL GUARDRAILS
Any of the following requires a formal Project Change Request:
Custom scripting or modification of protected baseline objects
Creation of custom tables outside the OOTB CSDM model
Customer dependencies (Foundation Data, SSO, SMEs) missed by Sprint 0/1
Connection SME unavailable for in-scope integration work
Third-party integrations not explicitly listed in the original SOW
MVP Mindset: secondary requirements deferred to the Phase 2 backlog
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
7 / 19

## Slide 8
07 · WORKSHOP APPROACH
Just-in-Time, OOTB-first, decision-led
Workshops are the foundation of our delivery approach — we run them throughout the engagement, not just upfront. Each session opens with a live OOTB demonstration, then focuses on the narrow set of decisions your team needs to make to fit the platform to Connection. Sessions are hands-on: we configure, test, and iterate against your data and scenarios in the room.. Because every workshop is timed Just-in-Time to the next sprint, requirements don't go stale — what's agreed moves straight into the active iteration of planned work, accelerating alignment and creating momentum into delivery.
01
ACCELERATOR PACK
Foundational core data — Accelerator Pack workbooks for CMDB classes, locations, groups, assignment rules, catalog taxonomy, datasets — to execute build and reach go-live.
02
CSDM
Map Business, Technical, Application Services to OOTB CSDM 5.0 domains. Connection leaves with a signed-off model that lets Discovery, Service Mapping, and AI work OOTB, documented in the CSDM & CMDB Blueprint.
03
REPORTING
Confirm OOTB Performance Analytics, dashboards, and standard reports meet Connection's business objectives before any custom report is entertained. Gaps are captured in stories and configure during the Execute phase.
04
PROCESS OOTB ALIGNMENT
Walk each in-scope process end-to-end against the OOTB demo. Identify the narrow set of justified deltas. Collectively we make adjustments to the baseline when adjustments align to outcomes. Sign off on user stories to be built.
05
INTEGRATION
Define in-scope integration patterns, data contracts, and OOTB Spoke / IntegrationHub usage. Document in stories and in. ECS owns the SN side; Connection owns source systems.
ECS PROVIDES facilitator · demo environment · accelerator templates · cadence · ServiceNow design | CONNECTION PROVIDES empowered process owners · timely SMEs · source-system access · signed-off outputs
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
8 / 19

## Slide 9
08 · INITIAL SERVICE CATALOG
10–15 most impactful + 2–3 generic = no customer left behind
10–15
MOST IMPACTFUL
Existing catalog items with clearly defined activities, workflows, approvals; current configuration leveraged where it does not introduce technical debt.
+
2–3
GENERIC ITEMS
Designed to capture services that do not yet have a dedicated workflow — every customer has a viable path on day one.
=
EVERY SERVICE ACCOUNTED FOR
Phase 1 lands the most impactful items.
Generic items keep all customers covered.
Expanded directed workflows arrive in later phases.
"We don't want to leave any of the customers behind." — Kristen, Connection
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
9 / 19

## Slide 10
09 · ROADMAP
Phase 1 implementation — 4 months, 8 sprints
MONTH 1
Foundation & Discovery
Architecture, CSDM data model, Discovery & connector ingestion begin.
MONTH 2
Core Build
ITSM Core (INC/PRB/REQ), modernized Change/CAB, top-priority catalog items.
MONTH 3
Advanced Features
Employee Center, Virtual Agent, KM, Performance Analytics, HAM foundations.
MONTH 4
Validate & Go-Live
UAT, training, governed cutover, Hypercare and stabilization.
16 weeks of build + 2 weeks of Hypercare · Sprint 0 sets the foundation · Go-Live targeted for week 16
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
10 / 19

## Slide 11
10 · STAGE 1 · INITIATE & PLAN
Sprints 0–2 · Weeks 1–6 · Foundation
STAGE
01
SPRINT 0
WEEKS 1–2
Project Setup & Governance
Formal kickoff & SOW review
ECS Accelerator Pack distribution
Backlog triage & governance strategy
Roles, responsibilities & acceptance criteria
SPRINTS 1 & 2
WEEKS 3–6
Core Data & CSDM Foundation
CSDM mapping & CI relationship standards
Greenfield basics — SSO, AD, roles, SLAs
Foundation Data imports
Discovery & SCCM/Intune Service Graph kickoff
FOCUS · Set governance. Stand up the greenfield. Build the CSDM-aligned data foundation that everything else depends on.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
11 / 19

## Slide 12
11 · STAGE 2 · EXECUTE
Sprints 3–5 · Weeks 7–12 · Core build & employee experience
STAGE
02
SPRINTS 3 & 4
WEEKS 7–10
ITSM Core & Modernized Change
INC, PRB, CHG, REQ in SO Workspace
CI-driven change risk scoring
CAB Workbench standup
Replace customized legacy with OOTB workflows
SPRINT 5
WEEKS 11–12
Employee Experience & Automation
Stand up Employee Center
Virtual Agent + AI Search
Knowledge Management workflow & ported articles
Initial Predictive Intelligence configuration
FOCUS · Replace customized legacy processes with streamlined OOTB workflows; drive ticket deflection on the front end.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
12 / 19

## Slide 13
12 · STAGE 3 · DELIVER
Sprints 6–7 · Weeks 13–16 · Validation, readiness & Go-Live
STAGE
03
SPRINT 6
WEEKS 13–14
Testing & Analytics
System Integration Testing (SIT)
User Acceptance Testing (UAT) cycles
Finalize Performance Analytics dashboards
MTTR, SLA & change-success tracking standup
SPRINT 7
WEEKS 15–16
Training, Cutover & Hypercare
Deliver KT sessions & train-the-trainer materials
Execute governed migration to new instance
Provide post-launch Hypercare support
Confirm clean exit from legacy env.
FOCUS · Deliverables: UAT/SIT Report · Go-Live Checklist · Cutover Runbook
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
13 / 19

## Slide 14
13 · STAGE 4 · CLOSE
Sprint 8 · Weeks 17–18 · Hypercare & strategic handover
STAGE
04
KEY ACTIVITIES
1
Stabilize Production
Finalize post-go-live Hypercare; stabilize the live environment.
2
Formal Project Closeout
Archive artifacts, sign off on deliverables, conduct Lessons Learned.
3
Roadmap Review
Align on long-term vision; transition operations to internal team.
CLOSE DELIVERABLES
Knowledge Transfer Library
SOPs, Admin 101 guides, train-the –trainer workshops and material.
Lessons Learned & Closeout Report
Final KPIs, OOTB wins, and 12-month strategic roadmap.
A clean transition. A documented handover. A roadmap for what's next.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
14 / 19

## Slide 15
14 · PROGRAM RECAP
Phase 1 · Foundation & Core
PHASE 1 TIMELINE 16 weeks build + 2 weeks Hypercare ROM $350,000
ITSM Core & Modernized Change
Incident, Request, Problem, Change/CAB, Major Incident running in Service Operations Workspace, with CI-driven change risk scoring and the CAB Workbench.
CSDM-Aligned CMDB
OOTB CSDM 5.0 model with normalized class hierarchy. Discovery and Service Graph Connectors (SCCM, Intune) populating clean, AI-ready CI data.
Initial Service Catalog
10–15 most impactful items + 2–3 generic items so every service has a path on day one. Documented activities, workflows, and approvals.
Employee Experience
Employee Center, Virtual Agent + AI Search, Knowledge Management — driving deflection and reducing friction at the front end.
Analytics & AI Foundations
Performance Analytics dashboards live; Predictive Intelligence configured. MTTR, SLA attainment, and change-success tracking standing up.
HAM, & Integrations
HAM Foundations + Stockrooms,, AD/SSO, SCCM and Intune and the Agile delivery framework for the platform team.
AT END OF PHASE 1 · Connection is operating on a clean, OOTB-aligned ServiceNow foundation — ready for the Phase 2 expansion roadmap.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
15 / 19

## Slide 16
15 · LONG-TERM ROADMAP
Phase 2 · Baseline expansion & enhanced experience
PHASE 2 TIMELINE 12–14 weeks ROM $150K – $185K
Full Service Catalog
Expand to 18–20 Business/Technical Services + 50–70 catalog items with documented workflows.
Virtual Agent Expansion
Tune VA accuracy with Keyword Aliases, Topic Discovery; route to automation or live agents.
On-Call Scheduling
Compliant On-Call Wizard setup — schedules, rotations, escalations, communication triggers.
HAM Expansion
Lifecycle automation via Context Service + 6 OOTB asset workflows tied to INC and CHG.
SAM Foundation
Visibility + normalization through Context Service & Library — your software baseline.
Service Graph Connectors
Vonage integration; discovery around Boomi & Databricks for future Workflow Data Fabric strategy.
* Final estimate depends on additional evaluation of the catalog consolidation effort.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
18 / 19

## Slide 17
16 · LONG-TERM ROADMAP
Phase 3 · ITOM, intelligence & the AI horizon
PHASE 3 TIMELINE 12–14 weeks ROM $100K – $125K
Event Management
Bi-directional integration to event sources (SolarWinds, AWS); deduplication, event rules bound to a CSDM-clean CMDB; correlation rules to prevent alert storms.
Service Mapping
Built on a mature CMDB. Leverage ServiceNow OOTB patterns; document custom-pattern needs in the backlog for future work.
SAM Expansion
Tie entitlements (what is owned) to installed software — true license position, optimization, true-up needs and audit-risk reduction.
FUTURE · ENHANCED AI & ADVANCED AUTOMATION
With three phases complete on a clean OOTB foundation, the door opens to Now Assist / Agentic Agents and Workflow Data Fabric — "zero-copy" integration across Boomi, Databricks, Atlassian, UKG, and E1 to power AI-driven decisions without ingesting external data.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
18 / 19

## Slide 18
17 · ENGAGEMENT MODEL
Roles & responsibilities — ECS and Connection
ECS
Delivery, configuration & demonstration
Workshop facilitation & demonstration environment
ECS Accelerator Pack templates & cadence
ServiceNow-side configuration, integration & build
Sprint reviews, governance triage, definition of done
UAT support, KT sessions, train-the-trainer materials
Hypercare support, closeout report, 12-month roadmap
CONNECTION
Decisions, data & domain knowledge
Empowered process owners with decision authority
Timely SME availability for workshops & sprint reviews
Source-system access, credentials & counterpart engineers
Workshop output sign-off feeding the active sprint backlog
UAT execution and stakeholder approval at each gate
Operations hand-off and post-Hypercare ownership
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
18 / 19

## Slide 19
PROGRAM ROM · ROUGH ORDER OF MAGNITUDE
Estimated cost by phase
PHASE 1
Foundation & Core
16 weeks + 2 weeks Hypercare
$350,000
Fixed ROM
KEY SCOPE
ITSM Core · CSDM/CMDB · Employee Center · Virtual Agent · AI Search · Performance Analytics · Discovery · HAM Foundations
PHASE 2
Baseline Expansion
12–14 weeks
$150K – $185K
ROM range *
KEY SCOPE
Full Catalog · VA Expansion · On-Call · HAM Expansion · SAM Foundation · Additional Service Graph Connectors
PHASE 3
ITOM & Intelligence
12–14 weeks
$100K – $125K
ROM range **
KEY SCOPE
Event Management · Service Mapping · SAM Expansion (entitlements + license position)
TOTAL THREE-PHASE PROGRAM ESTIMATE $600,000 – $660,000 · ~10–11 months of build, all phases
* Phase 2 final estimate pending catalog consolidation evaluation. ** Phase 3 final pricing pending entitlements discovery.
ECS · PC CONNECTION · SERVICENOW RE-IMPLEMENTATION
19 / 19