STATEMENT OF WORK · MODERNIZING THE CORE

Statement of Work:

Connection ServiceNow OOTB-First Reimplementation

Modernizing the Core — Ensuring AI Realization and Optimizing Long-Term Value

ECS Federal · ServiceNow Practice

Audience: Connection· ECS Federal — ServiceNow Practice

Document ID: DOC0004841     ·     Version: 2.0

This Statement of Work (SOW) also serves as the Project Charter for the engagement. It defines the scope, delivery approach, customer responsibilities, governance model, and contractual guardrails that govern the ECS Federal ServiceNow reimplementation engagement with Connection. Upon execution, this document is binding on both parties and supersedes any prior proposals, presentations, or correspondence related to the same scope of work.

Table of Contents

1.  Executive Summary	4

Core Project Goals	4

Current State and Pain Points	4

2.  Phase 1: In-Scope Applications and Integrations	5

ITSM Core	5

Service Catalog	5

Employee Experience	5

Platform Baselines	5

CMDB and CSDM	5

Hardware Asset Management (HAM)	6

Integrations	6

3.  Technical Approach: The OOTB-First Framework	6

The Rule of Three	6

Definition of Done	7

MVP Mindset	7

Low-Code / No-Code Governance	7

Upgradeability Scorecard	7

Intelligent Reuse: Accelerating Delivery Without Compromising OOTB	7

4.  Delivery Approach and Engagement Model	8

Workshop Model	8

Sprint Sequencing	8

5.  Engagement Deliverables	9

Sprint 0 Deliverables (Weeks 1–2)	9

Month 1 Deliverables (Weeks 3–6)	9

Month 2 Deliverables (Weeks 7–10)	10

Month 3 Deliverables (Weeks 11–14)	10

Go-Live Deliverables (Weeks 15–18)	10

6.  Customer Responsibilities and Dependencies	11

Sprint 0 / Pre-Build Dependencies	11

Ongoing Engagement Responsibilities	11

7.  Out of Scope	12

8.  Assumptions	12

9.  Project Guardrails and PCR Process	13

Scope Boundary Definitions	13

PCR Triggers: Customer-Initiated Scope Changes	13

PCR Triggers: Schedule and Dependency Impacts	14

PCR Process	15

Governance Triage Log	15

10.  Testing and Acceptance	15

Testing Approach	15

Acceptance Criteria	16

11.  Organizational Change Management and Training	17

Hypercare	17

12.  Engagement Governance	18

Governance Cadence	18

Roles and Responsibilities	18

13.  Timeline and Pricing	20

Phase 1 Timeline	20

Phase 1 Pricing	20

Payment Schedule	20

14.  Long-Term Roadmap: Beyond Phase 1	22

Phase 2: Baseline Expansion and Enhanced User Experience	22

Phase 3: ITOM and Intelligence	22

Phase 4 and Beyond: Full AI Realization	22

15.  Terms and Conditions	22

16.  Signature Block	23

Acronyms & Definitions	24

# 1.  Executive Summary

Connection has initiated a strategic ServiceNow reimplementation designed to exit a Domain Separated shared instance and establish a modern, AI-ready platform foundation built on the CMDB and CSDM best practices. ECS Federal will lead this engagement under an Out-of-the-Box (OOTB)-First delivery discipline — standing up proven ServiceNow baseline capability before any deviation is considered — so that Connection lands on a platform that is architecturally ready for Now Assist, Agentic Agents, Predictive Intelligence, and the Workflow Data Fabric.

This 18-week Phase 1 delivery focuses on modernizing IT Service Management (ITSM) Core processes and standing up a modern Employee Center with Virtual Agent and AI Search to drive ticket deflection and improve the overall employee experience. A foundational Sprint 0 precedes the build sprints and is dedicated to alignment, governance setup, and accelerator pack data collection. Delivery follows an iterative Agile methodology with two-week sprints.

A critical success factor for this engagement is alignment to Common Service Data Model (CSDM) best practices from day one, ensuring a healthy Configuration Management Database (CMDB) that can support Configuration Item (CI)-based change risk scoring and provide the clean data required for AI Return On Investment (ROI). Key outcomes will be tracked via Platform Analytics, focusing on operational improvements including Mean Time to Resolution (MTTR), Service Level Agreement (SLA) attainment, and change success rates.

## Core Project Goals

Adopt OOTB processes as the default, leading with ServiceNow best practices before making iterative adjustments.

Modernize Change Management and CMDB alignment to CSDM standards, enabling CI-based risk scoring.

Deliver a modern Employee Center with Virtual Agent, AI Search, and a curated Knowledge Base.

Enable Platform Analytics and Predictive Intelligence to achieve measurable operational ROI.

Establish strict governance to intake, triage, and prioritize platform requests based on business need.

Ensure all purchased ServiceNow license SKUs are actively configured and delivering value within the engagement scope.

Exiting Domain Separation: Moving to a governed, dedicated instance to remove operational complexities and allow for future expansion.

## Current State and Pain Points

The following pain points, identified during pre-engagement discovery with Connection, form the basis for the scope and sequencing decisions in this SOW:

Technical debt and accumulated customization that limits AI adoption and upgrade flexibility.

Low OOTB adoption resulting in process inefficiencies, complexity, and limited scalability.

Domain Separation Blocks, the current domain-separated environment complicates operations and prevents the platform from expanding, user experience gaps: employees uncertain where or how to request services.

CMDB health issues preventing AI ROI — CI data quality insufficient for risk scoring or automation.

Underutilized license SKUs — purchased capabilities not yet configured or delivering value.

# 2.  Phase 1: In-Scope Applications and Integrations

The following capabilities are in scope for Phase 1. Each capability is selected because it delivers immediate operational value and serves as a prerequisite for the AI capabilities Connection will leverage in subsequent phases.

## ITSM Core

Incident Management, Request Management, Knowledge Management.

Change Management including CAB Workbench and [2–3] well-defined standard changes.

Problem Management and Major Incident Management.

Service Operations Workspace.

## Service Catalog

Top [10–15] most impactful existing catalog items with clearly defined activities, workflows, and approvals. Existing catalog configurations are leveraged where they do not introduce technical debt.

[2–3] of the Phase 1 catalog items are designed to be generic enough to capture services that do not yet have a dedicated workflow, ensuring no user community is left without a service path. Directed workflows for those services are delivered in later phases.

## Employee Experience

Employee Center portal with Connection specific branding

Virtual Agent with 5 baseline topic configurations.

AI Search configuration for knowledge base

Knowledge Management: ECS delivers KM taxonomy, article structure, and baseline content ported from legacy platform

## Platform Baselines

Subscription Management — configured as a platform-level baseline for license visibility. Set up groups and provide basic training

Security Center — baseline posture visibility from day one.

Turn on Predictive Intelligence, Task Intelligence.

Turn on Platform Analytics, Data Visualization, Benchmarks.

## CMDB and CSDM

Foundational alignment to CSDM best practices.

CMDB and CI relationship standards established.

Service Graph Connectors for

MS SCCM

inTune

Discovery

Current Discovery configuration leveraged where it does not introduce technical debt.

## Hardware Asset Management (HAM)

"Enable" Stockrooms and HAM foundational configuration to ensure CSDM alignment in Phase 1, prior to Phase 2

## Integrations

Active Directory (AD) and Single Sign-On (SSO) — current configuration leveraged where aligned to best practices.

MS SCCM (current existing integration)

inTune (current existing integration)

Vonage - current configuration leveraged

AI ALIGNMENT NOTE: Each capability above is selected because it both delivers immediate operational value and is a prerequisite for AI capabilities Connection has invested in. The OOTB foundation established in Phase 1 is the architectural requirement for Now Assist, Agentic Agents, and the Workflow Data Fabric.

# 3.  Technical Approach: The OOTB-First Framework

The goal of this engagement is to make customization the exception rather than the default. Every in-scope application build begins with a demonstration of out-of-the-box ServiceNow functionality. Any delta between the baseline and a user story requirement must be justified by a documented business necessity, scoped to budget, and signed off by the Project Sponsor before ECS proceeds with configuration.

The "OOTB Baseline" defines the scope specifically as the implementation and configuration of out-of-the-box ServiceNow functionality as defined by the ServiceNow Product Documentation for the installed release for all in-scope applications.

An acceptable threshold for deviating from OOTB is qualitative: a delta is acceptable only when it is (a) tied to a documented business outcome, (b) cannot be met by configuration of an OOTB capability, and (c) signed off by the Project Sponsor. ECS will proactively present the OOTB alternative in every case before a deviation is considered.

## The Rule of Three

If a requirement cannot be met by (1) Configuration, (2) UI Policy, or (3) Flow Designer, it is treated as a Customization. Customizations require a separate technical review, a formal impact assessment against scope and budget, and Project Sponsor approval before work begins.

## Definition of Done

A user story is considered Done when:

Acceptance criteria were reviewed and approved by the Product Owner prior to build activities commencing. All acceptance criteria in the user story have been met and approved by the Product Owner or assigned delegate.

The configuration adheres to the Rule of Three unless a Customization has been approved by the Project Sponsor and ECS Implementation Team.

The configuration is documented in the relevant design artifact, and the sprint workbook is updated.

## MVP Mindset

To complete this engagement within the 18-week timeline and achieve a Go-Live at week during month 4, ECS and Connection will maintain an MVP mindset: delivering a baseline implementation for all in-scope applications while capturing secondary and enhancement requirements in the backlog for the Phase 2 roadmap. This keeps the initial implementation clean and the timeline protected.

## Low-Code / No-Code Governance

ServiceNow configuration will prioritize Flow Designer, Decision Tables, and UI Builder over custom Script Includes or Jelly/Angular modifications. Any request that requires scripted solutions is subject to the Rule of Three review and may require a Project Change Request (PCR).

## Upgradeability Scorecard

During an upgrade, the baseline configuration is assessed for its impact on future ServiceNow upgrades. If a request creates a Skipped Record risk for the next ServiceNow family version, it is flagged for the Governance Triage Log and brought to the Customization Council for disposition.

## Intelligent Reuse: Accelerating Delivery Without Compromising OOTB

A pragmatic accelerator for the delivery timeline is the intelligent reuse of Connection’s existing platform investments where they align with the OOTB pattern. ECS and Connection’s technical leadership will assess current configurations and port them to the new instance where doing so does not introduce technical debt.

Integration configurations (AD/SSO, Discovery, SCCM/Intune): ECS reviews current integration designs with Connection SMEs and ports the working configuration where it aligns to current best practices.

Service Catalog items: Existing items using OOTB workflow patterns and standard form variables are ported and adapted. Items relying on custom Script Includes or non-standard data models are rebuilt against the OOTB pattern.

Knowledge articles: KM articles are curated and ported as a baseline for the new KM instance and Virtual Agent / AI Search content. Stale, redundant, or off-pattern articles are retired rather than ported.

The principle: reuse what aligns to OOTB; rebuild what does not. This accelerates delivery while preserving the OOTB-first discipline that makes the platform AI-ready.

# 4.  Delivery Approach and Engagement Model

## Workshop Model

The engagement is anchored by a structured, Just-in-Time workshop approach that grounds every design decision in standard ServiceNow OOTB capability before any deviation is considered. Workshops are deliberately short, outcome-oriented sessions where the platform demonstrates the baseline functionality first, and the conversation focuses on the narrow set of decisions Connection actually needs to make.

Workshops are organized into five tiers, each tied directly to the active sprint backlog:

Accelerator Pack Workshops: Capture foundational core data required to execute the build (CSDM, CMDB classes, locations, groups, assignment rules, catalog taxonomy, reference datasets).

CSDM Workshops: Establish the Common Service Data Model foundation that every downstream workstream depends on.

Process Design Workshops: One per in-scope ITSM process — demonstrate OOTB capability, identify the minimal set of decisions, and close with documented decisions before the sprint begins.

Employee Experience Workshops: Employee Center structure, Virtual Agent topic design, Knowledge Management taxonomy, and AI Search configuration.

Validation Workshops: UAT facilitation, stakeholder sign-off, and go-live readiness review.

During initial workshops, it is Connection’s responsibility to ensure all relevant stakeholders and product owners are available and actively participate in order to prevent facilitate timely and informed decisions and to avoid potential delays, rework, PCRs.

## Sprint Sequencing

| Sprint | Phase | Focus Areas |
| --- | --- | --- |
| Sprint 0 | Initiate & Plan | Project kickoff, governance setup, environment provisioning, Accelerator Pack data collection, CSDM alignment workshop, access to HiWave accounts |
| Sprint 1 | Execute — Month 1 | Platform architecture, CSDM validation, ITSM design workshops, Discovery / Service Graph Connectors initiation |
| Sprint 2 | Execute — Month 1 | CMDB normalization, ITSM Core configuration begins (Incident, Problem), integration review |
| Sprint 3 | Execute — Month 2 | ITSM Core build (Incident, Problem, Request), SLA and assignment rule configuration |
| Sprint 4 | Execute — Month 2 | Change Management and CAB, first set of high-priority catalog items developed |
| Sprint 5 | Execute — Month 3 | Employee Center, Virtual Agent, Knowledge Management, Platform Analytics |
| Sprint 6 | Execute — Month 3 | HAM foundations, remaining catalog items (totaling [13–15]), environment stabilization |
| Sprint 7/8 | Deliver — Month 4 | UAT, Knowledge Transfer, production cutover, Hypercare |

# 5.  Engagement Deliverables

The following deliverables define ECS’s obligations under this SOW. Each deliverable falls into one of two categories: Platform Configuration (capabilities configured and demo-accepted in the ServiceNow instance) or Documentation (formal artifacts produced and handed over to Connection). Sprint workbooks, the Governance Triage Log, and design decisions are produced throughout the engagement and are considered living documentation until Go-Live, at which point they form part of the Knowledge Transfer Package.

Payment Milestone Note: Payment milestones in Section 13 are calendar-based. The deliverables below define ECS’s obligations for each period. If a milestone delivery is delayed due to Connection (e.g., delayed data provision, unavailable SMEs, withheld access), the payment milestone date is not extended.

## Sprint 0 Deliverables (Weeks 1–2)

| Deliverable | Type |
| --- | --- |
| Governance Charter Package (Decision Rights document, Customization Council Charter, RACI Matrix) | Documentation |
| Baseline 18-Week Project Plan | Documentation |
| Foundation Data Workbooks (users, locations, departments, groups, SLAs, assignment rules, catalog taxonomy) provided to Connection for their completion. | Documentation |
| Baseline Risk Register | Documentation |
| Plug-ins installed and core configuration completed (once Connection has provisioned development and test environments with ECS admin access) | Platform Configuration |

## Month 1 Deliverables (Weeks 3–6)

| Deliverable | Type |
| --- | --- |
| Platform Architecture and CSDM Alignment Document | Documentation |
| Sprint 1–2 Design Documentation (workbooks updated with workshop decisions) | Documentation |
| Active Governance Triage Log (current through Sprint 2) | Documentation |
| ITSM Core v1 — Incident Management and Problem Management configured in test environment based on approved acceptance criteria | Platform Configuration |

## Month 2 Deliverables (Weeks 7–10)

| Deliverable | Type |
| --- | --- |
| Sprint 3–4 Design Documentation (workbooks updated, Governance Triage Log current) | Documentation |
| ITSM Core v2 — Service Request, Change Management, CAB Workbench, SLA framework, and assignment rules configured based on approved acceptance criteria | Platform Configuration |
| Service Catalog Phase 1 — 5 catalog items with workflows configured based on approved acceptance criteria | Platform Configuration |
| Integration Baseline — AD/SSO and named Service Graph Connectors for MS SCCM and inTune validated in test environment | Platform Configuration |

## Month 3 Deliverables (Weeks 11–14)

| Deliverable | Type |
| --- | --- |
| Employee Experience — Employee Center, Virtual Agent baseline topics, AI Search, and Knowledge Management based on approved acceptance criteria | Platform Configuration |
| HAM Foundations — stockrooms, asset classes, and CSDM-aligned hardware data model configured based on approved acceptance criteria | Platform Configuration |
| Remaining Catalog Items — 13 - 15 total items configured based on approved acceptance criteria | Platform Configuration |
| Performance Analytics — baseline dashboard set configured based on approved acceptance criteria | Platform Configuration |

## Go-Live Deliverables (Weeks 15–18)

| Deliverable | Type |
| --- | --- |
| UAT Execution Report (test scenario results, P1/P2 defect resolution log) | Documentation |
| Go-Live Readiness Sign-Off (signed by Executive Sponsor and Product Owner) | Documentation |
| Knowledge Transfer Package (administrator guide, train-the-trainer materials, sprint workbook set) | Documentation |
| Operational Handoff Pack (post-go-live ownership matrix, support model, escalation contacts) | Documentation |
| Production environment with all in-scope capabilities from Section 2 live and verified | Platform Configuration |
| Lesson’s Learned & Project Closeout | Documentation |

# 6.  Customer Responsibilities and Dependencies

The successful delivery of this engagement within the agreed timeline depends on active, timely participation from Connection. The following responsibilities are not optional elements of the engagement — they are structural dependencies that gate ECS’s ability to build, validate, and deliver on schedule. ECS will provide reasonable advance notice of each dependency so Connection can plan accordingly.

## Sprint 0 / Pre-Build Dependencies

Completed Accelerator Pack workbooks for Foundation Data (users, locations, departments, groups, assignment rules, schedules, SLAs) — ECS will provide templates. Due one week prior to execution sprint start for each in scope process.

SSO/AD configuration details and access to a technical SME for integration review.

Procuring licenses and provisioning development and test environments with admin-level ECS access.

ServiceNow Mid Server(s) configuration must be in place by the end of Sprint 0 in order to avoid potential project delays and additional related costs.

Document complete IP Range Sets (for a subset of IPs for all Discovery Schedules) that will utilize existing ServiceNow probes, sensors, and patterns.

Named Product Owner with authority to make acceptance decisions on behalf of Connection.

Named SMEs per process area — at minimum: ITSM, Catalog, CMDB/Discovery, integrations, Employee Experience.

Executive Sponsor confirmed and available for governance cadence (bi-weekly, 45 minutes).

## Ongoing Engagement Responsibilities

SME availability for workshops and validation sessions as scheduled by ECS and Connection Project Manager.

User story acceptance decisions within [3] business days of demo delivery; delays beyond this window may push stories to the backlog for reprioritization and may trigger a PCR

Governance Triage Log review and disposition within [5] business days of ECS submission.

Data quality ownership: Connection is responsible for the accuracy and completeness of data loaded via Accelerator Pack workbooks.

Change Advisory Board participation: Connection CAB members to be available for Change Management configuration workshops in Sprint 4.

UAT execution: Connection assigns and makes available testers with sufficient platform knowledge to execute UAT scenarios within the defined UAT window.

Training and adoption: Connection is responsible for end-user communication, change management, and adoption activities beyond the train-the-trainer sessions delivered by ECS.

Knowledge Content: Connection is responsible for ongoing content creation and maintaining all knowledge / knowledgebase content.

Vonage integration: Connection is responsible for completing the integration tasks on the Vonage side.

ECS will flag any approaching dependency milestone in advance. If a dependency is at risk, ECS and Connection will jointly assess the timeline impact and document it in the sprint workbook before it becomes a delay.

# 7.  Out of Scope

The following items are explicitly excluded from the Phase 1 scope of this SOW. Requirements in any of these categories that emerge during the engagement will be captured in the Governance Triage Log and may be addressed through a Project Change Request or deferred to a subsequent phase.

Any ServiceNow application or module not listed in Section 2.

Custom scripting, modification of protected baseline objects, or creation of custom tables outside of Project Sponsor–approved deviations.

Any third-party integration not explicitly named in Section 2.

Data migration of historical incident, change, or request records (data migration scope, if applicable, is addressed separately).

End-user training delivery beyond train-the-trainer and admin knowledge transfer sessions.

ServiceNow licensing procurement or license advisory (ECS will surface licensing observations but does not act as a licensing agent).

Ongoing platform administration, break-fix, or managed services after the Hypercare period.

Phase 2, Phase 3, or roadmap capabilities identified in Section 14 of this SOW — those phases require a separate SOW.

# 8.  Assumptions

This SOW and the associated timeline are based on the following assumptions. If any assumption proves incorrect or changes during the engagement, ECS will assess the impact and may initiate a PCR discussion.

Connection will have a clean [net-new / dedicated] ServiceNow instance provisioned and ECS-accessible by the start of Sprint 0.

ECS has been granted admin/security admin access to all development and test environments required for this engagement.

The ServiceNow version targeted for this implementation is Australia or later.

All Connection SMEs named for this engagement have authority to make design decisions within their process area, subject to Product Owner acceptance.

The 10-15 catalog items in scope have been prioritized and the top [10–15] are identified and agreed upon by Connection prior to Sprint 2.

Discovery and Service Graph Connector configurations from the existing instance are accessible for review by ECS and Connection SMEs during Sprint 1.

ECS will operate under a fixed-fee model as defined in Section 13. Additional scope is addressed via PCR.

The Project Team will utilize ECS document templates for all project documents/deliverables unless explicitly stated in the SOW or mutually agreed by project team.

Connection will supply Subject Matter Expert(s) for the non-ServiceNow side of relevant in-scope integrations described in this SOW. The Connection Subject Matter Expert(s) is responsible for making any configuration changes or performing any development on the non-ServiceNow side of relevant in-scope integrations.
In the case of a ServiceNow-to-ServiceNow integration, ECS is responsible for the Connection side of the integration and Connection is responsible for the other side of the integration if that ServiceNow environment belongs to a 3rd party.

# 9.  Project Guardrails and PCR Process

ECS and Connection share a mutual interest in protecting the timeline, the agreed budget, and the OOTB-first discipline that makes Phase 1 valuable. The guardrails and Project Change Request (PCR) process below are designed to surface impacts early, preserve transparency, and give both parties the information needed to make sound decisions — not to create friction or assign blame. When a trigger is reached, ECS will raise it as a conversation first and a formal PCR only if the impact cannot be absorbed within the current sprint plan.

## Scope Boundary Definitions

The OOTB Baseline defines the scope specifically as the implementation and configuration of out-of-the-box ServiceNow functionality as defined by ServiceNow Product Documentation for all in-scope applications listed in Section 2.

| Term | Definition |
| --- | --- |
| OOTB Configuration | Use of standard ServiceNow fields, tables, workflows, UI policies, and Flow Designer without modification of baseline objects. |
| Governed Deviation | A delta from OOTB that has been reviewed by the Customization Council, documented in the Governance Triage Log, and approved by the Project Sponsor. |
| Customization | Any requirement that cannot be met by Configuration, UI Policy, or Flow Designer alone. Triggers mandatory technical review and Project Sponsor approval before work begins. |
| Structural Deviation | Use of custom tables instead of standard CI classes, or modification of core platform objects. Requires Project Sponsor approval and automatic escalation to the Customization Council. |
| Project Change Request (PCR) | A formal document initiated by ECS that describes a scope, timeline, or resource impact and proposes a resolution. Both parties must sign a PCR before ECS proceeds with out-of-scope work. |

## PCR Triggers: Customer-Initiated Scope Changes

The following conditions, when initiated by Connection, will trigger a PCR discussion. ECS will document the trigger in writing within [2] business days of identification and schedule a PCR conversation within [3] business days.

Requirements beyond the OOTB Baseline: Any requirement that necessitates custom scripting, modification of protected baseline objects, or creation of custom tables not listed in Section 2. ECS will present the OOTB alternative before raising the PCR.

Expansion of in-scope catalog items: Requests to add catalog items beyond the agreed 10–15 items will be assessed for sprint capacity impact. Items that displace agreed-scope work require a PCR.

Addition of in-scope applications or integrations: Any application, module, or integration not listed in Section 2. No work begins on out-of-scope items without an executed PCR.

Process redesign requests: Requests to redesign an existing OOTB process beyond the configuration decisions captured in workshops. Redesign typically signals a Customization and triggers the Rule of Three review.

Significant volume increases: Material increases in the number and/or complexity of user stories, locations, groups, assignment rules, or catalog taxonomy entries beyond what was baselined in the Accelerator Packs.

Connection requests to re-solution after functionality has been configured based on approved user stories and acceptance criteria

## PCR Triggers: Schedule and Dependency Impacts

The following conditions, regardless of which party initiates them, may trigger a PCR for timeline extension. ECS’s obligation is to flag the risk as soon as it is identified and to work collaboratively on mitigation before formalizing a PCR.

Accelerator Pack data not delivered on time: Foundation Data workbooks (users, locations, groups, SLAs, assignment rules) are required by Sprint 0 to enable build. If completed workbooks are not received within [5] business days of the agreed delivery date, ECS will document the delay and assess the impact of the timeline. Delays that push build start beyond Sprint 1 Week 1 may result in a PCR for timeline and/or fee adjustment.

SME unavailability: If a named SME is unavailable for a scheduled workshop or validation session and no qualified substitute is provided with [2] business days’ notice, ECS will reschedule the session. If repeated unavailability (defined as [2] or more missed sessions in a single sprint) causes sprint goals to slip, ECS will initiate a PCR discussion.

Decision delays: User story acceptance decisions are expected within [3] business days of demo delivery. Governance Triage Log dispositions are expected within [5] business days of ECS submission. Decisions outstanding beyond these windows will be documented in the sprint workbook; accumulated delays that affect the sprint plan trigger a PCR conversation.

Environment or access delays: If provisioned environments or admin credentials are not available as committed and ECS is blocked from building for more than [3] consecutive business days, ECS will document the blockage and assess timeline impact. Sustained blockage may result in a PCR.

Third-party vendor delays: If a third-party vendor (e.g., AD/SSO provider, SCCM/Intune administrator) required for an in-scope integration is not available within the sprint window, ECS will document the dependency and may adjust sprint sequencing. If the delay affects the critical path, a PCR will be initiated.

Executive Sponsor escalation hold: If a governance decision requires Executive Sponsor input and that input is not received within [5] business days of escalation, ECS will document the hold and assess downstream impact.

GUARDRAIL PRINCIPLE: A PCR is not a penalty. It is a shared acknowledgment that circumstances have changed and that ECS and Connection need to agree on how to proceed. ECS will always present mitigation options alongside a PCR trigger — the goal is a decision, not a dispute.

## PCR Process

When a PCR trigger is reached, the following process applies:

| Step | Owner | Timeframe | Action |
| --- | --- | --- | --- |
| 1. Identify | ECS | Within 5 business days of trigger | ECS documents the trigger, the impact assessment, and the proposed resolution in a PCR document. |
| 2. Notify | ECS | Within 1 business day of Step 1 | ECS delivers the PCR document to Connection Project Sponsor and Product Owner. |
| 3. Review | Both parties | Within 3 business days of receipt | Connection reviews the PCR and may request a working session to discuss. |
| 4. Decide | Customer Sponsor | Within 5 business days of receipt | Customer Sponsor approves, modifies, or rejects the PCR in writing. |
| 5. Execute | ECS | Upon PCR execution | No out-of-scope work begins, and no contractual changes are made, prior to PCR execution by both parties. |

PCRs that involve additional fees are subject to the same review and approval process. ECS will not invoice for PCR-related work until the PCR is executed by both parties.

## Governance Triage Log

All scope deviation requests, open questions, and deferred requirements are captured in the Governance Triage Log, a living artifact maintained by ECS and reviewed at each bi-weekly Sponsor Sync. The Log tracks the deviation, its business rationale, scope impact, and disposition (deferred to Phase 2 / approved as Governed Deviation / escalated for PCR). The Log is a feature of this engagement, not a warning sign — it is how both parties protect the baseline and the customer’s legitimate requirements simultaneously.

# 10.  Testing and Acceptance

## Testing Approach

ECS follows a continuous testing model throughout the build sprints, with formal User Acceptance Testing (UAT) conducted in Sprint [7]. Testing phases include:

Unit Testing: ECS consultants validate each configuration against approved user story acceptance criteria before sprint demo.

Sprint Demo Validation: Product Owner reviews configured capability at the end of each sprint and provides formal acceptance based on approved acceptance criteria or identifies defects and/or enhancement requests to be evaluated and prioritized.

Integration Testing: ECS validates end-to-end data flows across integrated systems in Sprint [6–7].

UAT: Connection executes test scenarios against a defined UAT script in the test environment. ECS provides UAT baseline test scripts for validation and/or augmentation by connection  ECS will facilitate UAT sessions.

Defects and Enhancement Requests: Defects and Enhancement Requests will be centrally tracked, triaged and prioritized

Regression Testing: ECS performs regression validation prior to production cutover.

## Acceptance Criteria

A configuration is accepted when the Product Owner confirms, in writing or via the sprint workbook, that all user story acceptance criteria have been met. Defects identified during sprint demos are classified as:

P1 (Blocker): Prevents core process execution. ECS resolves within the sprint.

P2 (Critical): Significant impact to user experience or process; prioritized for potential future sprints.

P3 (Enhancement): Desirable improvement not required for go-live. Captured in the Phase 2 backlog.

Go-live readiness requires Connection sign-off on all P1 and P2 defects as resolved or prioritized for future sprints and written acceptance of the UAT results by the Product Owner and Executive Sponsor.

Scope Classification. The parties agree that all scope-related findings during delivery will be classified as one of the following:

Defect, meaning a delivered configuration that does not perform as documented in approved design artifacts (typically acceptance criteria) or that contradicts ServiceNow’s published platform documentation;

Enhancement, meaning a request to add or modify functionality not described in this SOW or in approved design documentation; or

Missed Requirement, meaning a functional need not captured during discovery or Sprint 0 that was not documented by either party.

Defects identified during the project will be remediated by ECS at no additional charge. Enhancements require a signed Change Order prior to commencement of work. Missed Requirements will be treated as Enhancements by default but will be evaluated jointly by the parties on a case-by-case basis.

# 11.  Organizational Change Management and Training

ECS’s delivery scope includes the following knowledge transfer and enablement activities. Broader organizational change management, end-user communication, and adoption campaigns are Connection’s responsibility.

Admin Knowledge Transfer (KT): 4 remote sessions covering platform administration, update set management, and OOTB governance principles.

Train-the-Trainer sessions: 2 remote sessions per process area enabling Connection’s designated trainers to deliver end-user training.

Process documentation: ECS delivers design documentation per sprint. Connection is responsible for translating these into internal procedures and training materials.

Hypercare support: ECS provides 2 weeks of Hypercare support post-go-live, available during business hours for production issues classified as P1 or P2.

# Hypercare

ECS provides two (2) weeks of dedicated post-go-live Hypercare support, commencing on the agreed go-live date. Support is structured with daily standups in Week 1 stepping down to twice-weekly in Week 2 and closes with a formal exit-criteria review prior to handover to steady-state operations. During this period, Connection's Service Desk manages Level 0–1 incident intake and first-line support. ECS provides Level 2 and above escalation support for ServiceNow-related incidents, available during business hours throughout the Hypercare window.

| IT Support Level | Provider | Function |
| --- | --- | --- |
| Level 0 | Customer | Self-help and user-retrieved information |
| Level 1 | Customer | Basic help desk resolution and service desk delivery |
| Level 2 | ECS | In-depth technical support |
| Level 3 | ServiceNow | Expert product and service support |

Any defects found after go-live, during the post-go-live support, will be corrected by ECS.

Hypercare services are limited to:

Stabilization of the implemented solution as deployed at Go-Live

Resolution of defects attributable to ECS-delivered configuration

Knowledge transfer and operational guidance to Connection personnel

Hypercare services do not include enhancements, or reconfiguration, due to changes in Connection systems, infrastructure, or business processes.

Connection is solely responsible for:

Maintaining the integrity and stability of its production environment

Managing all changes to infrastructure, applications, and configurations

Ensuring required access, credentials, and network conditions remain valid

ECS shall not be responsible for issues arising from changes made by Connection or third parties to the production environment following Go-Live.

Discovered CIs and Service Maps reflect real-time or near-real-time conditions of the underlying IT environment. Changes to infrastructure, application architecture, network configurations, credentials, or discovery patterns may impact the appearance, completeness, or accuracy of Service Maps. Any degradation, alteration, or perceived “breakage” of Service Maps resulting from such changes shall not be considered a defect in the implemented solution.

Any investigation, remediation, or reconfiguration required as a result of Connection initiated or third-party changes to the production environment shall be considered out-of-scope for Hypercare services. Such work may be performed only upon mutual written agreement and may be subject to additional fees, schedule adjustments, or a separate statement of work.

Hypercare services shall conclude automatically at the end of the Hypercare Period.

The expiration of the Hypercare Period is not contingent upon:

Resolution of issues caused by Connection or third-party changes

Ongoing environmental instability

Connection acceptance tied to conditions outside the implemented solution

# 12.  Engagement Governance

## Governance Cadence

| Cadence | Participants | Frequency | Purpose |
| --- | --- | --- | --- |
| Daily Stand-up | ECS delivery team +Connection Product Owner | Daily (15 min) | Sprint progress, blockers, and dependency flags. |
| Sprint Review / Demo | ECS +Connection Product Owner + Process SMEs | Bi-weekly (end of sprint) | Demo of completed stories; formal acceptance or defect logging. |
| Sprint Retrospective | ECS delivery team +Connection Product Owner | Bi-weekly (end of sprint) | Process improvement and sprint planning. |
| Bi-Weekly Sponsor Sync | ECS Engagement Manager +Connection Executive Sponsor | Bi-weekly (45 min) | Schedule health, Governance Triage Log review, PCR decisions. |
| Steering Committee | ECS Practice Lead +Connection Sponsor + Stakeholders | Monthly | Program-level decisions, risk review, roadmap alignment. |

## Roles and Responsibilities

| Role | Party | Responsibilities |
| --- | --- | --- |
| Engagement Manager | ECS | Day-to-day delivery oversight, sprint planning, PCR management, Sponsor Sync facilitation. |
| Solution Architect & Developers | ECS | Technical design authority, OOTB-first discipline, architecture decisions, configuration, Customization Council chair, peer testing |
| Business Analysts & Process Consultants | ECS | Business Process Engineering, SRCUM Master, Workshop facilitation, configuration, user story delivery, sprint workbook maintenance, testing. |
| Executive Sponsor | Connection | PCR approval authority, escalation resolution, program-level decisions, go-live sign-off. |
| Product Owner | Connection | User story acceptance, sprint backlog prioritization, Governance Triage Log dispositions. |
| Process SMEs | Connection | Subject matter input in workshops, UAT execution, knowledge transfer participation. |
| Platform Administrator | Connection | Environment provisioning, access management, post-go-live administration. |
| Integration SMEs | Connection | For all in-scope integrations, Connection to provide SME(s) for the non-ServiceNow side of the integration |

# 13.  Timeline and Pricing

## Phase 1 Timeline

| Phase | Weeks | Key Milestone |
| --- | --- | --- |
| Sprint 0: Initiate & Plan | Week 1–2 | Kickoff, governance established, Accelerator Pack data collected, environments provisioned. |
| Month 1: Foundation & Discovery | Weeks 3–6 | Platform architecture, CSDM, ITSM design, Discovery/Connectors initiated. |
| Month 2: Core Build | Weeks 7–10 | ITSM Core, Change Management, first catalog items. |
| Month 3: Advanced Features | Weeks 11–14 | Employee Experience, HAM, remaining catalog items, environment stabilization. |
| Month 4: Validation & Go-Live | Weeks 15–17 | UAT, Knowledge Transfer, cutover, Hypercare begins. |
| Hypercare | Weeks 1820 | 2-week post-go-live support window. |

## Phase 1 Pricing

| Item | Description | Fee |
| --- | --- | --- |
| Phase 1 Fixed Fee | Delivery of all in-scope capabilities as defined in Section 2, including Sprint 0 through Hypercare. | $325,000 |
| Travel and Expenses | Estimated travel for on-site workshops 1 trip 3 day trip for 3 people.. Actuals billed as incurred. If no travel is expected this can be removed. | $5,000 |
| Out-of-Scope / PCR Work | Billed at the agreed blended rate of $200.00/hour upon executed PCR. | As incurred |
| Phase 1 Total (Estimated) |  | $330,000 |

## Payment Schedule

| Milestone | Payment | Trigger |
| --- | --- | --- |
| Contract Execution | 10% | Upon execution of this SOW. |
| Sprint 0 Complete | 10% | Due at the close of Sprint 0 (end of Week 2), provided ECS has completed all Sprint 0 delivery obligations listed in Section 5, except for any items documented in writing as blocked by Customer action or inaction. |
| Month 1 Complete | 20% | Due at the close of Month 1 (end of Week 6), provided ECS has completed all Month 1 delivery obligations listed in Section 5, except for any items documented in writing as blocked by Customer action or inaction. |
| Month 2 Complete | 20% | Due at the close of Month 2 (end of Week 10), provided ECS has completed all Month 2 delivery obligations listed in Section 5, except for any items documented in writing as blocked by Customer action or inaction. |
| Month 3 Complete | 20% | Due at the close of Month 3 (end of Week 14), provided ECS has completed all Month 3 delivery obligations listed in Section 5, except for any items documented in writing as blocked by Customer action or inaction. |
| Go-Live – Hypercare completion | 20% | Due at the close of Month 4 (end of Week 18), provided ECS has completed all Final Month delivery obligations listed in Section 5, except for any items documented in writing as blocked by Customer action or inaction. |

# 14.  Long-Term Roadmap: Beyond Phase 1

Phase 1 delivers the OOTB baseline that unlocks Connection’s full ServiceNow investment. The following phases are not in scope for this SOW and will be addressed in separate engagements but are summarized here to provide Connection’s leadership with a view of the full value trajectory.

## Phase 2: Baseline Expansion and Enhanced User Experience

Expanded Service Catalog: Additional catalog items and directed workflows for services captured in the Phase 1 generic workflow buckets.

Enhanced Virtual Agent: Additional topic coverage and integration with backend systems.

Broader HAM Realization: Full asset lifecycle, procurement integration, and disposal workflows.

Governed Deviations Backlog: Triage Log items deferred from Phase 1 assessed for implementation.

## Phase 3: ITOM and Intelligence

Event Management foundations and AIOps integration.

Service Mapping and Business Service topology.

Advanced Predictive Intelligence models and Task Intelligence tuning.

Now Assist and Agentic Agents activation.

## Phase 4 and Beyond: Full AI Realization

Workflow Data Fabric integration.

Cross-domain automation and orchestration.

Continuous platform optimization and innovation cadence.

Each phase builds directly on the OOTB foundation established in Phase 1. Skipping or compromising the baseline in Phase 1 creates rework in every subsequent phase. The investment in OOTB discipline now is the investment in AI realization later.

# 15.  Terms and Conditions

This SOW is pursuant to the Terms and Conditions VERSION: 1.0 dated 5/25/2023 which can be viewed at: https://ecstech.com/ecs-servicenow-tcs/

# 16.  Signature Block

By signing below, both parties agree to the terms, scope, and conditions set forth in this Statement of Work.

| ECS Federal | Connection |
| --- | --- |
| Signature: ________________________ | Signature: ________________________ |
| Name: ____________________________ | Name: ____________________________ |
| Title: ____________________________ | Title: ____________________________ |
| Date: _____________________________ | Date: _____________________________ |

Project Sponsor Acknowledgment (Connection) — The Project Sponsor named below confirms their availability and authority as described in Section 6 and Section 9 of this SOW.

Project Sponsor Acknowledgment

Signature: ________________________

Name: ____________________________

Title: ____________________________

Date: _____________________________

# Acronyms & Definitions

| Acronym | Term | Definition |
| --- | --- | --- |
| AD | Active Directory | Microsoft's directory service that manages user identities, passwords, and access permissions across an organization's network. |
| CAB | Change Advisory Board | A governance body that reviews and approves significant IT changes before they go live, to minimize risk and disruption. |
| CI | Configuration Item | Any component — hardware, software, document, or service — tracked in the CMDB as part of the IT environment. |
| CMDB | Configuration Management Database | A centralized repository storing information about all IT assets and the relationships between them. |
|  | Configuration | Adjusting platform behavior using supported, upgrade-safe capabilities and standard platform tools without fundamentally altering core platform behavior. |
| CSDM | Common Service Data Model | ServiceNow's standardized framework for organizing business services, applications, and infrastructure so data in the CMDB is clean and AI-ready. |
|  | Customization | Altering, extending, or overriding platform functionality in ways that go beyond standard supported configuration patterns. If a requirement cannot be met by (1) Configuration, (2) UI Policy, or (3) Flow Designer, it is treated as a Customization. |
|  | Customization Council | Cross-functional governance body chaired by ECS SA reviewing OOTB deviations. |
|  | Defect | A failure of the implemented solution to perform materially in accordance with the approved requirements, user stories, acceptance criteria, design documentation, or agreed solution behavior that existed at the time of production deployment. |
| ECS | Everforth Consulting Services | The consulting practice delivering this ServiceNow engagement (also referred to as ECS Federal). |
|  | Enhancement | Any requested modification, expansion, redesign, optimization, or new functionality that changes the originally approved scope, requirements, workflows, integrations, user experience, business logic, infrastructure assumptions, or operational behavior of the implemented solution. |
| HAM | Hardware Asset Management | The discipline of tracking physical IT assets — laptops, servers, peripherals — throughout their full lifecycle from purchase to disposal. |
| ITSM | IT Service Management | The set of practices and processes used to design, deliver, manage, and continuously improve IT services for the organization. |
| KM | Knowledge Management | The practice of creating, organizing, and publishing articles and known solutions so employees and agents can quickly find answers without opening a ticket. |
| KT | Knowledge Transfer | Structured training sessions where the delivery team teaches customer administrators and process owners how to operate and maintain the platform after go-live. |
| MSA | Master Services Agreement | A standing contract that establishes the legal terms governing all work between two organizations, under which individual Statements of Work are issued. |
| MTTR | Mean Time to Resolution | The average time it takes to fully resolve an incident or service disruption from the moment it is reported to the moment it is closed. |
| MVP | Minimum Viable Platform | The smallest complete set of configured capabilities that meets go-live acceptance criteria and delivers real operational value — without scope creep. |
| NDA | Non-Disclosure Agreement | A legal contract requiring both parties to keep shared confidential information private and not disclose it to unauthorized third parties. |
| OCM | Organizational Change Management | The structured approach to preparing, supporting, and guiding people through process and technology changes to maximize adoption and minimize resistance. |
| OOTB | Out of the Box | ServiceNow's native, uncustomized functionality exactly as delivered by ServiceNow — the baseline before any customer-specific modifications are applied. The "OOTB Baseline" defines the scope specifically as the implementation and configuration of out-of-the-box ServiceNow functionality as defined by the ServiceNow Product Documentation for the installed release for all in-scope applications. |
| PA | Platform Analytics | ServiceNow's built-in reporting and dashboarding capability that surfaces real-time operational metrics, trends, and performance insights. |
| PCR | Project Change Request | A formal document submitted when scope, timeline, or budget needs to change; requires written approval from both parties before additional work proceeds. |
| PI | Predictive Intelligence | ServiceNow's machine learning feature that automatically categorizes, routes, and suggests resolutions for incoming incidents and requests. |
| SAM | Software Asset Management | The practice of tracking and managing software licenses to ensure compliance with vendor agreements and eliminate unnecessary spend. |
| SCCM | System Center Configuration Manager (Microsoft) | Microsoft's endpoint management tool used as a discovery source to populate hardware and software inventory in the CMDB. |
| SLA | Service Level Agreement | A formal commitment defining how quickly a service request or incident will be acknowledged and resolved, used to measure service team performance. |
| SME | Subject Matter Expert | A customer team member with deep knowledge in a specific process area, empowered to make design decisions for that domain during workshops. |
| SOW | Statement of Work | The contractual document defining the scope, deliverables, timeline, responsibilities, and fees for a specific engagement. |
| SSO | Single Sign-On | An authentication method that allows users to log into multiple applications using one set of credentials, improving security and user experience. |
|  | Technical Debt | Accumulated platform complexity from customizations that increase maintenance cost and reduces upgrade safety. |
| UAT | User Acceptance Testing | The final testing phase where the customer validates that all configurations meet their requirements and acceptance criteria before go-live sign-off. |
| VA | Virtual Agent | ServiceNow's conversational AI chatbot embedded in the Employee Center that handles common requests automatically, deflecting tickets from the service desk. |