## Instructions
01 — Discovery Scope & IP Ranges
Discovery Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Discovery scope: which IP ranges are in scope, which subnets are excluded, and the phasing strategy for rolling Discovery across the environment. Scope decisions made here directly control what CI data populates in Sprint 2 and what remains out of scope for Phase 2.
Who fills this out | Customer-side: Network/Infrastructure Lead provides IP range documentation. IT Operations Manager approves the scope. ECS Architect reviews for Discovery feasibility.
Sprint window | Sprint 1 Week 2 — Sprint 2 Week 1
Estimated effort | 2–3 hours to gather and document network topology
Related workbooks | 02 MID Server Configuration · 03 Credential Management · CMDB-CSDM Pack — CI Class Selection
Success criteria
• | All in-scope IP ranges are documented with CIDR notation.
• | Excluded subnets are listed with rationale (DMZ, OT networks, etc.).
• | Phase 1 vs Phase 2 scope boundary is agreed.
• | Estimated device count per subnet is provided.
• | Network team has confirmed Discovery traffic is permitted on in-scope ranges.

## Process Decisions
01 — Discovery Scope & IP Ranges — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should we discover everything on the network or a scoped subset? | Start with a scoped subset: corporate LAN subnets housing servers and workstations managed by IT. Exclude DMZ, OT/SCADA, guest Wi-Fi, and printer networks from Phase 1. |  | Discovering everything creates thousands of stub CI records for unmanaged devices. A scoped approach produces accurate data for the CIs that matter and avoids polluting the CMDB with noise.
2 | How should we handle cloud-hosted resources in the Discovery scope? | Exclude cloud resources from IP-range Discovery. Use Service Graph Connectors or Cloud Management for cloud CIs. IP-range Discovery was designed for on-prem networks. |  | IP-range Discovery of cloud VPCs requires VPN connectivity and produces unreliable results. OOTB SGCs (AWS, Azure) are the authoritative source for cloud CIs.
3 | What happens to devices Discovery finds but that are not in the agreed CI class scope? | Discovery finds them but IRE rules prevent CI creation for out-of-scope classes. Configure IRE to skip creation for out-of-scope classes rather than creating stub records. |  | Stub records for out-of-scope devices (printers, phones, IoT) are harder to clean up than preventing their creation. Configure IRE exclusion rules before the first Discovery run.
4 | How often should Discovery run? | Weekly for servers and workstations. Daily for critical infrastructure CIs. SGC syncs can run more frequently (every 4–6 hours for SCCM/Intune). Do not run Discovery continuously — it generates significant network traffic. |  | Weekly Discovery provides a 7-day staleness window which is within the 30-day threshold. Daily runs are reserved for environments with high CI turnover (e.g., VDI pools).

## Dependencies
01 — Discovery Scope & IP Ranges — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Network topology document (IP ranges, VLANs, subnets) | Required | Customer Network Lead | Sprint 1 Wk 2 | Cannot scope Discovery without network documentation.
2 | Network team approval for Discovery traffic on in-scope subnets | Required | Customer Network Lead | Sprint 1 Wk 2 | Discovery generates ICMP, WMI, SSH, and SNMP traffic. Security team must approve.
3 | CMDB-CSDM CI Class Selection (Workbook 02) confirmed | Required | ECS SA | Sprint 1 Wk 2 | Discovery scope must align with agreed CI classes.

## Configuration Data
01 — Discovery Scope & IP Ranges — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. In-Scope IP Ranges
Corporate LAN — servers | [Customer: CIDR notation, e.g. 10.10.0.0/24] | Primary server subnet.
Corporate LAN — workstations | [Customer: CIDR notation] | End-user device subnets.
DMZ | Excluded — Phase 2 if required | DMZ devices require separate credential set and security approval.
Guest Wi-Fi | Excluded permanently | Guest devices are not IT-managed and should not appear in CMDB.
OT/SCADA networks | Excluded permanently | OT networks must never be scanned without explicit OT team approval.
Cloud (AWS/Azure) | Excluded — use SGC instead | Handled by Service Graph Connectors, not IP-range Discovery.
2. Phasing
Phase 1 (Sprint 2) | [Customer: list subnets] | Start with server subnet; add workstation subnet after first validation.
Phase 2 (post-Sprint 2) | [Customer: list subnets] | Remaining in-scope subnets after Phase 1 is validated.
Estimated device count — Phase 1 | [Customer: estimate] | Used to size MID Server and validate Discovery results.

## R&R
01 — Discovery Scope & IP Ranges — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Provide IP range and network topology documentation | I | R/A | Customer Network Lead.
Approve Discovery traffic on in-scope subnets | I | R/A | Customer Network/Security team.
Configure Discovery scope in ServiceNow | R/A | I | ECS Architect.
Validate first Discovery run — device counts plausible | R | A | ECS validates; customer confirms counts.

## Consultant Guide
01 — Discovery Scope & IP Ranges — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Scope conversation
The most common scope mistake is including too many subnets in Phase 1. Start with the server subnet only. A successful server Discovery in week 1 builds confidence. Workstation Discovery can be added in week 2 once credentials and MID Server are validated.
OT/SCADA boundary
Never agree to discover OT networks without explicit sign-off from both the OT team and the CISO. OT equipment (PLCs, SCADA controllers) can be destabilized by network scanning. This is a safety issue, not just a scope issue.

## Adoption vs Re-engineering
01 — Discovery Scope & IP Ranges — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to discover everything — all subnets, all devices | Phase 1 scope to managed IT subnets. Phase 2 expands after validation. | Discovering everything in Sprint 2 creates thousands of CI records for unmanaged devices before governance is in place. Scope creep at Discovery is CMDB health debt. | 'Discovering everything at once means your first CMDB report will be full of printers, phones, and IoT devices that nobody is responsible for. Let's start with what IT manages, prove the model works, then expand. You get a trusted CMDB faster with a narrower start.' | Never expand scope without confirming governance (data steward, staleness process) is in place.

## ServiceNow Mapping
01 — Discovery Scope & IP Ranges — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Discovery Configuration
Discovery Schedule | Discovery > Discovery Schedules | One schedule per phase. Set IP ranges, frequency, and MID Server.
Discovery Status | Discovery > Discovery Status | Monitor active Discovery runs and errors here.
Excluded IP Ranges | Discovery > Exclusion Lists | Configure excluded subnets before the first Discovery run.