## Instructions
04 — Discovery Schedules & Patterns
Discovery Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Discovery schedule configuration: schedule names, IP ranges, MID Server assignment, frequency, and the Discovery patterns activated for each in-scope CI class. Pattern selection determines what attributes are collected — activating unnecessary patterns wastes MID Server resources and slows Discovery.
Who fills this out | ECS Architect completes this workbook based on decisions from Workbooks 01–03. Customer IT Ops reviews the schedule plan and confirms frequency is acceptable.
Sprint window | Sprint 2 Week 1
Estimated effort | 2–3 hours to configure schedules and validate patterns in non-prod
Related workbooks | 01 Discovery Scope · 02 MID Server Configuration · 03 Credential Management
Success criteria
• | At least one Discovery schedule is configured and validated for in-scope subnets.
• | Only required Discovery patterns are activated (no pattern sprawl).
• | First Discovery run completes without critical errors.
• | CI counts from first run are within expected range (validated against network team estimate).
• | Discovery log is reviewed and any authentication failures are documented.

## Process Decisions
04 — Discovery Schedules & Patterns — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should we use Quick Discovery or full Horizontal Discovery? | Horizontal Discovery for the primary run (discovers full CI attributes). Quick Discovery for validation checks only — it identifies what devices are on the network but does not collect full attribute data. |  | Horizontal Discovery is the OOTB pattern that populates CI attributes. Quick Discovery is a reconnaissance tool, not a data collection tool. Many customers confuse them — only Horizontal Discovery populates CIs.
2 | Which Discovery patterns should be activated at MVP? | Activate only: Windows OS pattern (for servers and workstations), Linux OS pattern (if Linux in scope), VMware Infrastructure pattern (if virtualised), Software (Installed) pattern (for cmdb_ci_appl population via Discovery). Deactivate: Network Gear, Storage, Printer patterns unless those classes are in scope. |  | Every activated pattern runs on every device in scope. Activating Network Gear patterns on a workstation subnet generates thousands of failed probes. Pattern selection must match CI class scope from the CMDB-CSDM pack.
3 | How should Discovery handle devices that fail authentication? | Log authentication failures in Discovery Status. Review weekly — authentication failures mean a device was found on the network but credentials did not work. These are either out-of-scope devices or a credential issue. Do not create CI records for devices that fail all authentication attempts. |  | Authentication failure logs are the most useful diagnostic tool for Discovery health. Review them after every Discovery run in the first 4 weeks to confirm credential coverage is complete.

## Dependencies
04 — Discovery Schedules & Patterns — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | MID Server validated (Workbook 02) | Required | ECS Architect | Sprint 2 Wk 1
2 | Credentials configured (Workbook 03) | Required | ECS Architect | Sprint 2 Wk 1
3 | Discovery scope confirmed (Workbook 01) | Required | Customer + ECS | Sprint 1 Wk 2

## Configuration Data
04 — Discovery Schedules & Patterns — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Discovery Schedules
Schedule 1 — Name | ECS_Phase1_Servers
Schedule 1 — IP range | [Server subnet CIDR from Workbook 01]
Schedule 1 — Frequency | Weekly (Sunday 02:00 AM) | Run during low-traffic period.
Schedule 1 — MID Server | [MID Server hostname from Workbook 02]
Schedule 2 — Name | ECS_Phase1_Workstations
Schedule 2 — IP range | [Workstation subnet CIDR]
Schedule 2 — Frequency | Weekly (Saturday 23:00) | Run after server schedule completes.
2. Activated Patterns (MVP)
Windows OS — Horizontal | Active | Populates cmdb_ci_server, cmdb_ci_computer, cmdb_ci_network_adapter.
Linux OS — Horizontal | Active if Linux in scope / Inactive otherwise
VMware Infrastructure | Active if VMware in scope / Inactive otherwise | Populates cmdb_ci_vm_instance.
Software (Installed) | Active | Populates cmdb_ci_appl from installed software inventory.
Network Gear | Inactive — Phase 2 | Activate only if network devices are in CI class scope.
Storage | Inactive — Phase 2
Printer | Inactive — permanently excluded | Printers are not in scope.

## R&R
04 — Discovery Schedules & Patterns — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure Discovery schedules in ServiceNow | R/A | I | ECS Architect.
Activate/deactivate Discovery patterns per scope | R/A | I | ECS Architect.
Run first Discovery and review results | R/A | C | ECS Architect runs; customer IT Ops reviews device counts.
Review authentication failure log | R/A | C | ECS reviews; customer confirms out-of-scope devices.

## Consultant Guide
04 — Discovery Schedules & Patterns — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
First Discovery run review
After the first Discovery run, export and review: (1) CI count by class — does it match the customer's estimate? (2) Authentication failure list — any in-scope devices that failed? (3) Pattern probe errors — any patterns that found no targets? This 30-minute review after the first run is the most valuable time investment in the Discovery sprint.

## Adoption vs Re-engineering
04 — Discovery Schedules & Patterns — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want Discovery to run continuously (always-on) | Schedule Discovery weekly. Continuous Discovery is not an OOTB option and would generate excessive network traffic. | Continuous Discovery would generate WMI and SSH connections on every device every few minutes. This creates significant network overhead and is not supported by ServiceNow. | 'Weekly Discovery gives you a 7-day staleness window — which is well within the 30-day threshold. If you need faster updates for specific critical servers, we can run a daily schedule targeting just those servers by IP. That gives you the freshness where it matters without the overhead everywhere.' | Daily schedule for critical infrastructure is acceptable. Never continuous.

## ServiceNow Mapping
04 — Discovery Schedules & Patterns — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Discovery Configuration Tables
Discovery Schedule | discovery_schedule | One record per Discovery schedule.
Discovery Status | discovery_status | Tracks active and completed Discovery runs.
Discovery Log | discovery_log | Authentication failures, probe errors, CI creation events.
ECC Queue | ecc_queue | MID Server probe results queue. Review for errors during first run.