## Instructions
05 — Service Graph Connector Configuration
Discovery Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the configuration for SCCM and Intune Service Graph Connectors — the primary data source for endpoint CI data (cmdb_ci_computer) and installed application CIs (cmdb_ci_appl). SGC is preferred over agentless Discovery for endpoints because SCCM/Intune data is more comprehensive and more reliable than WMI probes on roaming devices.
Who fills this out | ECS Architect configures SGC; customer SCCM/Intune admins provide API credentials and validate device counts after the first sync.
Sprint window | Sprint 2 Weeks 1–2
Estimated effort | 4–6 hours per connector for initial configuration and validation
Related workbooks | 03 Credential Management · CMDB-CSDM Pack — CI Class Selection
Success criteria
• | SCCM SGC is installed, configured, and first sync completed successfully.
• | Intune SGC is installed, configured, and first sync completed successfully.
• | CI count from SGC syncs matches SCCM/Intune device inventory (within 5% tolerance).
• | Duplicate CI prevention rules (IRE) are validated — SGC and Discovery do not create duplicates.
• | Sync schedule is configured and documented.

## Process Decisions
05 — Service Graph Connector Configuration — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should we use SCCM SGC, Intune SGC, or both? | Both if the environment uses both management platforms. SCCM for domain-joined managed workstations; Intune for modern-managed (Azure AD joined) devices. They use different identifiers — configure both and rely on IRE deduplication. |  | Environments moving from SCCM to Intune frequently have devices managed by both simultaneously. Using both SGCs ensures complete coverage during the transition period.
2 | Should SGC replace Discovery for endpoints or complement it? | SGC is the primary source for endpoint CIs. Agentless Discovery is the primary source for servers. Do not run both on the same device — IRE will deduplicate, but the redundant data creates probe noise. |  | SGC produces richer endpoint data than WMI Discovery because SCCM/Intune already collect comprehensive hardware inventory. Using SGC for endpoints and Discovery for servers divides the data collection work by the tool best suited for each CI type.
3 | How frequently should SGC syncs run? | Every 4–6 hours for SCCM (incremental sync — only changed devices). Daily full sync as a baseline. Intune SGC can run more frequently as it uses a lightweight Microsoft Graph API call. |  | Frequent incremental syncs keep endpoint CIs current without the overhead of full syncs. A 4-hour window means endpoint CIs are at most 4 hours stale — well within the 30-day staleness threshold.

## Dependencies
05 — Service Graph Connector Configuration — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | SCCM API credentials configured (Workbook 03) | Required | Customer SCCM Admin | Sprint 2 Wk 1
2 | Intune Azure AD app registration (Workbook 03) | Required | Customer Azure Admin | Sprint 2 Wk 1
3 | IntegrationHub licence confirmed | Required | ECS Architect | Sprint 1 | SGCs require IntegrationHub. Confirm licence before configuring.
4 | MID Server validated (Workbook 02) | Required | ECS Architect | Sprint 2 Wk 1 | SGC runs through the MID Server.

## Configuration Data
05 — Service Graph Connector Configuration — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. SCCM SGC Configuration
SCCM site server hostname | [Customer to complete]
SCCM WMI namespace | root\SMS\site_[site code] | Replace [site code] with customer's SCCM site code.
SCCM sync frequency | Incremental: every 4 hours / Full: daily at 01:00
SCCM CI classes populated | cmdb_ci_computer, cmdb_ci_appl (managed software), cmdb_ci_network_adapter
MID Server for SCCM SGC | [MID Server hostname from Workbook 02]
2. Intune SGC Configuration
Azure AD Tenant ID | [Customer to complete]
Azure AD App Client ID | [Customer to complete]
Intune sync frequency | Every 6 hours
Intune CI classes populated | cmdb_ci_computer (modern-managed devices)
IRE deduplication key between SCCM and Intune | Serial number + OS | IRE uses serial number to deduplicate CIs found by both SGCs.
3. IRE Deduplication Rules
Deduplication between SCCM SGC and Discovery | Active — serial number + hostname | IRE prevents duplicate CI creation when both sources find the same device.
Deduplication between SCCM and Intune SGC | Active — serial number + OS
Source priority (in case of conflict) | SCCM > Intune > Discovery | SCCM data takes precedence for domain-joined devices.

## R&R
05 — Service Graph Connector Configuration — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Provide SCCM site server details and WMI namespace | I | R/A | Customer SCCM Admin.
Create Azure AD app registration for Intune SGC | C | R/A | Customer Azure Admin.
Install and configure SCCM SGC in ServiceNow | R/A | I | ECS Architect.
Install and configure Intune SGC in ServiceNow | R/A | I | ECS Architect.
Validate first SGC sync — CI counts match SCCM/Intune inventory | R | A | ECS validates counts; customer SCCM/Intune admin confirms source counts.
Configure IRE deduplication rules | R/A | I | ECS Architect.

## Consultant Guide
05 — Service Graph Connector Configuration — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
SGC vs. Discovery for endpoints
The most important sequencing decision: configure SCCM/Intune SGC before running Discovery on workstation subnets. If Discovery runs first and creates computer CIs, SGC will create duplicates that IRE must resolve. SGC first means Discovery can be scoped to server-only subnets and the workstation CI data comes entirely from the more reliable SCCM/Intune source.
IntegrationHub licence check
SGCs require IntegrationHub. Confirm this licence is active before Sprint 2 begins. IntegrationHub licensing issues are a common Sprint 2 blocker that ECS cannot resolve without customer involvement with their ServiceNow account team.

## Adoption vs Re-engineering
05 — Service Graph Connector Configuration — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to use SCCM/Intune data but keep Discovery running on workstations too | Use SGC as the primary source for endpoints. Exclude workstation subnets from Discovery schedules. | Running both on the same devices creates IRE merge conflicts and doubles the data collection overhead. SGC data from SCCM is more complete than WMI Discovery for endpoints. | 'SCCM already has everything Discovery would find — and more. Hardware inventory, installed software, patch status. Running Discovery on top of SCCM data is duplicate work. We'll use SCCM for endpoints and Discovery for servers — each tool doing what it does best.' | Only if the customer has specific servers that must come from SGC rather than Discovery. Design with ECS Architect.

## ServiceNow Mapping
05 — Service Graph Connector Configuration — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. SGC Tables
SGC Data Source | sn_disco_datasource | Registered SGC data sources.
SGC Transform Map | sys_transform_map | Maps SCCM/Intune data to ServiceNow CI fields.
IntegrationHub Flow | Flow Designer > SGC Flows | Orchestrates the SGC sync process.