## Instructions
01 — EC Portal Design Decisions
Employee Center Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the foundational Employee Center portal design decisions: single vs. multi-catalog, branding approach, navigation structure, and homepage layout. These decisions cascade into every subsequent EC configuration workbook and must be agreed before any portal build begins.
Who fills this out | ECS SA facilitates; Customer IT Director and HR representative approve the portal design. Communications or Marketing team provides branding inputs.
Sprint window | Sprint 5 Week 1
Estimated effort | 2–3 hours (one design workshop)
Related workbooks | 02 Topic Taxonomy · 03 Homepage Layout · Service Catalog Pack · Knowledge Pack
Success criteria
• | Multi-catalog vs. single-catalog decision made and documented.
• | Portal branding (logo, primary color, font) confirmed by Communications/Marketing.
• | Navigation structure agreed (top nav items and their order).
• | Homepage sections and their content sources defined.
• | Mobile optimization requirement confirmed (Employee Center is mobile-native).

## Process Decisions
01 — EC Portal Design Decisions — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should Employee Center use a single catalog or separate IT and HR catalogs? | Separate catalogs if HR is in scope. OOTB Employee Center natively supports multi-catalog with a unified search experience. IT Catalog and HR Catalog display as separate topic groups on the homepage. |  | Mixing IT and HR items in one catalog creates fulfillment routing complexity and confuses employees who expect different experiences for IT requests vs. HR transactions. Multi-catalog is the OOTB design pattern for Employee Center.
2 | Should we use OOTB Employee Center branding or customise to match the corporate brand? | Apply corporate primary color and logo using OOTB branding settings. Do not customise EC CSS or page layouts. OOTB themes are upgrade-safe; custom CSS breaks on every EC upgrade. |  | Employee Center has an OOTB theming engine that handles color, logo, and font without touching CSS. Custom CSS applied outside the theme engine is overwritten by ServiceNow upgrades and requires remediation every release cycle.
3 | What should appear in the top navigation of Employee Center? | OOTB top nav items: Home, Catalog (or IT Services / HR Services if multi-catalog), Knowledge, My Requests, Approvals. Do not add custom nav items for MVP — the OOTB nav covers every user need. |  | Custom top nav items require portal widget customisation. The OOTB nav is well-understood by employees from other ServiceNow deployments and requires no training. Additions should be driven by post-launch analytics, not assumptions.
4 | Should Employee Center be the single entry point or coexist with a legacy portal? | Employee Center as the single entry point. Redirect legacy portal URLs to EC on go-live. Dual-portal operation creates user confusion and doubles the maintenance burden. |  | Customers who run EC alongside a legacy portal for a 'transition period' typically end up with both portals active indefinitely as the cutover deadline slips. Set a hard cutover date on go-live day.

## Dependencies
01 — EC Portal Design Decisions — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Service Catalog category structure (Catalog Pack Workbook 01) | Required | ECS SA | Sprint 4 | EC homepage topic groups mirror catalog categories.
2 | Knowledge Base structure (Knowledge Pack Workbook 01) | Required | ECS SA | Sprint 5 Wk 1 | EC homepage surfaces KB articles.
3 | Corporate brand guidelines (logo, primary colour, font) | Required | Customer Communications | Sprint 5 Wk 1
4 | HR catalog scope decision | Required | Customer HR Director | Sprint 5 Wk 1 | Determines single vs. multi-catalog architecture.

## Configuration Data
01 — EC Portal Design Decisions — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Portal Architecture
Catalog architecture | [Single catalog / Multi-catalog (IT + HR)] | Multi-catalog recommended if HR is in scope.
Legacy portal cutover date | [Go-live date — redirect legacy portal on this date] | Hard cutover, no dual-portal period.
Mobile optimization | Yes — OOTB (Employee Center is mobile-native) | No additional configuration required.
2. Branding Configuration
Portal name | [Customer to complete — e.g., 'IT Support Center']
Primary color (hex) | [Customer: corporate primary color] | Applied to header, buttons, and nav highlights.
Logo file | [Customer: PNG, 200x60px recommended] | Upload in EC Branding settings.
Font | [Customer: corporate font or 'default OOTB'] | OOTB font is clean and accessible. Custom fonts require font file upload.
3. Top Navigation
Nav item 1 | Home | OOTB — do not rename.
Nav item 2 | IT Services (or Catalog if single) | Rename to match catalog name.
Nav item 3 (if multi-catalog) | HR Services | Only if HR catalog is in scope.
Nav item 4 | Knowledge | OOTB — links to Employee Self-Service KB.
Nav item 5 | My Requests | OOTB — shows user's open requests and approvals.

## R&R
01 — EC Portal Design Decisions — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Facilitate EC design workshop | R/A | C | ECS SA.
Provide corporate branding assets | I | R/A | Customer Communications/Marketing.
Approve portal architecture and navigation | I | R/A | Customer IT Director + HR Director.
Configure EC branding in ServiceNow | R/A | I | ECS SA.
Configure navigation structure | R/A | I | ECS SA.
Set redirect from legacy portal to EC | R/A | C | ECS SA configures; customer web team assists if URL is external.

## Consultant Guide
01 — EC Portal Design Decisions — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The dual-portal trap
The most common EC deployment failure is running Employee Center alongside a legacy Service Portal indefinitely. Customers promise a 'parallel run for 4 weeks' that stretches to 12 months. Set a hard cutover date: Employee Center launches on Day X, the legacy portal redirects to EC on Day X. There is no parallel run. Communicate this to the customer in Sprint 5 Week 1 so they can plan their user communications.
Branding scope management
Customers frequently want to match Employee Center exactly to their corporate intranet — custom fonts, custom page layouts, custom widgets. Set the boundary early: OOTB theming handles color, logo, and font. Everything beyond that is a customisation that requires upgrade maintenance. A simple question to ask: 'Is the portal for IT self-service or a brand showcase?' The answer is always self-service.

## Adoption vs Re-engineering
01 — EC Portal Design Decisions — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to heavily customise the EC portal layout and widgets | Apply OOTB branding (color, logo, font). Use OOTB homepage sections and widgets. | Custom EC widgets and layouts are overwritten by every ServiceNow upgrade. The OOTB EC layout is the result of extensive UX research — it performs well without customisation. | 'Every custom widget you add is a widget we need to re-test after every ServiceNow upgrade — typically 3 times a year. The OOTB EC layout performs well out of the box. Let us launch with OOTB and use actual analytics from your users to justify any specific customisations. That way the customisation budget goes where it actually matters.' | Custom widgets are acceptable for genuinely unique content types (e.g., an IT health status dashboard embedded on the EC homepage). Scope explicitly and plan for upgrade maintenance.

## ServiceNow Mapping
01 — EC Portal Design Decisions — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Employee Center Configuration
EC Portal | sn_hr_sp_portal | Employee Center portal record.
EC Branding | Employee Center > Administration > Branding | Configure color, logo, and font here.
EC Navigation | Employee Center > Administration > Navigation | Configure top nav items and order.
Multi-catalog | Service Catalog > Catalogs | One record per catalog. EC surfaces all active catalogs.