## Instructions
03 — Homepage Layout & Content Blocks
Employee Center Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Employee Center homepage layout: which OOTB content blocks appear, in what order, and what content they surface. The homepage is the first thing every employee sees when they visit the portal — it must communicate value immediately and route users to the right place in two clicks.
Who fills this out | ECS SA designs the layout; Customer IT Director approves. Communications team provides any featured announcement content.
Sprint window | Sprint 5 Week 1–2
Estimated effort | 2 hours (layout design + content block configuration)
Related workbooks | 01 EC Design Decisions · 02 Topic Taxonomy
Success criteria
• | Homepage uses only OOTB content blocks (no custom widgets).
• | Homepage loads in under 3 seconds (validate in non-prod).
• | Hero section has a clear CTA (search bar is always prominent).
• | Announcements block is configured and the first announcement is drafted.
• | Popular items block surfaces the top 5 catalog items by volume.

## Process Decisions
03 — Homepage Layout & Content Blocks — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What OOTB homepage blocks should be included at MVP? | Recommended OOTB homepage blocks in order: (1) Hero with search bar, (2) Topic tiles (6 topics), (3) Popular catalog items, (4) Announcements/Featured news, (5) Recent items (user's recent requests). Do not add more blocks at MVP. |  | Five blocks is the OOTB maximum for a homepage that loads quickly and does not overwhelm users. Analytics from the first 60 days post-launch should drive any additions — not assumptions.
2 | Should we show personalized content on the homepage? | Yes — use OOTB personalisation: 'Recent Items' shows the user's recent requests and approvals. 'Recommended Items' shows catalog items popular with similar users. Both are OOTB and require no configuration. |  | OOTB personalisation drives repeat usage. Users who see their recent requests on the homepage return to check status more often than users who have to navigate to My Requests. This reduces 'where is my request?' helpdesk calls.
3 | Who manages homepage announcements? | Assign a named announcement manager (ITSM Process Owner or Communications representative). Use the OOTB Announcement record with start/end dates — announcements automatically appear and disappear without manual intervention. |  | Announcements without end dates accumulate on the homepage and eventually become noise that users ignore. OOTB start/end dates are the self-cleaning mechanism for announcements.

## Dependencies
03 — Homepage Layout & Content Blocks — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | EC branding configured (Workbook 01) | Required | ECS SA | Sprint 5 Wk 1
2 | EC topics configured (Workbook 02) | Required | ECS SA | Sprint 5 Wk 1

## Configuration Data
03 — Homepage Layout & Content Blocks — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Homepage Block Configuration
Block 1 — Hero with search | OOTB Hero block — search bar centered, tagline text | Configure tagline text to match portal name.
Block 1 — Tagline text | [Customer to complete — e.g., 'How can we help you today?']
Block 2 — Topic tiles | OOTB Topic Tiles block — shows 6 EC topics | Topics from Workbook 02.
Block 3 — Popular items | OOTB Popular Items block — top 5 by view count | Auto-populated from catalog usage data.
Block 4 — Announcements | OOTB Announcement block — active announcements with dates
Block 5 — Recent items | OOTB Recent Items — user's last 5 requests/approvals | Personalised. No configuration needed.
2. Announcement Configuration
Announcement manager | [Customer to complete] | Named individual responsible for announcements.
First announcement (for go-live) | [Customer to draft — EC launch announcement] | Announce the new portal to employees. Include link to KB article explaining how to use it.
Default announcement duration | 30 days maximum | All announcements must have an end date.
Announcement approval | Announcement manager approves before publish | No workflow needed — KM/AM publishes directly.

## R&R
03 — Homepage Layout & Content Blocks — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Design homepage block layout | R/A | C | ECS SA designs; customer IT Director approves.
Write homepage tagline text | C | R/A | Customer Communications.
Configure OOTB homepage blocks | R/A | I | ECS SA.
Draft go-live announcement | C | R/A | Customer ITSM PO or Communications.
Validate homepage load time in non-prod | R/A | I | ECS SA.
Assign announcement manager | I | R/A | Customer IT Director.

## Consultant Guide
03 — Homepage Layout & Content Blocks — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Homepage performance
Validate homepage load time in non-prod before go-live. A homepage that takes more than 4 seconds to load will see immediate user abandonment. The OOTB 5-block homepage is designed for performance. If load time is slow, check: (1) are there large image files in the hero block? (2) are there custom widgets from a previous developer? Remove them. OOTB blocks are optimized; custom widgets often are not.
The go-live announcement
Draft the go-live announcement for the customer — they rarely have time to do it themselves. A good go-live announcement covers: 'Starting [date], you can submit all IT requests at [EC URL]. You can also find answers in our new Knowledge Base. Your previous requests are visible under My Requests.' That is all it needs. Send it from the IT Director's email and pin it for 30 days.

## Adoption vs Re-engineering
03 — Homepage Layout & Content Blocks — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want a custom branded hero banner with animated graphics | Use OOTB Hero block with corporate color and logo. No custom animations. | Custom animations require CSS/JavaScript widgets that break on upgrade and slow page load. The OOTB hero block with the corporate color and logo provides clear branding without the maintenance cost. | 'A clean, fast portal with the right color and logo makes a better first impression than a slow, animated one. Your employees will visit this portal multiple times a day — they care about finding things quickly, not the animation. Let us launch clean and fast; if the analytics show users spending time on the homepage rather than clicking through, we can revisit the design then.' | Never animated hero widgets. Static custom hero images (replacing the OOTB background color) are acceptable if provided by Communications in the correct format.

## ServiceNow Mapping
03 — Homepage Layout & Content Blocks — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Homepage Configuration
EC Homepage | Employee Center > Administration > Homepage | Configure blocks and their order here.
Announcement | sn_hr_sp_announcement | OOTB announcement record. Include start_date and end_date.
EC Theme | Employee Center > Administration > Branding | Hero color and text configured here.