ACCELERATOR PACK

Foundation Data

Pack — README

Eight workbooks. The base data your ServiceNow instance needs before any process can be configured.

ECS Federal  ·  ServiceNow Practice

Recipient: Customer Project Sponsor and named SMEs

Confidential — for the recipient and their organization

# What This Pack Is

This Accelerator Pack contains eight workbooks that capture the foundation data your ServiceNow instance needs before any process can be configured. Foundation data is the base population of users, locations, departments, groups, schedules, and SLAs that everything else in the platform depends on.

This Pack is the first deliverable from your engagement with ECS. Completing it accurately and on time directly determines how much of Sprint 0 we spend gathering data versus configuring the platform. It is the highest-leverage thing you can do in the first two weeks.

# The Eight Workbooks

| # | Workbook | What it Captures | Owner | Due |
| --- | --- | --- | --- | --- |
| 01 | Users | Every person who will use ServiceNow | IT Operations Manager | End of Sprint 0, Wk 2 |
| 02 | Locations | Physical and logical locations | Facilities Manager | End of Sprint 0, Wk 1 |
| 03 | Departments | Org structure and cost centers | HR Operations | End of Sprint 0, Wk 1 |
| 04 | Groups | Assignment, fulfillment, and approval groups | IT Operations Manager | End of Sprint 0, Wk 2 |
| 05 | Group Members | Who belongs to which group | IT Operations Manager | End of Sprint 0, Wk 2 |
| 06 | Assignment Rules | Routing logic — who gets what work | IT Operations Manager | End of Sprint 0, Wk 2 |
| 07 | Schedules | Business hours, holidays, on-call rotations | IT Operations Manager | End of Sprint 0, Wk 2 |
| 08 | SLAs | Service Level Agreement targets | IT Service Manager | End of Sprint 0, Wk 2 |

Each workbook contains an Instructions tab (start here), a Data tab (where you enter your data), and a ServiceNow Mapping tab (reference for your ECS Solution Architect; you can ignore this).

# How to Fill Out a Workbook

- Open the workbook. Read the Instructions tab end-to-end. Pay attention to the Field-by-field guide and the Common pitfalls.

- Switch to the Data tab. The yellow-shaded italic rows are example data — they are there to show the format. Do not edit them in place; insert your real data in the rows below, then delete the example rows when you are done.

- Use the dropdown menus where present (status, type, priority, etc.). They enforce allowed values and prevent import errors.

- Cross-reference between workbooks. user_ids in workbook 01 are referenced from workbooks 04 and 05. Department names from 03 are used in 01. Location names from 02 are used in 01 and 06. Cross-checking now prevents errors at import time.

- If your data has more rows than the example shows, just keep adding rows below — there is no row limit.

- Do not add or remove columns. Do not rename columns. The structure must match exactly for the import pipeline to work.

- If you have data that doesn't fit, contact your ECS Solution Architect rather than improvising the workbook structure.

# Order of Completion

The workbooks have dependencies. Complete them in this order to avoid rework:

- Locations (02) and Departments (03) — no dependencies on other workbooks; do these first.

- Schedules (07) — no dependencies; can be done in parallel with 02 and 03.

- Users (01) — depends on Locations (02) and Departments (03).

- Groups (04) — depends on Users (01) for the manager_user_id field.

- Group Members (05) — depends on Groups (04) and Users (01).

- Assignment Rules (06) — depends on Groups (04) and Locations (02).

- SLAs (08) — depends on Schedules (07).

# Submission

- When a workbook is complete, save it without renaming the file.

- Send completed workbooks to your ECS Solution Architect via the engagement's secure file-share.

- ECS will run a validation script and return any errors within one business day.

- If errors are flagged, correct them and resubmit. Most workbooks pass validation on the first or second submission.

# Validation — What ECS Checks

Before importing your data into ServiceNow, ECS runs a validation script that catches common data-quality issues. The script checks for:

- Required fields populated for every row.

- No duplicate primary keys (e.g., duplicate user IDs, duplicate location names).

- Cross-workbook references that resolve (e.g., manager_user_id matches a user in the Users workbook).

- Allowed values used in dropdown columns.

- Date and time formats parseable.

- Plausible row counts (no near-empty workbooks where data is expected).

Errors are returned with specific row and column references so you can fix and resubmit quickly.

# What Happens Next

Once a workbook passes validation, ECS imports the data into your sub-prod ServiceNow instance using a pre-built import pipeline. This typically takes under 30 minutes per workbook. We confirm the import with a smoke test (record counts, reference integrity, no orphaned records) before moving the data through to your test instance and ultimately to production.

By the end of Sprint 0, your sub-prod instance will have a fully populated foundation: users provisioned, locations and departments configured, groups and members in place, assignment rules ready, schedules and SLAs configured. Sprint 1 begins with the foundation under us and the team focused on configuration, not data gathering.

# Frequently Asked Questions

Q: Can we use a tool other than Excel to fill these out?

A: The workbooks are designed for Excel. If you need an alternative format (e.g., CSV export from your HR system), discuss with your ECS Solution Architect — we can sometimes accept the export directly and avoid the manual entry. The structure must still match.

Q: What if our data is incomplete in some areas?

A: Submit what you have and flag the gaps. We work together to close them in Sprint 1. Submitting incomplete data is better than missing the deadline; we have time to fix gaps, we don't have time to recover from a missed Sprint 0 deadline.

Q: Who do we contact if we have questions while filling these out?

A: Your engagement's ECS Solution Architect, named in the engagement kickoff document. Don't wait — early questions take minutes; late questions take days.

Q: Can we customize the workbooks (add notes, color-code rows, etc.) for our internal use?

A: Yes — keep an internal working copy with your annotations. The version you submit to ECS must match the original structure (no added or removed columns; original column names; data on the Data tab).

Q: What if we discover after Sprint 0 that we need to update foundation data?

A: Foundation data updates are easy in the first few sprints. Send the updated workbook to your ECS Solution Architect and we re-import. After go-live, foundation data updates become standard ServiceNow administration — Connection's platform team handles them with the SOPs we provide as part of the Knowledge Transfer Library.

# A Final Note

Foundation data is the most leveraged work in the engagement. Time invested here saves time everywhere else. Customers who treat the Foundation Data Pack as a priority during Sprint 0 routinely have smoother engagements, faster sprints, and cleaner go-lives. Customers who treat it as a side task routinely consume Sprint 1 chasing data — which costs sprint capacity that cannot be recovered.

Thank you for the partnership. The work you put into this Pack in the first two weeks shapes the engagement we deliver together over the next 18 weeks.

ECS Federal  ·  ServiceNow Practice