## Instructions
03 — Problem Management
ITSM Process Pack · ECS Federal · ServiceNow Practice
Purpose | Problem Management identifies the root cause of incidents, documents Known Errors, and drives permanent fixes. It is the process most often skipped by customers under pressure — and the one that most directly enables AI-powered pattern detection. This workbook captures the OOTB Problem workflow, RCA approach, and Known Error lifecycle.
Who fills this out | Customer-side: Problem Manager (named role), Service Desk Manager. ECS-side: Solution Architect, Process Consultant.
When it's due | Process Decisions in Sprint 1; configuration in Sprint 4 alongside Incident.
How long it takes | 2–3 hours of decision-making.
Where the data comes from | Existing Problem SOPs (often thin or aspirational); Incident historical data for pattern context.
How to use this workbook | Same workflow as workbook 01.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-populated; customer confirms or proposes alternative with rationale.
Dependencies | Other Packs and source data that must be in place before this process can be configured.
Configuration Data | The final OOTB-aligned configuration parameters — used by the consultant to build in ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant building the configuration.
Adoption vs Re-engineering | Pushback scenarios — when the customer asks for legacy patterns, how to redirect to OOTB.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.
Common pitfalls
• | Treating Problem as optional or aspirational — if you don't run Problem, you don't get cross-incident pattern detection or AI training.
• | Custom RCA templates instead of OOTB Problem fields.
• | Manual Problem-to-Incident linkage instead of OOTB Related Records.
• | Skipping Known Error tracking — every Known Error is the answer to a future incident.
Who to ask | Your engagement's ECS Solution Architect.

## Process Decisions
Problem Management — Process Decisions
Decisions to make collectively. ECS recommendation pre-populated; customer confirms or proposes alternative with rationale.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Problem creation triggers | Manual; auto-suggest when 3+ similar incidents in 30 days (Predictive Intelligence)
2 | Problem Manager role | Single named role; rotation is acceptable but one accountable person per Problem
3 | RCA timeline expectation | Initial RCA within 5 business days; full root cause within 15 business days
4 | Known Error lifecycle | Problem → Investigating → Known Error (with workaround documented) → Resolved (permanent fix)
5 | Workaround documentation | Linked KB article; KB article visible to Service Desk and end users (per audience)
6 | Permanent fix tracking | Linked Change record; Problem closes when Change is implemented
7 | Problem closure approval | Problem Manager closes; no separate approval
8 | Predictive Intelligence — clustering | Enabled — auto-suggest Problem candidates from incident clusters
9 | Postmortem-to-Problem linkage | MI postmortem auto-creates Problem (configured in workbook 02)
10 | Problem Workspace usage | Problem Workspace in SO Workspace — adopt for all Problem work

## Dependencies
Problem Management — Dependencies
Other Packs and source data that must be in place before this process can be configured.
# | Dependency | Status | Owner | Due | Notes
1 | Incident Management workbook (01) configuration complete | In Progress | ECS
2 | Major Incident Management workbook (02) — auto-create Problem flow | Not Started | ECS
3 | Knowledge Management workbook (06) — for workaround articles | Not Started | ECS
4 | Change Management workbook (04) — for permanent fix linkage | Not Started | ECS
5 | CSDM with CIs in scope (Problem.cmdb_ci is a key field) | In Progress | ECS
6 | Problem Workspace plugin activated | Complete | ECS
7 | Predictive Intelligence baseline incident data (90+ days) | Not Started | Customer
8 | Problem Manager named and trained | Not Started | Customer

## Configuration Data
Problem Management — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are recommendations; replace with customer-confirmed values.
Field / Setting | Value | Notes
1. States and Lifecycle
Active states | New, Assess, Root Cause Analysis, Fix in Progress, Resolved, Closed | OOTB
Known Error sub-state | Known Error flag (boolean) on Problem | OOTB
Auto-close after resolved (days) | 30 | OOTB scheduled job
2. Triggers
Predictive Intelligence clustering | Enabled — Cluster Plugin on incident table | OOTB
Cluster suggestion threshold | 3+ similar incidents in 30 days | Configurable
MI auto-create | Yes (configured in MI workbook 02)
3. RCA
RCA fields | OOTB Problem fields: cause_notes, fix_notes, workaround | No customization
RCA template | Problem Workspace template | OOTB
4. Workarounds and Permanent Fix
Workaround in KB? | Yes — KB article auto-linked to Problem | OOTB
Permanent fix tracking | Linked Change record (problem.rfc field) | OOTB
5. Notifications
Active notifications | Created, Assigned, Known Error declared, Resolved, Closed | OOTB

## R&R
Problem Management — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Process Decisions facilitation | R | C
Problem Manager role definition and naming | C | R | Customer assigns role.
Problem state machine and Workspace configuration | R | I
Predictive Intelligence cluster plugin configuration | R | C
RCA template design | R | C | ECS configures OOTB; Customer reviews.
KB integration for workarounds (with KM workbook) | R | C
Change Management linkage (with Change workbook) | R | C
UAT and validation | R | R | Joint.
Production cutover | R | A
Long-term ownership | I | R | Customer's Problem Manager.

## Consultant Guide
Problem Management — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Step-by-step ServiceNow updates.
OOTB Problem Foundations
Use OOTB Problem table (problem) with the Problem Workspace UI. Custom fields are rare — OOTB cause_notes, fix_notes, workaround, rfc fields cover most needs.
Implementation Sequence
• Activate Problem Workspace plugin (sn_problem_workspace).
• Configure Predictive Intelligence Cluster solution on incident table (System > Predictive Intelligence > Cluster Solutions).
• Configure cluster threshold per Process Decisions (typically 3+ similar in 30 days).
• Configure auto-suggest workflow: when cluster forms, create draft Problem and notify Problem Manager.
• Configure Problem state transitions per OOTB lifecycle.
• Configure Known Error flag display in Problem Workspace.
• Configure KB integration: when Workaround field populated, prompt to create KB article.
• Configure Change linkage: rfc field reference to change_request.
• Configure auto-close: Resolved → Closed after 30 days (OOTB scheduled job).
• Configure Performance Analytics Problem dashboard (open count, MTTR-to-Known-Error, MTTR-to-permanent-fix).
Common Pitfalls to Avoid
• Custom RCA fields outside OOTB Problem fields — breaks Problem Workspace.
• Skipping cluster plugin — loses biggest source of Problem candidates.
• Workaround in free text without KB linkage — workaround dies with the Problem record.
• Permanent fix tracked manually in spreadsheet — loses Problem-to-Change linkage.
References
• ServiceNow Docs: Problem Management
• ServiceNow Docs: Problem Workspace
• ServiceNow Docs: Predictive Intelligence Clustering

## Adoption vs Re-engineering
Problem Management — Adoption vs Re-engineering
When the customer says "but our old system did X." Use these scenarios to redirect the conversation toward OOTB adoption rather than re-engineering legacy patterns.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"We don't really do Problem Management — we just fix incidents." | Activate OOTB Problem Management with Predictive Intelligence Clustering — auto-suggests Problems from incident clusters. | Without Problem Management, you can't detect the pattern of recurring incidents. AI features (Predictive Intelligence, Now Assist) need Problem records to learn cross-incident patterns. | "Problem Management isn't about adding work; it's about catching patterns. The cluster plugin auto-suggests Problems — your team validates instead of creating from scratch. Three months in, you'll see recurring incidents drop because the pattern got fixed instead of repeatedly resolved." | True one-off incidents only (rare in any enterprise) — even then, Problem records have value for audit.
"We have a custom RCA template in Word that we attach to incidents." | OOTB Problem record with cause_notes, fix_notes, and Problem Workspace template. | Word attachments lose searchability, lose AI training data, and don't link to the Change that fixed the issue. | "OOTB Problem record has all the RCA fields built in. Plus it links to the original incidents AND the Change that fixed the issue — the full causal chain. Word RCAs die in the attachment." | Rare; usually solved by configuring Problem fields per the template structure.
"Known Errors live in a separate Confluence/Wiki — easier to search." | OOTB Known Error flag on Problem, with linked KB article (visible in AI Search and Virtual Agent). | Confluence Known Errors are invisible to AI Search and Virtual Agent — service desk loses the deflection benefit. | "AI Search and Virtual Agent can serve Known Error workarounds at the moment of incident creation — Confluence can't. Linking Known Error → KB article means the next caller sees the workaround before they even submit a ticket." | Engineering wikis with deep technical detail — keep those, but the customer-facing workaround belongs in KB.
"Custom workflow to track 'permanent fix' separate from Change." | OOTB rfc field on Problem links to the Change record. | Separate tracking creates two sources of truth and breaks the Problem-to-Change linkage. | "OOTB linkage IS the tracking. The Change record has full history; the Problem closes when the Change implements. One source of truth." | Don't customize.
"We close Problems with workaround documented; we don't always pursue permanent fix." | Acceptable per ITIL — close as Known Error with workaround, not as Resolved. | OOTB supports this — Known Error state captures it. | "That's exactly the Known Error pattern. Mark Known Error, document workaround in KB, close Problem with that distinction. The data shows you what's still being worked around vs. what's been permanently fixed." | Don't push back here — this is correct ITIL practice.

## ServiceNow Mapping
ServiceNow Mapping (for ECS Solution Architect reference)
Primary table: problem. Linked: incident (problem_id reference), change_request (rfc reference), kb_knowledge (linked via problem.workaround_kb). Predictive Intelligence: ml_solution with type=Cluster on incident table. Workspace: Problem Workspace (sn_problem_workspace).