## Instructions
01 — Knowledge Base Structure
Knowledge Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Knowledge Base hierarchy: which KBs to create, their categories, audience, and ownership. OOTB ServiceNow supports multiple Knowledge Bases — the recommended pattern is one KB per distinct audience (IT Staff, All Employees, HR). This workbook sets the structure before any articles are authored.
Who fills this out | Customer ITSM Process Owner and Knowledge Manager. ECS SA facilitates.
Sprint window | Sprint 5 Week 1
Estimated effort | 2–3 hours
Related workbooks | 02 Article Template Standards · 03 Access Controls · Service Catalog Pack — Category Rationalization
Success criteria
• | Knowledge Bases defined with owner, audience, and category structure.
• | Maximum 3 Knowledge Bases at MVP (IT Staff, All Employees, optional HR).
• | Each KB has a named Knowledge Manager.
• | Category structure aligns with Service Catalog categories where applicable.

## Process Decisions
01 — Knowledge Base Structure — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | How many Knowledge Bases should we create at MVP? | Three maximum: IT Staff KB (internal procedures, runbooks), Employee Self-Service KB (how-to articles for end users), and optionally an HR KB if HR is in scope. |  | More than three KBs at MVP creates content silos and complicates search. The OOTB KB search searches all KBs the user has access to — separation is by audience, not by topic.
2 | Should Knowledge Base categories mirror Service Catalog categories? | Yes where the KB is user-facing. Employee Self-Service KB categories should mirror the Service Catalog category structure so users experience consistent navigation between catalog and knowledge. |  | Consistent taxonomy between catalog and knowledge reduces cognitive load and improves Virtual Agent intent matching, which uses both catalog and knowledge data.
3 | Who is the Knowledge Manager for each KB? | Assign a named individual — not a group — as Knowledge Manager per KB. The KM is accountable for article quality, review cycles, and retirement of stale articles. |  | Group ownership of a KB means no single person responds when articles become stale. The KM role is 2–3 hours per month for a well-maintained KB.

## Dependencies
01 — Knowledge Base Structure — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Service Catalog category structure (Catalog Pack Workbook 01) | Recommended | ECS SA | Sprint 4 | Align KB categories with Catalog categories for consistent user navigation.
2 | Virtual Agent topic list (VA Pack, if VA is in scope) | Recommended | ECS SA | Sprint 5 | VA topics link to KB articles — category alignment simplifies VA configuration.
3 | Foundation Data Pack — Users (for KB Managers) | Required | ECS SA | Sprint 0 | KB Managers must be active user records.

## Configuration Data
01 — Knowledge Base Structure — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Knowledge Base Definitions
KB 1 — Name | IT Staff Knowledge Base
KB 1 — Audience | IT Staff only (user criteria restriction)
KB 1 — Knowledge Manager | [Customer to complete]
KB 1 — Categories (MVP) | Incident Procedures; Change Management; Platform Administration; Asset Management
KB 2 — Name | Employee Self-Service
KB 2 — Audience | All employees
KB 2 — Knowledge Manager | [Customer to complete]
KB 2 — Categories (MVP) | IT Equipment; Software & Access; Troubleshooting; Onboarding
KB 3 — Name | HR Knowledge Base (if HR in scope)
KB 3 — Audience | All employees / HR staff only | Restrict sensitive policy content to HR staff using article-level user criteria.
KB 3 — Knowledge Manager | [Customer to complete]

## R&R
01 — Knowledge Base Structure — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Define KB structure and categories | R/A | C | ECS SA designs; customer confirms audience and naming.
Assign Knowledge Managers | I | R/A | Customer ITSM Process Owner assigns.
Configure KBs in ServiceNow | R/A | I | ECS SA configures.
Populate initial article set (MVP — 10 articles per KB) | C | R/A | Customer Knowledge Managers author; ECS SA reviews for template compliance.

## Consultant Guide
01 — Knowledge Base Structure — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
MVP article count
Set a realistic MVP article target: 10 articles per KB. Articles that are half-written are worse than no articles — they undermine trust in the KB. Better to launch with 10 excellent articles per KB than 50 draft-quality ones.
Aligning KB and catalog taxonomy
During the Sprint 5 KB setup, revisit the Service Catalog category structure from Sprint 4. If categories were adjusted during catalog build, the KB category structure must be updated to match. Misalignment between catalog and knowledge categories confuses users and breaks Virtual Agent's intent-to-knowledge linking.

## Adoption vs Re-engineering
01 — Knowledge Base Structure — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want one giant KB for everything | Create separate KBs by audience. IT Staff should not see draft runbooks when searching as an end user. | Mixing IT internal content with employee self-service content creates search noise and confidentiality risks. OOTB user criteria on KBs handle this cleanly. | 'One KB sounds simpler, but your IT staff will search and get employee how-to articles mixed with their runbooks. And employees will occasionally find IT procedures that don't make sense to them. Two KBs with the right access controls gives everyone a clean search experience.' | Only for very small IT teams (<5) with no internal procedures that should be restricted from employees.

## ServiceNow Mapping
01 — Knowledge Base Structure — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Knowledge Tables
Knowledge Base | kb_knowledge_base | One record per KB.
KB Category | kb_category | Categories within each KB.
Knowledge Article | kb_knowledge | Individual articles. References kb_knowledge_base.