## Instructions
04 — Article Workflow & Review Cadence
Knowledge Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the OOTB article lifecycle — Draft → Review → Published → Retired — and the review cadence that keeps articles current. The most common KB failure mode is articles that were accurate at go-live but were never reviewed and are now misleading users 18 months later.
Who fills this out | ECS SA defines the workflow configuration; Customer Knowledge Manager agrees the review cadence.
Sprint window | Sprint 5 Week 1
Estimated effort | 1–2 hours
Related workbooks | 02 Article Template Standards · 06 Knowledge KPIs
Success criteria
• | OOTB article workflow is configured (Draft → Review → Published → Retired).
• | Review cadence is set per KB (12 months for How-To, 90 days for Known Errors).
• | KB health report is scheduled to flag articles past their Valid to date.
• | Knowledge Manager has a monthly review task in their calendar.

## Process Decisions
04 — Article Workflow & Review Cadence — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should article approval require more than one reviewer? | One reviewer (the Knowledge Manager) is sufficient for MVP. Second reviewer can be added for compliance-sensitive categories in Phase 2. |  | Two reviewers double the time to publication without a proportionate quality benefit for a mid-market KB. The KM role carries the accountability — one reviewer with real ownership is more effective than two reviewers with diffused responsibility.
2 | What happens to articles that pass their Valid to date? | OOTB: articles are automatically flagged as 'Needs Review' when Valid to is exceeded. They remain published (not hidden) until the KM reviews and either extends the date or retires the article. Do not auto-retire articles. |  | Auto-retiring articles removes content that may still be accurate. The KM review step ensures intentional decisions — not automated actions — determine what stays in the KB.
3 | How should Known Error articles be handled when the underlying problem is resolved? | Retire the Known Error article. Create a How-To article if the resolution requires user action, or simply retire if the fix was transparent. Never leave Known Error articles published after the problem is resolved. |  | Stale Known Error articles undermine trust in the KB. A user who finds a Known Error workaround for a problem that was fixed 6 months ago loses confidence in all KB content.

## Dependencies
04 — Article Workflow & Review Cadence — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | KB Structure (Workbook 01) | Required | ECS SA | Sprint 5 Wk 1

## Configuration Data
04 — Article Workflow & Review Cadence — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Article Lifecycle Configuration
OOTB workflow states | Draft → Review → Published → Retired | Do not add custom states.
Author action | Author creates Draft, submits for review
KM action | KM reviews, publishes or returns to author with comments
Review notification | OOTB: KM notified when article submitted for review
2. Review Cadence
How-To articles — Valid to period | 12 months from publish date | KM receives review reminder 30 days before expiry.
Known Error articles — Valid to period | 90 days | More frequent review — Known Errors resolve faster.
Monthly KM review task | KM reviews OOTB 'Needs Review' report on the 1st of each month
Stale article threshold (KB Health) | Valid to exceeded by > 30 days = stale | Configure in KB Health settings.

## R&R
04 — Article Workflow & Review Cadence — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure OOTB article workflow | R/A | I | ECS SA.
Set Valid to periods per article type | R/A | C | ECS SA sets defaults; KM can adjust per article.
Schedule monthly KB review in KM calendar | I | R/A | Customer KM.
Review and action Needs Review report monthly | I | R/A | Customer KM.

## Consultant Guide
04 — Article Workflow & Review Cadence — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
KB health as an engagement metric
At the end of Sprint 5, set up the OOTB KB Health dashboard and show the customer: article count, average age, % with Valid to dates set, % flagged for review. This gives the KM a clear picture of the health of their KB from day one and establishes the baseline for the monthly review habit.

## Adoption vs Re-engineering
04 — Article Workflow & Review Cadence — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want articles to publish immediately without review | Use OOTB Draft → Review → Publish workflow. | Unreviewed articles create accuracy risks and erode user trust. The review step is 5–10 minutes per article — the cheapest quality control available. | 'Immediate publishing seems faster until an article with incorrect steps causes users to make mistakes — and they stop trusting the KB entirely. The review step is 10 minutes per article. The KM can batch-review 10 articles in an hour. The trust it builds is worth it.' | Never remove the review step for published articles.

## ServiceNow Mapping
04 — Article Workflow & Review Cadence — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Article Workflow
Article state field | kb_knowledge.workflow_state | Draft / Review / Published / Retired.
Valid to field | kb_knowledge.valid_to | Sets the review date. KB Health reports use this.
KB Health Dashboard | Knowledge > Administration > KB Health | Monitor article health, stale count, and review queue.