## Instructions
05 -- PA Governance & Review Cadence
Performance Analytics Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Establish the ongoing governance model, review cadence, and continuous improvement process for Performance Analytics post-go-live.
Who fills this out | ECS PM and Customer PM jointly complete. Dashboard owners commit to review cadence.
Sprint window | Sprint 6 -- governance model finalized before handover at Week 12
Estimated effort | 2 hours with Customer PM and dashboard owners
Related workbooks | 01 PA Scope · 03 Dashboard Design · 04 Scorecard · AP-20 Reporting & Stabilization
Success criteria
• | Dashboard owners committed to review cadence.
• | Monthly scorecard review scheduled (recurring).
• | Dashboard modification governance agreed (who can change what).
• | Phase 2 PA roadmap documented.
• | PA Admin trained on indicator activation and threshold management.

## Process Decisions
05 -- PA Governance & Review Cadence — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Who can modify PA dashboards and indicators post-go-live? | PA Admin role only -- Customer named PA Admin controls all changes. |  | Open dashboard modification creates widget proliferation and threshold drift. One named PA Admin is the gatekeeper.
2 | How should new dashboard requests be handled? | New requests go to Customer PA Admin. PA Admin evaluates against OOTB indicator availability. Custom indicators go through Change Management (RFC). |  | Treating new dashboard requests as mini-change items prevents uncontrolled PA sprawl.
3 | When should thresholds be revised? | At each monthly scorecard review. Thresholds should be revised quarterly based on trend data, not reactively after a single bad month. |  | Reactive threshold changes (lowering targets after a bad month) destroy the governance integrity of the scorecard. Quarterly revision with data is the right cadence.

## Dependencies
05 -- PA Governance & Review Cadence — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Named PA Admin with pa_admin role | Required | Customer | Sprint 6 close | PA governance requires a named admin.
2 | Dashboard owners trained on PA navigation | Required | ECS | Sprint 6 | Owners must know how to view, export, and interpret their dashboards.

## Configuration Data
05 -- PA Governance & Review Cadence — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Governance Model
PA Admin role | Named Customer PA Admin -- controls indicator activation, threshold changes, dashboard sharing | Customer to name PA Admin before Sprint 6 close
Dashboard modification process | PA Admin reviews request, evaluates OOTB indicator availability, implements change | New requests via email to PA Admin; tracked in PA Admin log
Custom indicator RFC requirement | Any custom indicator (non-OOTB) requires IT Change Request and PA Admin approval | Prevents uncontrolled custom indicator proliferation
Threshold revision cadence | Quarterly -- at each quarter-end scorecard review | Do not revise thresholds reactively after single bad period
2. Review Cadence
Weekly (Service Desk Team Lead) | Review Service Desk Performance dashboard every Monday | Team Lead owns -- no ECS involvement post-handover
Monthly (IT Manager) | Review Incident Management dashboard on last Friday of month | IT Manager owns -- part of regular management cycle
Monthly (IT Director) | Review ITSM Executive Overview and Scorecard on last Friday of month | IT Director owns -- ECS PM attends during engagement only
Quarterly threshold review | IT Director + PA Admin -- review and revise thresholds based on trend data | Scheduled recurring invite in calendar
3. Phase 2 PA Roadmap
Custom indicator library | Build indicators for request fulfillment SLA, change success, and problem MTTR | Scope for first post-stabilization sprint
Department-level dashboards | Individual dashboards per business unit for HR, Finance, etc. | Requires HR and Finance ITSM usage data to be meaningful
AI-assisted forecasting | Now Assist integration with PA for predictive capacity forecasting | Requires 6+ months of PA trend data as input

## R&R
05 -- PA Governance & Review Cadence — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Name and configure PA Admin | I | R/A | Customer IT Director names; ECS grants role.
Train PA Admin on indicator and threshold management | R/A | Attend | ECS delivers 1-hour admin training in Sprint 6.
Train dashboard owners on navigation and export | R/A | Attend | ECS delivers 30-min owner briefing per dashboard.
Schedule recurring review calendar invites | R (during engagement) | A (post-engagement) | ECS schedules during engagement; Customer PM takes over.
Phase 2 PA scope documentation | R/A | Review | ECS documents at 90-day review.

## Consultant Guide
05 -- PA Governance & Review Cadence — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
PA Admin training scope
The 1-hour PA Admin training should cover: (1) how to activate a new OOTB indicator, (2) how to set and change thresholds, (3) how to share a dashboard with a new user or role, (4) how to export the scorecard as PDF. These four skills cover 90% of post-go-live PA Admin tasks.
Governance enforcement
The most common PA failure mode is uncontrolled dashboard proliferation -- every manager wants their own custom dashboard. Enforce the governance model from day one: new dashboards go through the PA Admin. The OOTB indicator library is large -- most needs can be met without custom indicators.
Phase 2 sequencing
Phase 2 PA work should not begin until 6 months of OOTB data has accumulated. The first 90 days produce noise. Months 3-6 produce signal. Custom indicators and department dashboards built on 6 months of data will be far more accurate and useful than ones built on 30 days.

## Adoption vs Re-engineering
05 -- PA Governance & Review Cadence — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Every manager wants their own dashboard | Named dashboard owners only at go-live; department dashboards in Phase 2. | One dashboard per manager without governance creates 20 dashboards measuring slightly different things with different thresholds -- none of which tell the same story to leadership. | We have three dashboards that cover the three key audiences. Every manager's questions can be answered from these dashboards or from OOTB Reports. If there is a question no existing dashboard answers, the PA Admin evaluates whether a new widget or a new OOTB Report is the right answer. Department dashboards are the Phase 2 roadmap -- grounded in real usage data. | Phase 2 -- department dashboards after 6 months of OOTB baseline.

## ServiceNow Mapping
05 -- PA Governance & Review Cadence — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. PA Governance
pa_admin role | Grants full PA admin access -- indicator activation, threshold management, sharing | sys_user_role
pa_viewer role | Grants read-only access to PA dashboards -- for dashboard owners | sys_user_role
change_request | RFC process for custom indicator requests -- customer governance | change_request