## Instructions
04 -- Assignment Intelligence Configuration
Predictive Intelligence Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Configure the OOTB Assignment Intelligence PI model to predict the correct assignment group for new incidents based on category and short description.
Who fills this out | ECS Architect configures. Customer Service Desk Lead and IT Manager review during UAT.
Sprint window | Sprint 4-5 -- model active and tested by end of Week 9
Estimated effort | 4-5 hours including training, accuracy review, and UAT
Related workbooks | 01 PI Scope & Readiness · 02 Category Classification · AP-01 Foundation Data (groups)
Success criteria
• | Assignment Intelligence model trained and suggestions visible on Incident form.
• | Minimum 65% assignment group prediction accuracy on test set.
• | Assignment suggestions suppressed below 0.70 confidence threshold.
• | Agent UAT: 20 test incidents reviewed for assignment accuracy.
• | Average first-assignment accuracy baseline recorded.

## Process Decisions
04 -- Assignment Intelligence Configuration — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which fields should drive assignment prediction? | Category + subcategory + short description (OOTB combination). This is more accurate than short description alone. |  | Category provides strong signal for routing -- the model learns that 'Network' category incidents route to Network Ops, regardless of short description wording.
2 | Should Assignment Intelligence predict individual agent or just group? | Assignment group only at go-live. Individual agent assignment is Phase 2. |  | Group-level prediction has much higher accuracy. Individual agent prediction requires far more training data per agent and is highly sensitive to agent turnover.
3 | Should suggestions be shown on ticket creation or after categorization? | After categorization -- assignment suggestion appears once category is set. |  | Category is the strongest input signal. Showing assignment suggestions before category is set produces low-quality predictions.
4 | What happens to mis-assigned tickets during the suggestion period? | Agents correct the assignment manually. Each correction is captured as training feedback for the next retraining cycle. |  | OOTB PI captures agent overrides as negative feedback. The model improves with each correction cycle.

## Dependencies
04 -- Assignment Intelligence Configuration — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Assignment groups populated in ServiceNow (AP-01) | Required | Customer | Sprint 1 close | Groups must exist for PI to predict them.
2 | Category Classification active (WB2) | Required | ECS | Sprint 4 Wk 1 | Assignment Intelligence uses category as input -- category model must be active first.
3 | 1,000+ closed incidents with populated assignment group | Required | Customer | Sprint 4 Wk 1 | Training data requirement.

## Configuration Data
04 -- Assignment Intelligence Configuration — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Assignment Intelligence ML Solution
Solution name | ECS_Assignment_Intelligence
Source table | incident | Closed incidents only
Input fields | category, subcategory, short_description | Combined input for highest accuracy
Output field | assignment_group | Predict group only -- not individual agent
Training filter | state=7 AND assignment_group IS NOT NULL AND category IS NOT NULL
Confidence threshold | 0.70 | Suppress below this score
Suggestion display trigger | After category field is populated | OOTB event-driven suggestion
2. Accuracy Targets
Go-live accuracy target | 65% first-assignment accuracy | Measured against closed incident ground truth
30-day target | 70% | With weekly retraining incorporating corrections
Groups to exclude from prediction | [Customer: list groups with fewer than 50 historical incidents] | Too few examples = unreliable predictions for that group

## R&R
04 -- Assignment Intelligence Configuration — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Create and configure Assignment Intelligence ML Solution | R/A | I | ECS Architect.
Run model training | R/A | I | ECS runs job; Customer IT Manager notified.
Review accuracy report by assignment group | R | A | ECS presents; IT Manager approves go-live.
UAT -- 20 test incident assignment review | R | A | ECS + Service Desk Lead.
Record first-assignment accuracy baseline | R | A | ECS pulls baseline metric before go-live.
Monitor accuracy and retraining cycles | R (4 weeks) | A (ongoing) | Customer PI Admin takes over at sprint close.

## Consultant Guide
04 -- Assignment Intelligence Configuration — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
First-assignment rate baseline
Before go-live, pull a first-assignment rate metric from the past 90 days: what percentage of incidents were assigned correctly on the first assignment attempt? This is your baseline. At 30 and 90 days post-launch, compare. A good Assignment Intelligence deployment improves first-assignment rate by 15-25%.
Groups with too few records
If any assignment group has fewer than 50 historical incidents, Assignment Intelligence cannot predict it reliably. Options: (1) exclude it from prediction scope, (2) merge it with a similar group in the training filter, or (3) accept low confidence for that group and let agents manually assign. Discuss options with the IT Manager.
Override as training signal
Reinforce to agents: every time they override an incorrect assignment suggestion, they are improving the model. This reframes corrections from 'the AI is broken' to 'I am training it.' Increases agent engagement with the correction workflow.

## Adoption vs Re-engineering
04 -- Assignment Intelligence Configuration — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want PI to auto-assign tickets to individual agents | Group-level assignment at go-live; agent-level in Phase 2. | Agent-level prediction requires 10x more training data and is sensitive to agent turnover, workload, and specialization changes. | Group assignment is the 80% solution. Once the group accuracy is proven, we look at agent-level assignment in Phase 2 using workload data alongside the PI model. Agent-level is the right destination -- group-level is the right starting point. | Phase 2 -- after group accuracy exceeds 75% for 60 days.

## ServiceNow Mapping
04 -- Assignment Intelligence Configuration — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Assignment Intelligence
ml_solution (Assignment) | PI Solution for assignment group prediction | ml_solution
sys_user_group | Assignment groups -- must be populated for prediction | sys_user_group
incident (assignment_group) | Target field for prediction output | incident.assignment_group
PI Analytics | OOTB first-assignment rate, accuracy by group | ml_analytics