## Instructions
01 — Category Rationalization
Service Catalog Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the simplified category and subcategory structure for the ServiceNow Service Catalog, applying the OOTB 3-level maximum (Catalog > Category > Subcategory). This workbook replaces the legacy 'everything has its own category' pattern with a user-centric structure that is browsable, maintainable, and compatible with Employee Center search and Virtual Agent intent matching.
Who fills this out | Customer-side: ITSM Process Owner and a representative end user (ideally someone from HR or a business unit that uses IT services heavily). ECS SA facilitates the rationalization workshop. Customer approves the final category structure before Workbook 02 begins.
Sprint window | Sprint 3 Week 2 — Sprint 4 Week 1
Estimated effort | 3–4 hours (one rationalization workshop + customer review)
Related workbooks | 02 Catalog Item Inventory · 03 Item Template Standards · Foundation Data Pack — Departments
Success criteria
• | Legacy category list is audited and the proposed new structure is documented.
• | The new structure has no more than 3 levels (Catalog > Category > Subcategory).
• | Every category has a named owner (the group responsible for items in that category).
• | The structure is approved by the ITSM Process Owner before item triage begins.
• | The total number of top-level categories is 6 or fewer for the IT catalog.

## Process Decisions
01 — Category Rationalization — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | How many top-level categories should the IT Service Catalog have? | 6 or fewer. Recommended structure: IT Equipment, Software & Licensing, Access & Security, Infrastructure Services, HR & Onboarding, and General Requests. Each category should be meaningful to an end user, not to an IT team. |  | Catalogs with 20+ top-level categories force users to browse extensively and reduce self-service adoption. OOTB Employee Center search is the primary discovery mechanism — category structure is for browsing, not for taxonomy. Fewer, clearer categories drive higher adoption.
2 | Should categories reflect IT team structure or user needs? | User needs. Categories should reflect what a user is trying to accomplish, not which IT team handles it. 'Access & Security' is a user need; 'Active Directory Team Requests' is an IT team structure. |  | User-centric categories drive self-service adoption. Team-centric categories require the user to know which team handles their request before they can find the right item — defeating the purpose of a self-service catalog.
3 | Should we have separate catalogs for IT and HR? | Yes if HR services are in scope. Use the OOTB multi-catalog feature: one catalog for IT Services, one for HR Services. This is the Employee Center design pattern and requires no customisation. |  | Mixing IT and HR items in a single catalog creates confusion about ownership and fulfillment. The OOTB multi-catalog model is the right architecture for Employee Center.
4 | How do we handle categories from the legacy system that don't map neatly? | Map every legacy category to the new structure. Legacy categories that cannot map to any new category are candidates for the 'General Requests' catch-all. Flag these for Workbook 02 triage — some may be retired. |  | A legacy category that has no equivalent in the new structure usually contains items that are either duplicates, rarely used, or should be handled by a different process (e.g., a category full of items that should be Incident subtypes, not catalog requests).
5 | Should subcategories be mandatory or optional? | Optional. Use subcategories only where a category contains more than 8–10 items AND the items naturally cluster into sub-groups. Do not create subcategories for the sake of structure. |  | Subcategories add a navigation step. If a category has 5 items, a subcategory forces the user to click twice to find them. The OOTB search reduces the value of deep navigation hierarchies.
6 | How do we handle seasonal or project-specific catalog items (e.g., new hire equipment bundles)? | Keep these as regular catalog items within the appropriate category. Use the 'Available for' field to limit visibility to appropriate user populations. Do not create project-specific categories. |  | Project-specific categories become orphaned after the project ends. Use item-level visibility controls (Available for, Available to) rather than category proliferation.

## Dependencies
01 — Category Rationalization — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Existing catalog item list (from legacy system or current ServiceNow instance) | Required | Customer ITSM Owner | Sprint 3 Wk 2 | Cannot rationalize categories without knowing what items will live in them.
2 | Foundation Data Pack — Departments loaded | Required | ECS SA | Sprint 0 | Category ownership maps to departments/groups. Groups must exist.
3 | CSDM Business Service list (Workbook 03 from CMDB-CSDM pack) confirmed | Recommended | ECS SA + Customer EA | Sprint 2 | Category structure should complement the Business Service taxonomy, not contradict it.
4 | Employee Center design decisions (Employee Center pack, if in scope) | Recommended | ECS SA | Sprint 3 | Employee Center homepage layout affects how categories are displayed. Align before finalising category names.

## Configuration Data
01 — Category Rationalization — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Proposed Category Structure — IT Service Catalog
Catalog Name | IT Services | OOTB: one catalog per domain (IT, HR). Do not merge.
Category 1 | IT Equipment | Laptops, monitors, peripherals, mobile devices.
Category 2 | Software & Licensing | Software requests, licence requests, application access.
Category 3 | Access & Security | New accounts, access requests, password resets, MFA.
Category 4 | Infrastructure Services | VPN, storage, network drives, server requests.
Category 5 | HR & Onboarding | New hire setup, offboarding, transfer requests.
Category 6 | General Requests | Catch-all for items not fitting the above. Review quarterly.
2. Category Ownership
Category owner assignment | Each category must have a named fulfillment group as owner | Used for routing and accountability. Must be an existing assignment group.
IT Equipment — owner group | [Customer to complete] | Typically End User Computing or IT Operations.
Software & Licensing — owner group | [Customer to complete] | Typically Software Asset Management or IT Operations.
Access & Security — owner group | [Customer to complete] | Typically Identity & Access Management or IT Security.
Infrastructure Services — owner group | [Customer to complete] | Typically Infrastructure/Server team.
HR & Onboarding — owner group | [Customer to complete] | Joint: HR and IT Operations.
3. Legacy Category Mapping
Legacy category mapping approach | Document legacy category → new category mapping before Workbook 02 | Every legacy category must be accounted for. Unmapped categories = items to triage.
Legacy categories with no new equivalent | [Customer to complete — list here] | These items will be triaged in Workbook 02 as Retire or consolidate.

## R&R
01 — Category Rationalization — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Facilitate category rationalization workshop | R/A | C | ECS SA runs the workshop using the legacy category list as input.
Provide legacy category/item list | I | R/A | Customer ITSM Owner provides the existing catalog structure.
Draft new category structure | R/A | C | ECS SA drafts; customer reviews for user-centricity.
Map legacy categories to new structure | R | C | ECS SA leads mapping; customer confirms each mapping decision.
Assign category owner groups | I | R/A | Customer ITSM Owner assigns; must be existing assignment groups.
Obtain ITSM Process Owner approval | I | R/A | Customer governance step. Required before Workbook 02 begins.
Configure category structure in ServiceNow | R/A | I | ECS SA configures after customer approval.

## Consultant Guide
01 — Category Rationalization — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The rationalization workshop
Start the workshop by projecting the current category list (however messy) and asking: 'If you were a new employee trying to request a laptop, which of these categories would you click first?' This exercise immediately highlights whether the current structure is user-centric. Then group items by user intent rather than IT team. The 6-category structure in this workbook is a starting point — adjust it based on the customer's actual item mix, but hold the line on the 3-level maximum.
The 6-category ceiling
Customers often want 12–15 categories because they think more categories = more findable items. The opposite is true. Employee Center search is the primary discovery mechanism for most users. Categories are for browsing users who don't know what to search for — typically 20-30% of catalog users. For those users, 6 clear categories are more navigable than 15 specific ones. Use OOTB search analytics (available post-go-live) to validate this with data.
The General Requests catch-all
Always include a General Requests category. Without it, items that don't fit neatly into the agreed structure become blockers to the Sprint 4 build. Items in General Requests should be reviewed quarterly by the ITSM Process Owner — if a category consistently has more than 8 items, it has earned its own category. If it stays below 5 items after 6 months, those items are candidates for retirement or consolidation.
Multi-catalog vs. single catalog
The decision to create separate IT and HR catalogs should be made in Sprint 3 alongside Employee Center scoping. If Employee Center is in scope (Sprint 5), a multi-catalog approach with a unified Employee Center homepage is the OOTB best practice. If Employee Center is not in scope, a single catalog with IT and HR sections may be simpler to manage. Confirm with the ECS SA responsible for Employee Center before finalising this workbook.

## Adoption vs Re-engineering
01 — Category Rationalization — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We need to keep our 40 legacy categories for backward compatibility | Implement the new 6-category structure. Map legacy categories to the new structure and retire the legacy ones after go-live. | 40 categories is a proven barrier to self-service adoption. Legacy category names are not user-facing after the new catalog goes live — they exist only in reporting history, which can be preserved through incident/request metadata. | 'Your users don't know what category a request belongs to — they know what they need. A user who needs a laptop doesn't look for an IT Hardware Provisioning category. They look for IT Equipment. We're not losing your legacy categories; we're translating them into language your users actually use.' | Never preserve 40 legacy categories in the live catalog. Historical reporting references to legacy categories can be handled with a mapping field or report filter.
We want categories organized by IT team (Helpdesk, Server Team, Network Team) | Organise categories by user need. IT team routing belongs in the fulfillment workflow (Workbook 04), not the category structure. | Team-based categories require users to know which team handles their request before they can submit it. This defeats the purpose of self-service and increases misdirected requests. | 'We can absolutely route requests to the right team in the background — that's what the fulfillment workflow is for. The catalog category is what the user sees; the routing is invisible to them. Let's make the front end user-friendly and the back end team-friendly.' | Only if the customer explicitly operates a tiered-portal model where different user populations submit to different team portals. Rare and requires Employee Center configuration.
Every project needs its own category | Use the 'Available for' field and item tags to scope project-specific items. Do not create project-specific categories. | Project categories become orphaned after the project ends and accumulate in the catalog as dead weight. Item-level visibility controls handle scoping without creating structural debt. | 'A project category becomes a zombie after the project ends — it sits in the catalog forever with no owner. If we tag project items and set an expiry or review date, they're automatically tidied up without any structural change to the catalog. The catalog stays clean; the project team still gets their dedicated items.' | Never. There is no valid exception for project-specific categories in a governed catalog.

## ServiceNow Mapping
01 — Category Rationalization — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Catalog Structure Tables
Service Catalog | sc_catalog | One record per catalog (IT, HR). Configure in Service Catalog > Catalogs.
Catalog Category | sc_category | One record per category within each catalog. Parent/child for subcategories.
Catalog Item | sc_cat_item | Individual request items. Assigned to a category.
2. Key Category Fields
title | Category display name | What the user sees on the catalog homepage.
parent | Parent category (for subcategories) | Leave null for top-level categories.
manager | Category manager (sys_user) | Named individual responsible for category items.
sc_catalog | Reference to parent catalog | Links the category to the IT or HR catalog.
active | true/false | Inactive categories are hidden from users but preserved in history.
3. Employee Center Integration
EC Portal | Employee Center > Topics | Categories surface as Topics in Employee Center. Align category names with EC topic names.
Search index | Service Portal > Search Sources | OOTB Employee Center indexes sc_cat_item.short_description and description for search.