## Instructions
03 — Item Template Standards
Service Catalog Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the OOTB-aligned standards that every catalog item must meet: variable set design, item description format, delivery time field, ordering restrictions, and the 5-variable rule. Every item built in Sprint 4 and Sprint 6 is validated against these standards before it goes live.
Who fills this out | ECS SA owns this workbook — it is the build standard, not a customer data collection tool. The customer ITSM Process Owner should review and sign off the standards before Sprint 4 build begins.
Sprint window | Sprint 3 Week 2 — Sprint 4 Week 1 (standards agreed before build begins)
Estimated effort | 2 hours (ECS SA draft + customer review session)
Related workbooks | 02 Catalog Item Inventory · 04 Fulfillment Workflow Decisions · 05 Approval Matrix
Success criteria
• | OOTB item template fields are documented and agreed for all Sprint 4 items.
• | The 5-variable rule is adopted (maximum 5 variables at MVP; exceptions require ITSM Process Owner approval).
• | Variable naming conventions are agreed.
• | A quality checklist is in place that ECS SA uses before any item goes live.
• | Customer ITSM Process Owner has signed off the standards.

## Process Decisions
03 — Item Template Standards — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should all catalog items use a single shared variable set or item-specific variables? | Use a combination: one OOTB shared variable set for common fields (Requested For, Business Justification, Urgency) applied across all items, plus item-specific variables for unique inputs. Do not duplicate common fields on every item. |  | Shared variable sets reduce maintenance overhead and ensure consistent data collection across all items. Duplicating the same fields on every item means changing a common field requires editing every item individually.
2 | What is the maximum number of variables per catalog item at MVP? | 5 item-specific variables maximum. The shared variable set covers common fields. If a requested item genuinely requires more than 5 item-specific variables, it is a complex request that may need a workflow redesign or a Record Producer rather than a catalog item. |  | Every additional variable reduces self-service completion rates. Users abandon forms that feel like filling out a tax return. The OOTB benchmark for high-adoption catalog items is 3–5 total fields visible to the user.
3 | What variable types should be used by default? | Use OOTB variable types: Single Line Text, Multi-Line Text, Reference (for lookups), Choice (for fixed options), Date, and Yes/No. Avoid custom UI pages or client scripts unless a specific business rule requires them. |  | OOTB variable types are upgrade-safe and work natively in Employee Center, Mobile, and Virtual Agent. Custom UI pages and complex client scripts break on portal upgrades and block Virtual Agent from reading the variables.
4 | Should catalog items have mandatory fields? | Yes, but be selective. Only make a field mandatory if an empty response genuinely blocks fulfillment. 'Business Justification' for a password reset is not mandatory — it adds friction without value. |  | Over-use of mandatory fields is the second most common reason users abandon catalog requests. Before marking a field mandatory, ask: 'If the user leaves this blank, can we still fulfill the request?' If yes, it should not be mandatory.
5 | What should the catalog item description contain? | Three elements: (1) What the user receives — one sentence, plain language. (2) Who can request it — any restrictions. (3) How long it takes — expected delivery time. No IT jargon, no team names, no process codes. |  | Item descriptions are the only information a user has to decide if this is the right item. Technical descriptions written for IT teams ('Submits a ticket to the AD team to provision an O365 account') drive misdirected requests and abandonment.

## Dependencies
03 — Item Template Standards — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Category Rationalization (Workbook 01) approved | Required | Customer ITSM Owner | Sprint 3 Wk 2 | Item template standards reference category structure.
2 | Catalog Item Triage (Workbook 02) complete | Required | Customer ITSM Owner | Sprint 4 Wk 1 | Standards are validated against the agreed Sprint 4 item list.
3 | Employee Center configuration decisions | Recommended | ECS SA | Sprint 3 | EC portal affects which variable types display correctly on mobile and EC.

## Configuration Data
03 — Item Template Standards — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Shared Variable Set — Applied to All Catalog Items
Variable: Requested For | Reference — sys_user | Who is this request for? Defaults to current user. Delegates allowed.
Variable: Business Justification | Multi-line text — Optional | Why is this needed? Not mandatory unless item type requires it.
Variable: Urgency | Choice: High / Medium / Low — default Medium | Used to set RITM priority. Map to SLA if SLA is applied.
Shared variable set name | ECS_Catalog_Common | Apply this set to every catalog item before adding item-specific variables.
2. Item-Specific Variable Standards
Maximum item-specific variables at MVP | 5 | Exceptions require ITSM Process Owner approval and documentation.
Allowed variable types (OOTB only) | Single Line Text, Multi-Line Text, Reference, Choice, Date, Yes/No, Attachment | No custom UI pages. No complex client scripts at MVP.
Mandatory field policy | Mandatory only if empty value prevents fulfillment | Review each mandatory field: if fulfilment can proceed without it, make it optional.
Variable naming convention | snake_case, no spaces, prefixed by item code — e.g., eq_serial_number | Consistent naming enables bulk reporting across catalog items.
3. Catalog Item Description Template
Line 1 — What you receive | [Plain language — what IT delivers] | Example: 'A laptop pre-configured with your standard software image, delivered to your desk within 5 business days.'
Line 2 — Who can request | [Eligibility statement or 'All employees'] | Example: 'Available to all permanent employees. Contractors must obtain manager approval first.'
Line 3 — Delivery time | [Expected fulfillment duration] | Example: 'Expected delivery: 5 business days for standard models; 10 business days for configure-to-order.'
4. Item Quality Checklist (ECS SA pre-launch validation)
Description follows 3-element template | Yes / No | Reject if description uses IT jargon or team names.
Variable count ≤ 5 item-specific | Yes / No | Reject if >5 item-specific variables without ITSM PO approval.
All variables use OOTB types | Yes / No | Reject if custom UI pages or complex client scripts are used.
Shared variable set applied | Yes / No | ECS_Catalog_Common must be applied before item-specific set.
Delivery time field populated | Yes / No | Reject if delivery_time is blank.
Fulfillment group assigned | Yes / No | Reject if fulfillment_group is blank.
Category matches Workbook 01 structure | Yes / No | Reject if category is not in the approved structure.
Item tested in non-prod with a test RITM | Yes / No | Reject if not tested before promoting to production.

## R&R
03 — Item Template Standards — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Draft item template standards | R/A | I | ECS SA owns this workbook entirely.
Review and approve template standards | I | R/A | Customer ITSM Process Owner approves before Sprint 4 build begins.
Build shared variable set (ECS_Catalog_Common) | R/A | I | ECS SA configures the shared variable set in ServiceNow.
Apply quality checklist to each item before go-live | R/A | I | ECS SA runs the checklist; no item goes live without passing.
Approve exceptions to the 5-variable rule | I | R/A | Customer ITSM Process Owner approves exceptions.
Document variable design decisions for each Sprint 4 item | R/A | I | ECS SA documents in the item build notes.

## Consultant Guide
03 — Item Template Standards — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The 5-variable rule conversation
Customers frequently push back on the 5-variable rule because their legacy items had 15+ variables. The response: 'Look at the last 50 requests submitted for this item. Which of those 15 fields were actually filled in? Which fields, if left blank, would have changed what the fulfillment team did?' In most cases, only 3–4 variables actually influence fulfillment. The rest are data-collection aspirations that the fulfillment team never reads. Start with 5; add variables in Phase 2 if the data shows they're needed.
Shared variable set setup
Configure the ECS_Catalog_Common shared variable set in Sprint 3 before any item build begins. The three common fields (Requested For, Business Justification, Urgency) should be on every catalog item regardless of type. This ensures consistent data for reporting and SLA calculation. The shared variable set also simplifies Employee Center variable display — OOTB EC renders shared variable sets cleanly without additional configuration.
Record Producers vs. Catalog Items
If a customer has a catalog item that genuinely requires more than 10 variables to capture useful data (e.g., a complex project intake form), suggest a Record Producer instead of a catalog item. Record Producers create records in any ServiceNow table (not just RITM) and support complex form layouts. They are still catalog-accessible but are designed for complex data capture, not simple request fulfillment. Use sparingly — most catalog requests don't need this.

## Adoption vs Re-engineering
03 — Item Template Standards — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Our legacy items have 15+ variables and users are used to them | Rebuild items with 5 or fewer item-specific variables plus the shared common set. Move remaining variables to fulfillment notes or a post-submission form if absolutely necessary. | More variables = lower self-service completion rate. Legacy variable sets were designed when IT needed to capture everything upfront because there was no way to contact the requester. ServiceNow RITM conversations allow the fulfillment team to ask follow-up questions — this replaces the need for exhaustive upfront capture. | 'Your users have 15 fields to fill in before they can submit. Our data shows that completion rates drop 15-20% for every field added beyond 5. Let's identify the 5 fields that actually change what the fulfillment team does, and let the team ask for the rest if they need it. Users who can submit in 2 minutes are more likely to use the catalog than users who have to fill in a form.' | If a regulatory or audit requirement mandates specific data fields at submission time, they may be added as mandatory variables. Document the regulatory basis. Still aim to keep total variables below 10.
We want to use custom scripts and UI policies for complex validation | Use OOTB variable conditions and mandatory/optional settings for validation. Reserve custom scripts for genuinely unique business logic that has no OOTB equivalent. | Custom client scripts and UI policies break on ServiceNow upgrades and prevent Virtual Agent from reading variable values for AI-assisted request fulfillment. | 'OOTB variable conditions cover 90% of the validation logic I've seen in legacy catalogs. Let me show you what we can do without scripting — you'll be surprised how far OOTB gets us. If there's something genuinely unique after that, we'll scope it specifically rather than using scripting as the default.' | Complex calculation logic (e.g., cost estimation based on variable inputs) may require a client script. Scope explicitly, document, and plan for upgrade testing.

## ServiceNow Mapping
03 — Item Template Standards — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Variable Tables
item_option_new | Catalog Item Variable | Stores individual variables. References sc_cat_item.
io_set_item | Variable Set Item | Associates a variable set with a catalog item.
sc_variable_set | Variable Set | The shared variable set definition.
2. Key Variable Fields
question_text | Field label shown to user | Follow the plain-language naming standard.
type | Variable type (1=Single Line, 2=Multi-Line, 3=Choice, etc.) | Use OOTB types only.
mandatory | true/false | Only true if empty value prevents fulfillment.
reference_table | Table for Reference type variables | e.g., sys_user for Requested For.
3. Employee Center Variable Display
EC variable rendering | Employee Center renders shared variable sets cleanly by default | No additional portal widget configuration needed for shared variable sets.
Mobile variable support | OOTB variable types render on ServiceNow Mobile without scripting | Custom UI pages do not render on Mobile. Additional reason to avoid them.