## Instructions
04 — Fulfillment Workflow Decisions
Service Catalog Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the fulfillment workflow pattern for each catalog item in the Sprint 4 build list: who fulfills it, how it is routed, what the completion criteria are, and which OOTB workflow model applies. The goal is to use OOTB flow designer catalog workflows without custom logic, routing all items to the correct group through standard assignment rules.
Who fills this out | ECS SA completes the OOTB workflow recommendation; customer fulfillment team leads confirm routing and completion criteria. Complete this workbook for each Sprint 4 item before the item is built in ServiceNow.
Sprint window | Sprint 4 Weeks 1–2
Estimated effort | 1–2 hours (one per-item workflow review session with fulfillment team leads)
Related workbooks | 02 Catalog Item Inventory · 03 Item Template Standards · 05 Approval Matrix
Success criteria
• | Every Sprint 4 item has a documented fulfillment workflow model (Simple, Approval-then-Fulfill, Multi-stage).
• | Fulfillment group is confirmed for every item.
• | Completion criteria are defined for every item (what does 'done' look like?).
• | Delivery time is confirmed and set on the catalog item.
• | No item requires a custom Flow Designer subflow for MVP fulfillment.

## Process Decisions
04 — Fulfillment Workflow Decisions — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which OOTB fulfillment workflow model applies to most catalog items? | Simple fulfillment: RITM assigned to fulfillment group, group works the RITM, resolves when complete. Use this for 80%+ of catalog items. Add approval only when a business rule or policy genuinely requires it (see Workbook 05). |  | Adding approvals to every item adds 1–2 days of fulfillment time and reduces catalog adoption. The OOTB simple fulfillment model is purpose-built for the 80% of requests that don't need an approval step.
2 | Should we use OOTB Flow Designer catalog workflows or custom Workflow Editor flows? | Use OOTB Flow Designer catalog spokes and actions. Do not use the legacy Workflow Editor for new catalog items. |  | Flow Designer is the ServiceNow platform direction. Workflow Editor flows are not forward-compatible with Now Assist GenAI features and require additional upgrade maintenance. Any new catalog flow built in the legacy Workflow Editor is technical debt from day one.
3 | How should we handle multi-team fulfillment (e.g., an item that requires both the server team and the network team)? | Use OOTB catalog task chaining: create sequential or parallel catalog tasks within the RITM, each assigned to a different group. The OOTB Catalog Task (sc_task) table handles multi-team fulfillment without custom flows. |  | Multi-team fulfillment is a common pattern. OOTB catalog tasks handle this natively. Custom flows that split RITMs into child tickets create reporting complexity and break standard RITM dashboards.
4 | What are the completion criteria for a catalog item? | Define a specific, observable outcome for each item. 'Laptop delivered and user can log in' is a completion criterion. 'Fulfillment complete' is not. Completion criteria drive RITM closure quality and SLA accuracy. |  | Vague completion criteria mean RITMs are closed prematurely or left open indefinitely. Clear criteria enable the fulfillment team to close RITMs confidently and enable audit of fulfillment quality.
5 | How should catalog items with integration dependencies be handled at MVP? | Build the catalog item with a manual fulfillment workflow at MVP. Add the integration trigger (e.g., AD account creation, SCCM software push) as a Flow Designer spoke action in Sprint 6 after the integration is validated. |  | Building integration-dependent automation before the integration is stable creates brittle workflows. The manual fulfillment MVP approach gets the item live and in use while the integration is being validated in parallel.

## Dependencies
04 — Fulfillment Workflow Decisions — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Catalog Item Triage (Workbook 02) — Sprint 4 item list confirmed | Required | Customer ITSM Owner | Sprint 4 Wk 1 | Cannot design fulfillment workflows without the confirmed item list.
2 | Approval Matrix (Workbook 05) agreed | Required | Customer ITSM Owner | Sprint 4 Wk 1 | Workflow model (simple vs. approval-then-fulfill) depends on approval decisions.
3 | Fulfillment team leads available for per-item review | Required | Customer IT Ops | Sprint 4 Wk 1 | Fulfillment leads confirm routing and completion criteria.
4 | Integration Accelerator Pack status (if items have integration dependencies) | Recommended | ECS Architect | Sprint 4 Wk 1 | Integration readiness determines whether automation can be added in Sprint 4 or must be deferred to Sprint 6.

## Configuration Data
04 — Fulfillment Workflow Decisions — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Fulfillment Workflow Template (one section per Sprint 4 item)
Catalog Item Name | [From Workbook 02 triage list]
Fulfillment Model | [Simple / Approval-then-Fulfill / Multi-stage] | Simple = RITM → fulfill → close. Approval = approval step before RITM is assigned. Multi-stage = catalog tasks.
Primary Fulfillment Group | [Customer to complete] | Must be an existing assignment group.
Secondary Fulfillment Group (if multi-stage) | [Customer to complete or N/A] | Required only for multi-stage items with catalog task chaining.
Completion Criteria | [Customer to complete — specific observable outcome] | Example: 'Account created and user can authenticate. Confirmed by fulfillment team.'
Delivery Time (business days) | [Customer to complete] | Used to set the delivery_time field and SLA calculation.
Integration Dependency? | [Yes / No] | If Yes, automation deferred to Sprint 6. Manual fulfillment at MVP.
Flow Designer Spoke / Action (if integration) | [Sprint 6 scope — placeholder] | Document the intended integration action for Sprint 6 planning.
2. OOTB Fulfillment Workflow Models
Simple Fulfillment | RITM created → assigned to fulfillment group → worked → closed | Use for 80%+ of catalog items. No approval, no catalog tasks.
Approval-then-Fulfill | RITM created → approval step → if approved, assigned to fulfillment group → worked → closed | Use only when policy or business rule mandates approval.
Multi-stage (Catalog Tasks) | RITM created → sequential or parallel sc_tasks created → each task assigned to group → all tasks complete → RITM closed | Use for items requiring multiple teams. OOTB catalog task chaining.

## R&R
04 — Fulfillment Workflow Decisions — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Recommend OOTB fulfillment workflow model per item | R/A | C | ECS SA recommends; customer fulfillment leads confirm.
Confirm fulfillment group for each item | I | R/A | Customer fulfillment team leads confirm group assignment.
Define completion criteria for each item | C | R/A | Customer fulfillment teams define what 'done' looks like; ECS SA records.
Configure Flow Designer workflow per item | R/A | I | ECS SA configures in ServiceNow.
Test fulfillment workflow with test RITM in non-prod | R/A | C | ECS SA tests; customer fulfillment lead validates the test RITM.
Document integration deferred items for Sprint 6 planning | R/A | I | ECS SA documents the integration scope for Sprint 6.

## Consultant Guide
04 — Fulfillment Workflow Decisions — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The 80/20 workflow principle
Eighty percent of catalog items should use simple fulfillment. The remaining 20% may have an approval step. The very small minority (complex, multi-team items) use catalog task chaining. If you find yourself designing a complex custom Flow Designer flow for a standard request, stop and ask: 'Is this a catalog item or a process that should be managed as a project?' Complex custom flows are a signal that the request scope is too broad for the catalog.
Flow Designer vs. Workflow Editor
Never build new catalog workflows in the Workflow Editor. If the customer insists on migrating their legacy Workflow Editor flows, have the conversation about Now Assist: GenAI features (Now Assist for ITSM) read Flow Designer actions but cannot process legacy WE flows. A catalog built on Workflow Editor flows cannot leverage GenAI fulfillment assistance. This is the most compelling argument for rebuilding in Flow Designer.
Catalog task chaining for multi-team items
For items that require sequential steps from multiple teams (e.g., 'New Employee Setup' that requires IT account creation AND workstation provisioning AND badge access), use catalog task chaining rather than custom flows. Configure: one parent RITM, two or three sequential sc_tasks, each assigned to the relevant group. The RITM closes automatically when all tasks are complete. This is OOTB functionality that requires no scripting.

## Adoption vs Re-engineering
04 — Fulfillment Workflow Decisions — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to automate everything from day one — manual fulfillment is not acceptable | Build manual fulfillment for Sprint 4 items. Add automation via Flow Designer spokes in Sprint 6 after integrations are validated. | Automation built before integrations are stable creates brittle workflows that fail silently. A manual fulfillment workflow that works reliably is better than an automated workflow that fails 20% of the time. | 'Manual fulfillment is the safety net that lets us go live fast and prove the catalog works. We add automation in Sprint 6 — the form is already built, the routing is proven, and we're adding one step to a working process rather than building everything at once. This sequence reduces risk significantly.' | If a specific item has a simple, reliable API integration ready and tested, automation can be added in Sprint 4. Validate integration readiness with the ECS Architect before committing.
We need to keep our legacy workflow email triggers | Replace email triggers with OOTB Flow Designer actions and ServiceNow notifications. Do not replicate email-driven workflows. | Email-driven workflow triggers are not auditable, not scalable, and are not compatible with Virtual Agent and Now Assist. Flow Designer provides the same trigger mechanism with full auditability and AI compatibility. | 'Email triggers work until someone's inbox gets full, someone sets up an out-of-office, or the email server has a hiccup. Flow Designer triggers are instant, auditable, and don't have an inbox. Let me show you how the OOTB notification action in Flow Designer replicates exactly what your email trigger does — reliably.' | Never. Email triggers are not an acceptable fulfillment mechanism for a modern ServiceNow catalog.

## ServiceNow Mapping
04 — Fulfillment Workflow Decisions — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Fulfillment Tables
sc_req_item (RITM) | Requested Item | Primary fulfillment record. One per catalog item in a request.
sc_task | Catalog Task | Child tasks for multi-stage fulfillment. Parent = sc_req_item.
sysapproval_approver | Approval Record | Created by approval flow when approval step is required.
2. Flow Designer
Catalog Trigger | Flow Designer > Catalog > Service Catalog Item Requested | OOTB trigger for catalog item submission. Do not use Workflow Editor.
Catalog Task Action | Flow Designer > ServiceNow Core > Create Catalog Task | Creates sc_task records for multi-stage fulfillment.
Approval Action | Flow Designer > ServiceNow Core > Request Approval | OOTB approval step. Use instead of legacy approval engine configuration.