## Instructions
05 — Approval Matrix
Service Catalog Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines which catalog items require approval, who approves them, and what the OOTB approval policy configuration looks like. The default position is no approval — approvals are added only where a specific business policy, cost threshold, or compliance requirement mandates them. This workbook prevents the common pattern of approvals being added to every item 'just in case'.
Who fills this out | Customer-side: ITSM Process Owner and Finance/Compliance lead (if cost threshold approvals are required). ECS SA recommends the OOTB approval policy configuration. Agreed before Workbook 04 workflow design begins.
Sprint window | Sprint 4 Week 1 (agreed before workflow build)
Estimated effort | 1–2 hours (one approval policy workshop)
Related workbooks | 02 Catalog Item Inventory · 04 Fulfillment Workflow Decisions · Foundation Data Pack — Groups
Success criteria
• | Every Sprint 4 catalog item has an explicit approval decision: required or not required.
• | Where approval is required, the approver role (manager, department head, etc.) is defined.
• | OOTB approval policy is used — no custom approval scripts.
• | Approval SLA (how long an approver has before escalation) is defined.
• | The no-approval default is documented and agreed by the ITSM Process Owner.

## Process Decisions
05 — Approval Matrix — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What is the default approval policy for catalog items? | No approval required by default. Approval is added only where a specific business rule or compliance requirement mandates it. Most IT service requests do not require approval — adding approvals universally adds 1–2 days to every fulfillment cycle without commensurate governance value. |  | Universal approval policies are the most common cause of catalog abandonment. Users who submit a request and wait 3 days for manager approval (who approves 99% of requests) quickly learn to call the helpdesk instead. Targeted approvals on high-cost or compliance-sensitive items provide governance value without penalising routine requests.
2 | What triggers an approval requirement? | Three triggers: (1) Cost threshold — items above a defined cost threshold require manager approval. (2) Compliance/regulatory — items involving privileged access or sensitive data require security team approval. (3) Policy — items where HR or Finance policy mandates sign-off (e.g., new hire equipment for contractors). |  | Any trigger beyond these three is likely a process smell: either the item is not well-suited for the catalog, or the approval reflects a trust deficit in the fulfillment team. Address the root cause rather than adding approval overhead.
3 | Who should be the approver for a standard cost-threshold approval? | Requestor's direct manager (OOTB manager approval field on the user record). Do not build custom approver lookup logic unless the manager field is unreliable. |  | The OOTB manager approval field is populated from the user record and requires no custom lookup. Custom approver logic (e.g., 'find the department head from a cost centre table') requires maintenance and breaks when org structures change.
4 | What should the approval SLA be? | 24 business hours for standard approvals. After 24 hours, escalate to the approver's manager. After 48 hours, return the request to the requester with a note to resubmit. Do not let requests sit in approval indefinitely. |  | Unresolved approvals are a leading cause of RITM backlog. An OOTB approval SLA with escalation ensures approvers are reminded and requests don't expire silently.
5 | Should we use group approval or individual approval? | Individual approval (direct manager) for cost-threshold items. Group approval (security team) for privileged access items. Never use ad-hoc 'any member of the group can approve' for compliance-sensitive items — use designated approvers with individual accountability. |  | Group approval is appropriate for operational approvals where any authorised team member can review. Compliance-sensitive approvals require individual accountability — you need to know who approved what.

## Dependencies
05 — Approval Matrix — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Catalog Item Triage (Workbook 02) — Sprint 4 item list confirmed | Required | Customer ITSM Owner | Sprint 4 Wk 1 | Approval matrix is built against the confirmed item list.
2 | Cost threshold policy confirmed by Finance or IT Director | Required | Customer Finance / IT Director | Sprint 4 Wk 1 | Cost thresholds are a business policy decision, not an IT configuration decision.
3 | Foundation Data Pack — Users (manager field populated) | Required | ECS SA | Sprint 0 | OOTB manager approval requires the manager field to be populated on user records.
4 | Compliance/regulatory requirements review | Recommended | Customer Compliance Lead | Sprint 4 Wk 1 | Identify items with external compliance requirements (SOX, HIPAA, etc.) that mandate approval.

## Configuration Data
05 — Approval Matrix — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Approval Policy Matrix (one row per Sprint 4 item)
Catalog Item Name | [From Workbook 02]
Approval Required? | [Yes / No] | Default: No. Yes only with documented business rule.
Approval Trigger | [Cost threshold / Compliance / Policy / N/A] | Document the specific rule that requires approval.
Approver Role | [Manager / Security Team / IT Director / N/A] | Who approves? Use OOTB manager field where possible.
Approval SLA | [24 hrs / 48 hrs / N/A] | Time before escalation. Default: 24 business hours.
Escalation Path | [Approver's manager / ITSM PO / N/A] | Who is notified if approval SLA breaches?
OOTB Approval Policy Name | [ECS SA to complete] | The approval policy record in ServiceNow. ECS SA configures.
2. OOTB Approval Policy Configuration Standards
Approval policy type | Catalog Item Approval Policy (OOTB) | Configure in Service Catalog > Approval Policies. Do not use custom tables.
Approver source — manager | OOTB: requested_for.manager | Reads from the user record. Requires manager field populated.
Approver source — security team | OOTB: Approval Group = [Security Team assignment group] | Any member of the group can approve for operational approvals.
Approval SLA configuration | OOTB: SLA on sysapproval_approver table | Configure in SLA > Definitions. Apply to approval records, not RITM.
Auto-approval for low-value items | Not recommended at MVP | Auto-approval can be configured in Phase 2 based on usage data.

## R&R
05 — Approval Matrix — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Define approval trigger policy (cost thresholds, compliance items) | I | R/A | Customer Finance / IT Director defines the policy; ECS SA records.
Recommend OOTB approval configuration for each policy type | R/A | C | ECS SA recommends; customer approves the technical approach.
Complete approval matrix (one row per Sprint 4 item) | C | R/A | Customer ITSM PO completes with input from Finance and Compliance leads.
Configure OOTB approval policies in ServiceNow | R/A | I | ECS SA configures after matrix is approved.
Configure approval SLA and escalation | R/A | I | ECS SA configures OOTB SLA on approval records.
Test approval workflow for each approval-required item | R/A | C | ECS SA tests; customer approver validates the approval notification.

## Consultant Guide
05 — Approval Matrix — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The no-approval default conversation
The hardest part of the approval matrix workshop is getting the customer to accept that most items should not require approval. The framing: 'Every approval adds 24-48 hours to the request. If your manager approves 99% of requests without reading them, that 48 hours is pure delay with no governance value. Let's save approvals for the 10% of items where the manager actually needs to make a decision.' Then walk through each item and ask: 'What would happen if we fulfilled this without approval?' Usually, the answer is 'nothing bad' for 80% of items.
Privilege access approval is non-negotiable
Do not let the customer skip approvals for privileged access requests (admin account creation, elevated permissions, VPN access for external parties). These are compliance requirements in almost every security framework (SOX, ISO 27001, SOC 2). If the customer pushes back, document the risk and have the IT Director sign off. This is not an ECS preference — it is an audit requirement.
Manager field dependency
The OOTB manager approval model only works if the manager field is populated on user records. Before Sprint 4 starts, validate that the Foundation Data Pack loaded manager relationships correctly. Run a query: SELECT COUNT(*) FROM sys_user WHERE manager IS NULL AND active = true. If more than 10% of active users have no manager, this must be resolved before approval-required items are configured.

## Adoption vs Re-engineering
05 — Approval Matrix — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want every request to require manager approval | Apply the no-approval default. Add approval only where a specific policy requires it. | Universal approval degrades the value of the catalog. If every request requires approval, users call the helpdesk instead of submitting a request — defeating the purpose of a self-service catalog. | 'If a manager approves 95% of requests without question, the approval is friction, not governance. Governance value comes from selective approvals where the manager actually makes a decision. Let's target the 10% of requests where approval changes the outcome — those are the ones that deserve the governance step.' | Never universal approval. If a specific compliance requirement mandates approval on every item in a category, document the requirement and apply it to that category only — not the entire catalog.
We want custom approval routing based on cost center or department hierarchy | Use OOTB manager approval (reads from user record) for cost-threshold items. Custom routing logic requires maintenance when org structures change. | Custom approval routing breaks every time the org structure changes. The OOTB manager field is maintained by HR systems and stays current. Custom cost centre routing requires a separate maintenance process. | 'Custom routing sounds precise until your org restructures and the routing table is three months out of date. The OOTB manager field is maintained by your HR system — it's always current. If a specific item genuinely needs a non-manager approver, we can add that as a named approver on the catalog item without building a complex routing engine.' | If the customer has a complex cost centre approval hierarchy that is formally maintained by Finance, a simple lookup table (not a custom rule engine) is acceptable. Design with Practice Lead.

## ServiceNow Mapping
05 — Approval Matrix — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Approval Tables
sysapproval_approver | Approval Record | One record per approver per RITM. Created by Flow Designer approval action.
sc_cat_item_approval_policy | Catalog Item Approval Policy | Links an approval policy to a catalog item.
2. Approval Configuration
Approval Policy | Service Catalog > Approval Policies | Define OOTB approval policies here. One policy per approval pattern.
Manager field | sys_user.manager | OOTB field. Populate from Foundation Data Pack or HR integration.
Approval SLA | SLA > Definitions > apply to sysapproval_approver | Set to 24 business hours. Configure escalation to approver's manager.