## Customer Dependencies
CONNECTION - CUSTOMER RESPONSIBILITIES & DEPENDENCY TRACKER
Operationalizes SOW v2.0 Section 6. These are structural dependencies that GATE ECS's ability to build on schedule. ECS flags each milestone in advance; at-risk items are jointly assessed and logged in the sprint workbook before they become a delay.
ID | Dependency | Type | Connection Owner | Due / Timing Rule | Target Sprint | Status | Impact if Late | Notes / Date
DEP-01 | Foundation Accelerator Pack workbooks completed (users, locations, departments, groups, assignment rules, schedules, SLAs) | Pre-Build | Connection PM + SMEs | Due 1 week before each in-scope execution sprint | Sprint 0-1 | Not Started | Build cannot start; sprint slips | ECS provides templates
DEP-02 | SSO/AD configuration details + technical SME access for integration review | Pre-Build | Technical Lead | Sprint 0 | Sprint 0 | Not Started | SSO/AD config blocked; access issues at go-live
DEP-03 | Licenses procured; dev/test environments provisioned with ECS admin access | Pre-Build | IT / Procurement | Sprint 0 | Sprint 0 | Not Started | No environment to build in | Structural gate
DEP-04 | MID Server(s) configured and validated | Pre-Build | Technical Lead | By end of Sprint 0 | Sprint 0 | Not Started | Discovery/integrations blocked; possible added cost | SOW: avoid delays/costs
DEP-05 | Complete IP Range Sets documented for Discovery schedules | Pre-Build | Technical Lead | Sprint 0-2 | Sprint 2 | Not Started | Discovery cannot run / incomplete CMDB
DEP-06 | Named Product Owner with acceptance authority | Pre-Build | Executive Sponsor | Sprint 0 | Sprint 0 | Not Started | No one to accept stories; 3-day clock cannot run | Single empowered decision-maker
DEP-07 | Named SMEs per process area (ITSM, Catalog, CMDB/Discovery, Integrations, Employee Experience) | Pre-Build | Connection PM | Sprint 0 | Sprint 0 | Not Started | Workshops cannot be scheduled/decided
DEP-08 | Executive Sponsor confirmed and available for governance cadence (bi-weekly, 45 min) | Pre-Build | Executive Sponsor | Sprint 0 onward | Sprint 0 | Not Started | Governance and escalation stall
DEP-09 | SME availability for workshops and validation sessions as scheduled | Ongoing | Connection PM | Per ECS/PM schedule | All sprints | Not Started | Cold/late workshops; rework
DEP-10 | User story acceptance decisions within 3 business days of demo | Ongoing | Product Owner | 3 business days post-demo | All sprints | Not Started | Stories pushed to backlog; may trigger a PCR | SOW-defined window
DEP-11 | Governance Triage Log review and disposition within 5 business days | Ongoing | Executive Sponsor | 5 business days post-submission | All sprints | Not Started | Deviations unresolved; build blocked
DEP-12 | Data quality ownership (accuracy/completeness of Accelerator Pack data) | Ongoing | Connection | Continuous | All sprints | Not Started | Bad data -> rework, CMDB health miss
DEP-13 | CAB members available for Change Management configuration workshops | Ongoing | CAB Members | Sprint 4 | Sprint 4 | Not Started | Change/CAB config blocked
DEP-14 | UAT testers assigned and available with sufficient platform knowledge | Ongoing | UAT Lead | UAT window (Sprint 6-7) | Sprint 6-7 | Not Started | UAT cannot complete; go-live at risk
DEP-15 | End-user communication, change management, and adoption (beyond train-the-trainer) | Ongoing | Connection | Sprint 7-8 onward | Sprint 7-8 | Not Started | Low adoption; value not realized | Customer-owned per SOW
DEP-16 | Ongoing knowledge content creation and maintenance | Ongoing | Connection | Continuous | All / ongoing | Not Started | Thin KB; weak deflection | Customer-owned per SOW
DEP-17 | Vonage-side integration tasks completed | Ongoing | Connection / Vonage Admin | Sprint 4 (with CTI build) | Sprint 4 | Not Started | CTI/phone channel not functional | Customer-owned per SOW
SUMMARY
Total dependencies | 17
Complete | 0
In Progress | 0
At Risk / Blocked / Overdue | 0
Not Started | 17