## PCR Log
CONNECTION - PROJECT CHANGE REQUEST (PCR) LOG
Per SOW Sec 9. Any scope/schedule change, or the 6th approved customization, or chronic acceptance/dependency delay, is logged and dispositioned here.
PCR ID | Date Raised | Trigger | Description | Impact (scope/budget/schedule) | Disposition | Two-Key (Sponsor / ECS Practice) | Status | Notes

## PCR Request Form
PCR REQUEST FORM (template - copy per request)
Complete one form per PCR. The Solution Architect drafts the impact assessment; the two-key decision approves/rejects.
PCR ID
Date raised
Raised by
Trigger
Description of change
Business need / justification
OOTB alternative considered (SA)
Scope impact
Budget impact
Schedule impact
Upgrade/technical impact (SA)
Sponsor decision (business need)
ECS Practice decision (technical path)
Final disposition
Decision date
Logged in PCR Log? (Y/N)

## Acceptance & Sign-off Log
ACCEPTANCE & SIGN-OFF LOG
Operationalizes the SOW 3-business-day acceptance window. Late acceptance pushes stories to backlog and may trigger a PCR.
Item ID | Type | Description | Demo / Delivery Date | Acceptance Due (3 biz days) | Accepted By | Date Accepted | Status | Notes

## Decision Register
DECISION REGISTER
Running log of engagement decisions (beyond deviations, which live in the Triage Log).
Decision ID | Date | Topic / Area | Decision | Made By | Source (workshop / meeting) | Status | Notes

## Assumptions & Out-of-Scope
ASSUMPTIONS & OUT-OF-SCOPE REGISTER
Per SOW Sec 7-8. Track assumptions (and whether they hold) and out-of-scope items (so scope creep is visible).
ID | Type | Statement | SOW Ref | Owner | Status | Impact if Wrong / Requested | Notes
A-01 | Assumption | Connection provides timely, accurate data via Accelerator Packs | Sec 6/8 | Connection PM | Holds | Rework, CMDB health miss
A-02 | Assumption | Existing Discovery/Catalog configs are leveraged only where free of technical debt | Sec 2 | Solution Architect | Holds | Added scope if debt found
A-03 | Assumption | Connection completes Vonage-side integration tasks | Sec 6 | Connection | Holds | CTI not functional
O-01 | Out-of-Scope | Event Management (EM) - later phase | Sec 7 | - | Confirmed | PCR if requested in Phase 1
O-02 | Out-of-Scope | Now Assist / GenAI - later phase | Sec 7 | - | Confirmed | PCR if requested
O-03 | Out-of-Scope | SAM (Software Asset Mgmt) beyond foundations | Sec 7 | - | Confirmed | PCR if requested
O-04 | Out-of-Scope | End-user training delivery & broader OCM (customer-owned) | Sec 11 | Connection | Confirmed | Adoption risk if not done