## RACI
CONNECTION - RACI MATRIX (deliverable & activity level)
R=Responsible (does it), A=Accountable (owns the outcome, one per row), C=Consulted, I=Informed. ECS roles + Connection roles.
Activity / Deliverable | EM | SA | PC | TC | Prac.Lead | Sponsor | Prod.Owner | Cust.PM | Tech.Lead | SMEs
Engagement governance & status reporting | A | I | I | I | C | I | I | C | I | I
Customization Council / two-key decisions | A | R | C | I | R | R | C | I | I | I
Project plan & schedule | A | C | C | I | I | I | C | R | I | I
Customer dependency management | A | I | I | I | I | C | C | R | C | C
Workshops facilitation & sign-off | C | C | R | I | I | I | A | C | C | R
OOTB vs customization decisions (Rule of Three) | C | R | C | C | A | C | C | I | I | I
Platform architecture & CSDM alignment | I | A | C | C | C | I | C | I | R | C
Configuration build (per story) | I | C | C | R | I | I | A | I | C | C
Integrations & SGC build | I | A | I | R | C | I | I | I | R | C
Vonage CTI / Interactions build | I | A | I | R | C | I | I | I | C | R
Accelerator pack data completion | I | C | C | I | I | I | A | R | C | R
Data quality & validation | I | C | C | C | I | I | A | R | C | R
Story acceptance (3-day window) | C | C | C | I | I | I | A | C | I | C
Governance Triage Log disposition | R | C | I | I | C | A | C | I | I | I
SIT execution | I | C | I | R | A | I | I | I | C | I
UAT coordination & execution | C | C | C | I | A | I | C | R | I | R
Defect triage & resolution | C | A | C | R | C | I | C | I | I | I
Go-Live readiness & sign-off | R | C | C | I | C | A | R | C | C | I
Cutover execution | A | R | C | R | C | I | I | C | R | I
Admin KT & Train-the-Trainer | I | R | R | C | I | I | C | C | C | R
Knowledge content creation (ongoing) | I | I | C | I | I | I | A | R | I | R
End-user comms & adoption | I | I | C | I | I | C | A | R | I | C
Hypercare support | A | C | C | R | C | I | C | C | R | I
Operational handoff & ownership | A | C | I | I | C | R | C | R | R | I
Lessons learned & closeout | A | C | C | I | C | C | C | C | I | I
Legend: R = Responsible A = Accountable C = Consulted I = Informed
Roles: EM=Engagement Mgr, SA=Solution Architect, PC=Process Consultant, TC=Technical Consultant, Prac.Lead=ECS Practice Lead; Sponsor/Prod.Owner/Cust.PM/Tech.Lead/SMEs = Connection