## SIT Scripts
CONNECTION - SIT (SYSTEM INTEGRATION TEST) SCRIPTS
ECS-internal integration testing before UAT. Validates each integration touchpoint end-to-end in sub-production.
SIT ID | Integration | Scenario | Pre-Conditions | Test Steps | Expected Result | Result | Defect ID
SIT-01 | AD/SSO | SSO login + attribute mapping | IdP configured; test users in AD | 1. Initiate SSO login as a test user 2. Confirm SAML assertion accepted 3. Verify user record + attributes | User authenticates; profile attributes populate from AD
SIT-02 | AD groups | Group-to-role sync | AD group mapping configured | 1. Add a test user to a mapped AD group 2. Run/await the group import 3. Check ServiceNow group/role membership | User receives the mapped group/role in ServiceNow
SIT-03 | SCCM SGC | CI import + class mapping | SCCM connector configured; MID up | 1. Run the SCCM scheduled import 2. Inspect imported CIs and classes 3. Validate sample against SCCM | In-scope CIs populate with correct class/attributes; no load errors
SIT-04 | Intune | Endpoint CI import | Intune connector configured | 1. Run the Intune import 2. Inspect mobile/endpoint CIs | Intune-managed devices appear as CIs
SIT-05 | IRE | Reconciliation / dedup across sources | SCCM + Intune + Discovery active | 1. Ingest a CI present in two sources 2. Confirm IRE matches to one record | Single authoritative CI per source-of-record rules; no duplicates
SIT-06 | Email | Outbound + inbound | SMTP relay + inbound mailbox set | 1. Trigger a notification 2. Send an inbound test email | Notification delivered; inbound action creates/updates the correct record
SIT-07 | Vonage CTI | Inbound call -> Interaction -> Incident | OpenFrame + Vonage adapter configured | 1. Place an inbound test call 2. Confirm screen-pop Interaction with caller match 3. Create an incident from the Interaction | Call opens a matched Interaction; linked incident is created
SIT-08 | CMDB->Change | CI impact drives change risk | CMDB populated; CSDM maps built | 1. Raise a change against a CI 2. Confirm affected services/CIs + risk score | Change shows CI/service impact and a CI-driven risk score

## Test Data Plan
TEST DATA PLAN (SIT + UAT)
What test data is needed, its source, and how it is refreshed/anonymized for testing.
# | Data set | Purpose | Source | Volume | Refresh / Anonymization | Owner | Status
1 | Users & groups | SSO/role testing | AD import (subset) | ~50 test users | Refresh from AD; no anonymization needed (internal) | Tech Lead | Not Started
2 | CIs (servers/endpoints) | CMDB/Change/Discovery | SCCM/Intune (subset) | ~100 CIs | Discovery/connector run in sub-prod | Integration Engineer | Not Started
3 | Catalog items + requests | Request/fulfillment | Configured items | Top 10-15 items | Created during build | Process Consultant | Not Started
4 | Knowledge articles | Search/VA/deflection | Ported baseline | ~20 articles | Ported from legacy; reviewed | Knowledge Manager | Not Started
5 | Incidents/Problems (seed) | Incident/Problem/PI | Generated | ~30 records | Created for PI similarity + reporting | Process Consultant | Not Started
6 | Phone test number + agent | Vonage CTI | Vonage tenant | 1 number, 1 agent | Provided by Connection | Connection / CTI | Not Started