## Overview
CONNECTION - UAT END-TO-END TEST SCRIPTS
End-to-end business journeys grouped into suites. Each script traces directly to the user stories it validates (Stories Validated column + Story Coverage tab).
What this is
Purpose | End-to-end UAT scripts for end users (business validation), grouped by functional suite to keep UAT contained. This is NOT story testing - story acceptance criteria are validated by the team during the sprint.
Traceability | Every script lists the exact story IDs it validates. The Story Coverage tab inverts this so each of the 141 stories shows the UAT script(s) that exercise it (or 'Sprint story-test only').
When | Stage 3 / Sprint 6-7 (UAT, Weeks 13-16), before Go-Live (Week 16).
Result codes | PASS = worked as described ¦ FAIL = did not (log a defect) ¦ BLOCKED = could not run ¦ SKIP = not applicable. Do NOT FAIL for a feature that was never in scope.
Suites
1. Service Desk - Incident Lifecycle
2. Request & Catalog Fulfillment
3. Change & Release
4. Problem to Permanent Fix
5. Employee Self-Service & Deflection
6. Identity & Access
7. CMDB / CSDM & Change Impact
8. Asset Lifecycle (HAM)
9. Knowledge Management
10. Reporting & Dashboards

## Test Scripts
UAT END-TO-END TEST SCRIPTS
Run each script as a journey. Record Result and (if FAIL) a Defect ID. Stories Validated ties each script to the backlog.
Suite | Script ID | Scenario Name | Who Tests | Pre-Conditions | Test Steps | Expected End Result | Stories Validated | Result | Defect ID | Notes
1. Service Desk - Incident Lifecycle | UAT-INC-01 | Report and resolve an issue via Employee Center | Business Tester (Service Desk User + Agent) | User logged into Employee Center; an agent account available; KB seeded | 1. As an employee, open Employee Center and search for the issue. 2. Confirm a relevant knowledge article appears; if it resolves the issue, stop (deflected). 3. If not resolved, create an incident from the portal and submit. 4. As an agent, confirm the incident appears with category, priority (Impact x Urgency), and routed to the correct group. 5. Confirm the SLA timer is visible for the priority. 6. Work and resolve the incident with resolution notes. 7. Confirm the requester receives notification and a satisfaction prompt. | Incident is created via the portal, correctly categorized/prioritized/routed, SLA tracked, resolved, and the requester is notified and surveyed - end to end. | CONN-INC-001, CONN-INC-002, CONN-INC-003, CONN-INC-004, CONN-INC-005, CONN-INC-006, CONN-INC-008, CONN-INC-009, CONN-EC-001, CONN-EC-004, CONN-EC-005, CONN-KM-006, CONN-PA-001
1. Service Desk - Incident Lifecycle | UAT-INC-02 | Report an issue by phone (Vonage CTI) | Business Tester (Service Desk Agent) | Agent logged into the workspace with the Vonage softphone; test number available | 1. Place an inbound test call to the service desk number. 2. Confirm the OpenFrame softphone rings in the agent workspace. 3. Confirm an Interaction opens with the caller matched (screen-pop). 4. Create an incident from the Interaction. 5. Confirm the Interaction links to the incident. 6. Resolve the incident and end the call. | An inbound Vonage call opens a matched Interaction, the agent creates a linked incident, and resolves it - the phone channel works end to end. | CONN-CTI-001, CONN-CTI-002, CONN-CTI-003, CONN-CTI-004, CONN-CTI-005, CONN-INC-004, CONN-INC-006
1. Service Desk - Incident Lifecycle | UAT-INC-03 | Major incident declaration and coordination | Business Tester (Service Desk Manager + Coordinator) | A P1 incident exists or can be created; MIM roles assigned | 1. Create or open a P1 incident that meets the major-incident criteria. 2. Promote/declare it as a Major Incident. 3. Confirm the MIM coordinator and roles engage and the MIM workspace opens. 4. Send a stakeholder communication from a template. 5. Drive the incident to resolution. 6. Confirm a Post-Incident Review (PIR) is generated. | A qualifying P1 is declared major, coordination and comms engage via OOTB MIM, it is resolved, and a PIR is created. | CONN-INC-007, CONN-MIM-001, CONN-MIM-002, CONN-MIM-003, CONN-MIM-004, CONN-MIM-005
2. Request & Catalog Fulfillment | UAT-REQ-01 | Order a catalog item end to end | Business Tester (Requester + Approver + Fulfiller) | Catalog items configured; approver and fulfillment group set | 1. As a requester, open Employee Center and order an in-scope catalog item. 2. Complete the variables and submit the request. 3. As the approver, receive the approval notification and approve (via email or portal). 4. Confirm the request moves to fulfillment and tasks generate to the right group. 5. As the fulfiller, complete the fulfillment tasks. 6. Confirm the request closes and the requester is notified; confirm the SLA tracked. | A catalog request is ordered, approved, fulfilled, and closed with SLA tracking and notifications - the full request lifecycle. | CONN-SCR-001, CONN-SCR-002, CONN-SCR-003, CONN-SCR-004, CONN-SCR-005, CONN-SCR-006, CONN-EC-003, CONN-PF-006
2. Request & Catalog Fulfillment | UAT-REQ-02 | Order a service via Virtual Agent | Business Tester (Requester) | Virtual Agent active with catalog topic; user authenticated | 1. Open the Virtual Agent from Employee Center. 2. Ask to order an in-scope item via conversation. 3. Provide the requested details in the conversation. 4. Submit and confirm a request is created. 5. Verify the request appears in 'my requests'. | A user orders an in-scope item conversationally through the Virtual Agent and a correct request is created. | CONN-VA-001, CONN-VA-006, CONN-SCR-004
2. Request & Catalog Fulfillment | UAT-REQ-03 | Generic catch-all request routing | Business Tester (Requester) | Generic catch-all catalog item configured | 1. Order a service that has no dedicated catalog item using the generic request. 2. Submit and confirm it routes to a defined service path/group. 3. Confirm no user community is left without a path. | A service without a dedicated item is captured by the generic catch-all and routed correctly. | CONN-SCR-001, CONN-SCR-004, CONN-SCR-006
3. Change & Release | UAT-CHG-01 | Normal change with CI impact and CAB approval | Business Tester (Change Requester + CAB Member) | A configuration item exists in CMDB; CAB configured | 1. Raise a Normal change and relate it to an in-scope CI. 2. Complete the risk assessment; confirm CI-driven risk scoring produces a score. 3. Confirm affected services/CIs display from the service map. 4. Confirm the change routes to CAB for review. 5. As CAB, approve the change. 6. Implement and close the change; confirm conflict/blackout checks ran. | A normal change inherits CI/service impact, is risk-scored, reviewed by CAB, approved, implemented, and closed. | CONN-CHG-001, CONN-CHG-002, CONN-CHG-003, CONN-CHG-004, CONN-CHG-006, CONN-CHG-007, CONN-CHG-008, CONN-CMDB-008, CONN-CSDM-008
3. Change & Release | UAT-CHG-02 | Standard (pre-approved) change | Business Tester (Change Requester) | Standard Change Catalog templates configured | 1. Raise a change from a Standard Change template. 2. Confirm it follows the pre-approved path (no full CAB). 3. Implement and close the change. | A standard change is raised from a template, follows the pre-approved path, and closes. | CONN-CHG-005, CONN-CHG-001
3. Change & Release | UAT-CHG-03 | Emergency change expedited path | Business Tester (Change Manager) | Emergency change type active | 1. Raise an Emergency change. 2. Confirm the expedited approval path engages. 3. Approve, implement, and close; confirm post-implementation review if required. | An emergency change follows the expedited approval path and closes with the required review. | CONN-CHG-001, CONN-CHG-006
4. Problem to Permanent Fix | UAT-PRB-01 | Recurring incidents to problem to fix | Business Tester (Problem Manager) | Several related incidents exist; PI similarity active | 1. Identify recurring/similar incidents (PI may surface a cluster). 2. Create a problem from the incidents. 3. Record a workaround in the KEDB and confirm it is discoverable from related incidents. 4. Raise/link a change to deliver the permanent fix. 5. Resolve the problem and confirm linked incidents reflect the resolution. | Recurring incidents become a problem with a KEDB workaround, a change delivers the fix, and the problem resolves - closed-loop. | CONN-PRB-001, CONN-PRB-002, CONN-PRB-003, CONN-PRB-004, CONN-PRB-007, CONN-INC-009, CONN-PI-004, CONN-PI-005, CONN-CHG-001
5. Employee Self-Service & Deflection | UAT-EX-01 | Self-serve via search, knowledge, and Virtual Agent | Business Tester (Employee) | Employee Center live with KB and Virtual Agent | 1. Open Employee Center and search for a common question. 2. Confirm AI Search returns a relevant knowledge article. 3. Open the Virtual Agent and attempt the same request conversationally. 4. Confirm the VA resolves it or offers to create a record. 5. Provide article feedback (useful/not). | An employee self-serves through search, knowledge, and the Virtual Agent - deflecting a ticket or creating one cleanly. | CONN-EC-001, CONN-EC-003, CONN-EC-004, CONN-EC-005, CONN-EC-007, CONN-KM-001, CONN-KM-006, CONN-KM-008, CONN-VA-001, CONN-VA-002, CONN-VA-005, CONN-INC-004
5. Employee Self-Service & Deflection | UAT-EX-02 | Check my ticket status via Virtual Agent | Business Tester (Employee) | Authenticated VA session; user has an open record | 1. Open the Virtual Agent as an authenticated user. 2. Ask for the status of your open incident/request. 3. Confirm the VA returns your record status correctly. | An authenticated user retrieves their ticket status conversationally. | CONN-VA-003, CONN-VA-005, CONN-EC-007
6. Identity & Access | UAT-IAM-01 | SSO login and role-based access | Business Tester (Standard User + Agent) | SSO configured; AD groups mapped to roles | 1. Log in via SSO with a standard user. 2. Confirm successful authentication and appropriate menus/records. 3. Log in as a user in an ITIL group. 4. Confirm the agent sees agent capabilities per their role. 5. Confirm a user without a role cannot access restricted areas. | SSO authenticates users and role/group membership from AD grants the correct access - no more, no less. | CONN-INT-001, CONN-INT-002, CONN-INT-005, CONN-PF-002, CONN-PF-004
7. CMDB / CSDM & Change Impact | UAT-CMDB-01 | CI data flows and drives change impact | Business Tester (CMDB/Change SME) | SCCM/Intune connectors run; CSDM service maps built | 1. Confirm a device discovered by SCCM/Intune appears as a CI in the CMDB. 2. Open the related service map and confirm the CI is in the dependency chain. 3. Raise a change against that CI. 4. Confirm affected services and downstream CIs display for impact assessment. 5. Confirm risk reflects the impact. | Connector-sourced CI data populates the CMDB, builds service maps, and drives change impact and risk - data to decision. | CONN-SGC-001, CONN-SGC-002, CONN-SGC-004, CONN-SGC-006, CONN-CMDB-001, CONN-CMDB-003, CONN-CMDB-008, CONN-CSDM-006, CONN-CSDM-008, CONN-DISC-003
7. CMDB / CSDM & Change Impact | UAT-CMDB-02 | CMDB health and source-of-record reconciliation | Business Tester (CMDB SME) | Multiple CI sources active; IRE rules configured | 1. Open the CMDB Health dashboard and confirm completeness/compliance metrics. 2. Confirm a CI from overlapping sources resolves to a single record per the source-of-record rules. 3. Confirm a duplicate candidate is matched, not duplicated. | CMDB health is measurable and IRE reconciliation keeps a single, authoritative CI across sources. | CONN-CMDB-004, CONN-CMDB-005, CONN-DISC-006, CONN-DISC-008, CONN-SGC-002, CONN-SGC-008
8. Asset Lifecycle (HAM) | UAT-HAM-01 | Asset from intake to retirement | Business Tester (Asset Manager) | Stockrooms and asset classes configured | 1. Intake a new hardware asset into a stockroom. 2. Assign the asset to a user. 3. Confirm the asset links to its CMDB CI. 4. Move the asset through its lifecycle states. 5. Retire and dispose the asset; confirm the record reflects disposal. | A hardware asset is tracked from intake through assignment, CI linkage, and retirement/disposal. | CONN-HAM-001, CONN-HAM-002, CONN-HAM-003, CONN-HAM-005, CONN-HAM-006, CONN-HAM-007, CONN-HAM-008, CONN-CMDB-008
9. Knowledge Management | UAT-KM-01 | Author, review, publish, and consume an article | Business Tester (Knowledge Author + Manager + Consumer) | Knowledge bases and workflow configured | 1. As an author, create an article from a template in the correct KB. 2. Submit it through the review workflow. 3. As a manager, review and publish the article. 4. As a consumer, find the article via Employee Center search and the Virtual Agent. 5. Submit feedback on the article. | An article moves through authoring, review, publish, consumption, and feedback - the knowledge lifecycle. | CONN-KM-001, CONN-KM-002, CONN-KM-003, CONN-KM-004, CONN-KM-005, CONN-KM-006, CONN-KM-008
10. Reporting & Dashboards | UAT-PA-01 | Operational activity reflects in dashboards | Business Tester (Manager / Analytics user) | PA indicators activated; activities performed in prior scripts | 1. Perform or rely on prior incidents, requests, and changes. 2. Open the relevant Performance Analytics dashboard/scorecard. 3. Confirm indicators (MTTR, SLA attainment, request volume, change success) reflect the activity. 4. Confirm thresholds (green/yellow/red) display. 5. Confirm access is correct for the role. | Operational activity surfaces correctly in PA dashboards and scorecards with thresholds and role-based access. | CONN-PA-001, CONN-PA-002, CONN-PA-003, CONN-PA-004, CONN-PA-006, CONN-INC-005, CONN-CHG-003

## Story Coverage
STORY COVERAGE - direct correlation to UAT
Every story and where it is validated in UAT. 'Sprint story-test only' = validated against acceptance criteria during the sprint (not an end-user journey).
Story ID | Module | Story | Validated by UAT script(s) | Validation type
CONN-PF-001 | Platform Foundation | Configure sub-production and production instances | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PF-002 | Platform Foundation | Configure AD/LDAP user import and ongoing sync | UAT-IAM-01 | End-to-end UAT
CONN-PF-003 | Platform Foundation | Load the OOTB location hierarchy | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PF-004 | Platform Foundation | Configure groups and roles at go-live | UAT-IAM-01 | End-to-end UAT
CONN-PF-005 | Platform Foundation | Configure business hour schedules and holiday calendars | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PF-006 | Platform Foundation | Configure outbound and inbound email | UAT-REQ-01 | End-to-end UAT
CONN-PF-007 | Platform Foundation | Deploy and configure the MID Server(s) | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PF-008 | Platform Foundation | Establish platform health baseline KPIs | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CSDM-001 | CSDM | Set CSDM adoption scope to the foundation tier for Phase 1 | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CSDM-002 | CSDM | Load the Business Application inventory | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CSDM-003 | CSDM | Structure the service taxonomy mapped to OOTB CSDM tables | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CSDM-004 | CSDM | Assign Application Service ownership | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CSDM-005 | CSDM | Model service relationships to the agreed depth | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CSDM-006 | CSDM | Align CSDM with CMDB to create accurate service maps | UAT-CMDB-01 | End-to-end UAT
CONN-CSDM-007 | CSDM | Link CSDM services to the Service Catalog | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CSDM-008 | CSDM | Enable CSDM service maps for Change impact assessment | UAT-CHG-01, UAT-CMDB-01 | End-to-end UAT
CONN-CMDB-001 | CMDB | Define in-scope CI classes for go-live | UAT-CMDB-01 | End-to-end UAT
CONN-CMDB-002 | CMDB | Set the CMDB scope boundary | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CMDB-003 | CMDB | Configure CI relationship types and maintenance | UAT-CMDB-01 | End-to-end UAT
CONN-CMDB-004 | CMDB | Set CMDB health targets | UAT-CMDB-02 | End-to-end UAT
CONN-CMDB-005 | CMDB | Define the source of record per CI class | UAT-CMDB-02 | End-to-end UAT
CONN-CMDB-006 | CMDB | Configure CI lifecycle states and retired-CI management | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CMDB-007 | CMDB | Assign CI ownership | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CMDB-008 | CMDB | Integrate CMDB with Change and Incident | UAT-CHG-01, UAT-CMDB-01, UAT-HAM-01 | End-to-end UAT
CONN-DISC-001 | Discovery | Plan MID Server count and placement for Discovery | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-DISC-002 | Discovery | Define Discovery IP ranges and subnets | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-DISC-003 | Discovery | Activate OOTB Discovery patterns for in-scope classes | UAT-CMDB-01 | End-to-end UAT
CONN-DISC-004 | Discovery | Configure Discovery credentials in the vault | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-DISC-005 | Discovery | Set the Discovery schedule and maintenance windows | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-DISC-006 | Discovery | Configure IRE reconciliation and duplicate handling | UAT-CMDB-02 | End-to-end UAT
CONN-DISC-007 | Discovery | Decide and configure cloud Discovery (if in scope) | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-DISC-008 | Discovery | Verify the CMDB after the first Discovery run | UAT-CMDB-02 | End-to-end UAT
CONN-INC-001 | Incident | Configure incident priority via OOTB Impact x Urgency | UAT-INC-01 | End-to-end UAT
CONN-INC-002 | Incident | Configure incident categories and subcategories | UAT-INC-01 | End-to-end UAT
CONN-INC-003 | Incident | Adopt the OOTB incident lifecycle states | UAT-INC-01 | End-to-end UAT
CONN-INC-004 | Incident | Activate in-scope incident intake channels | UAT-INC-01, UAT-INC-02, UAT-EX-01 | End-to-end UAT
CONN-INC-005 | Incident | Configure incident SLAs by priority | UAT-INC-01, UAT-PA-01 | End-to-end UAT
CONN-INC-006 | Incident | Configure incident routing/assignment | UAT-INC-01, UAT-INC-02 | End-to-end UAT
CONN-INC-007 | Incident | Configure Major Incident escalation from Incident | UAT-INC-03 | End-to-end UAT
CONN-INC-008 | Incident | Configure incident notifications | UAT-INC-01 | End-to-end UAT
CONN-INC-009 | Incident | Connect Predictive Intelligence and Knowledge to Incident | UAT-INC-01, UAT-PRB-01 | End-to-end UAT
CONN-MIM-001 | Major Incident | Define major incident criteria | UAT-INC-03 | End-to-end UAT
CONN-MIM-002 | Major Incident | Configure MIM team roles | UAT-INC-03 | End-to-end UAT
CONN-MIM-003 | Major Incident | Configure stakeholder communication templates | UAT-INC-03 | End-to-end UAT
CONN-MIM-004 | Major Incident | Configure major-incident SLAs | UAT-INC-03 | End-to-end UAT
CONN-MIM-005 | Major Incident | Configure the Post-Incident Review (PIR) process | UAT-INC-03 | End-to-end UAT
CONN-MIM-006 | Major Incident | Configure Event Management trigger to MIM (alignment note) | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-MIM-007 | Major Incident | Decide war-room tooling integration (Teams/Zoom/Slack) | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PRB-001 | Problem | Adopt the OOTB problem lifecycle | UAT-PRB-01 | End-to-end UAT
CONN-PRB-002 | Problem | Align problem categories to the incident taxonomy | UAT-PRB-01 | End-to-end UAT
CONN-PRB-003 | Problem | Configure the Known Error Database (KEDB) | UAT-PRB-01 | End-to-end UAT
CONN-PRB-004 | Problem | Configure problem assignment and Problem Manager role | UAT-PRB-01 | End-to-end UAT
CONN-PRB-005 | Problem | Configure problem SLAs and KPIs | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PRB-006 | Problem | Configure problem notifications | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PRB-007 | Problem | Link Problem to Change | UAT-PRB-01 | End-to-end UAT
CONN-PRB-008 | Problem | Connect Predictive Intelligence to Problem | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-CHG-001 | Change | Adopt the 3 OOTB change types | UAT-CHG-01, UAT-CHG-02, UAT-CHG-03, UAT-PRB-01 | End-to-end UAT
CONN-CHG-002 | Change | Adopt the OOTB change lifecycle states | UAT-CHG-01 | End-to-end UAT
CONN-CHG-003 | Change | Configure CI-driven change risk scoring | UAT-CHG-01, UAT-PA-01 | End-to-end UAT
CONN-CHG-004 | Change | Stand up the CAB Workbench | UAT-CHG-01 | End-to-end UAT
CONN-CHG-005 | Change | Configure the Standard Change Catalog | UAT-CHG-02 | End-to-end UAT
CONN-CHG-006 | Change | Configure change approvals and sequence | UAT-CHG-01, UAT-CHG-03 | End-to-end UAT
CONN-CHG-007 | Change | Configure change conflict detection and blackout windows | UAT-CHG-01 | End-to-end UAT
CONN-CHG-008 | Change | Configure change notifications | UAT-CHG-01 | End-to-end UAT
CONN-CHG-009 | Change | Connect Predictive Intelligence/Now Assist to Change (alignment) | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-SCR-001 | Service Catalog | Define and bound the Phase 1 catalog item list | UAT-REQ-01, UAT-REQ-03 | End-to-end UAT
CONN-SCR-002 | Service Catalog | Design catalog variables and variable sets | UAT-REQ-01 | End-to-end UAT
CONN-SCR-003 | Service Catalog | Configure the catalog approval model | UAT-REQ-01 | End-to-end UAT
CONN-SCR-004 | Service Catalog | Structure catalog fulfillment tasks | UAT-REQ-01, UAT-REQ-02, UAT-REQ-03 | End-to-end UAT
CONN-SCR-005 | Service Catalog | Configure catalog request SLAs | UAT-REQ-01 | End-to-end UAT
CONN-SCR-006 | Service Catalog | Configure catalog categorization for AI and reporting | UAT-REQ-01, UAT-REQ-03 | End-to-end UAT
CONN-SCR-007 | Service Catalog | Define the catalog post-launch governance model | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-SCR-008 | Service Catalog | Define catalog performance measurement (30/60/90) | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-KM-001 | Knowledge | Configure knowledge bases and access model | UAT-EX-01, UAT-KM-01 | End-to-end UAT
CONN-KM-002 | Knowledge | Configure the article lifecycle workflow | UAT-KM-01 | End-to-end UAT
CONN-KM-003 | Knowledge | Define knowledge ownership and authorship | UAT-KM-01 | End-to-end UAT
CONN-KM-004 | Knowledge | Activate article templates | UAT-KM-01 | End-to-end UAT
CONN-KM-005 | Knowledge | Configure article feedback capture | UAT-KM-01 | End-to-end UAT
CONN-KM-006 | Knowledge | Integrate Knowledge with Virtual Agent and Employee Center search | UAT-INC-01, UAT-EX-01, UAT-KM-01 | End-to-end UAT
CONN-KM-007 | Knowledge | Define knowledge governance KPIs and review | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-KM-008 | Knowledge | Plan and execute initial knowledge content seeding | UAT-EX-01, UAT-KM-01 | End-to-end UAT
CONN-EC-001 | Employee Center | Configure Employee Center topic categories and owners | UAT-INC-01, UAT-EX-01 | End-to-end UAT
CONN-EC-002 | Employee Center | Apply Connection branding via the OOTB theme engine | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-EC-003 | Employee Center | Curate the home page and promoted items | UAT-REQ-01, UAT-EX-01 | End-to-end UAT
CONN-EC-004 | Employee Center | Configure Employee Center search | UAT-INC-01, UAT-EX-01 | End-to-end UAT
CONN-EC-005 | Employee Center | Surface knowledge in Employee Center | UAT-INC-01, UAT-EX-01 | End-to-end UAT
CONN-EC-006 | Employee Center | Define Employee Center migration from the existing portal | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-EC-007 | Employee Center | Integrate Virtual Agent into Employee Center | UAT-EX-01, UAT-EX-02 | End-to-end UAT
CONN-EC-008 | Employee Center | Define Employee Center adoption measurement | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-VA-001 | Virtual Agent | Activate the 5 baseline Virtual Agent topics | UAT-REQ-02, UAT-EX-01 | End-to-end UAT
CONN-VA-002 | Virtual Agent | Configure NLU vs menu-driven matching | UAT-EX-01 | End-to-end UAT
CONN-VA-003 | Virtual Agent | Configure VA live-agent escalation | UAT-EX-02 | End-to-end UAT
CONN-VA-004 | Virtual Agent | Activate VA channels for go-live | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-VA-005 | Virtual Agent | Configure VA authentication | UAT-EX-01, UAT-EX-02 | End-to-end UAT
CONN-VA-006 | Virtual Agent | Integrate VA with the Service Catalog | UAT-REQ-02 | End-to-end UAT
CONN-VA-007 | Virtual Agent | Document Now Assist enhancement for VA (later-phase) | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-VA-008 | Virtual Agent | Define VA performance measurement and governance | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PI-001 | Predictive Intelligence | Select and activate the PI use cases | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PI-002 | Predictive Intelligence | Assess training data quality and volume | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PI-003 | Predictive Intelligence | Set PI confidence thresholds | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PI-004 | Predictive Intelligence | Configure similar-incident surfacing | UAT-PRB-01 | End-to-end UAT
CONN-PI-005 | Predictive Intelligence | Decide and configure incident clustering | UAT-PRB-01 | End-to-end UAT
CONN-PI-006 | Predictive Intelligence | Define PI model governance | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-HAM-001 | HAM | Configure asset classes and models for go-live | UAT-HAM-01 | End-to-end UAT
CONN-HAM-002 | HAM | Configure asset lifecycle states and transitions | UAT-HAM-01 | End-to-end UAT
CONN-HAM-003 | HAM | Configure stockrooms | UAT-HAM-01 | End-to-end UAT
CONN-HAM-004 | HAM | Activate the agreed IMAC workflows | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-HAM-005 | HAM | Configure the asset intake process | UAT-HAM-01 | End-to-end UAT
CONN-HAM-006 | HAM | Configure asset retirement and disposal | UAT-HAM-01 | End-to-end UAT
CONN-HAM-007 | HAM | Define the asset ownership model | UAT-HAM-01 | End-to-end UAT
CONN-HAM-008 | HAM | Link HAM assets to CMDB CIs | UAT-HAM-01 | End-to-end UAT
CONN-PA-001 | Performance Analytics | Activate the baseline OOTB indicators | UAT-INC-01, UAT-PA-01 | End-to-end UAT
CONN-PA-002 | Performance Analytics | Configure breakdown dimensions | UAT-PA-01 | End-to-end UAT
CONN-PA-003 | Performance Analytics | Build the agreed scorecards | UAT-PA-01 | End-to-end UAT
CONN-PA-004 | Performance Analytics | Set indicator thresholds (green/yellow/red) | UAT-PA-01 | End-to-end UAT
CONN-PA-005 | Performance Analytics | Configure the data collection cadence | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PA-006 | Performance Analytics | Publish dashboards with the right access | UAT-PA-01 | End-to-end UAT
CONN-PA-007 | Performance Analytics | Decide trending and forecasting activation | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-PA-008 | Performance Analytics | Migrate or retire Classic Reports | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-INT-001 | Integrations | Configure Active Directory / Entra ID user sync | UAT-IAM-01 | End-to-end UAT
CONN-INT-002 | Integrations | Configure SSO (SAML 2.0 / OIDC) | UAT-IAM-01 | End-to-end UAT
CONN-INT-003 | Integrations | Configure the SCCM / MECM Service Graph Connector | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-INT-004 | Integrations | Configure the Microsoft Intune connector | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-INT-005 | Integrations | Map AD groups to ServiceNow groups and roles | UAT-IAM-01 | End-to-end UAT
CONN-INT-006 | Integrations | Configure email integration | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-INT-007 | Integrations | Configure integration health monitoring | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-INT-008 | Integrations | Confirm certificate and security requirements | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-SGC-001 | Service Graph Connectors | Activate the in-scope Service Graph Connectors | UAT-CMDB-01 | End-to-end UAT
CONN-SGC-002 | Service Graph Connectors | Set the source of record per CI class across connectors | UAT-CMDB-01, UAT-CMDB-02 | End-to-end UAT
CONN-SGC-003 | Service Graph Connectors | Configure connector sync frequency | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-SGC-004 | Service Graph Connectors | Map source attributes to ServiceNow CI fields | UAT-CMDB-01 | End-to-end UAT
CONN-SGC-005 | Service Graph Connectors | Configure Content Library normalization | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-SGC-006 | Service Graph Connectors | Define the deduplication strategy across connectors | UAT-CMDB-01 | End-to-end UAT
CONN-SGC-007 | Service Graph Connectors | Configure connector health monitoring and escalation | Sprint story-test only (acceptance criteria) | Sprint story-test only
CONN-SGC-008 | Service Graph Connectors | Validate the expanded CMDB before sprint close | UAT-CMDB-02 | End-to-end UAT
CONN-CTI-001 | Vonage CTI & Interactions | Install and configure the OOTB OpenFrame softphone | UAT-INC-02 | End-to-end UAT
CONN-CTI-002 | Vonage CTI & Interactions | Map agents to Vonage extensions | UAT-INC-02 | End-to-end UAT
CONN-CTI-003 | Vonage CTI & Interactions | Configure inbound screen-pop and caller matching | UAT-INC-02 | End-to-end UAT
CONN-CTI-004 | Vonage CTI & Interactions | Configure Interaction to Incident/Request creation | UAT-INC-02 | End-to-end UAT
CONN-CTI-005 | Vonage CTI & Interactions | Map Vonage queues to assignment groups | UAT-INC-02 | End-to-end UAT
CONN-CTI-006 | Vonage CTI & Interactions | Port the legacy Vonage configuration | Sprint story-test only (acceptance criteria) | Sprint story-test only
SUMMARY
Total stories | 141
Covered by end-to-end UAT | 90
Sprint story-test only | 51

## Defect Log
UAT DEFECT LOG
Log every FAIL here. ECS triages and resolves; testers re-test.
Defect ID | Script ID | Story ID | Severity | Summary | Steps to Reproduce | Expected | Actual | Status | Owner | Resolution