## README - Import Guide
CONNECTION - USER STORY BACKLOG (ServiceNow Agile import)
Default Phase 1 user stories for the configurable decisions defined by the SOW. NOT exhaustive per process - one story per contract-configurable decision.
What this is
Purpose | Seed backlog of default configuration user stories for Connection Phase 1. Each story maps to a contract-configurable decision from the workshop decks / SOW. Teams refine estimates and add detail per engagement.
Tabs | Epics (import first) ¦ Application User Stories ¦ Integration User Stories ¦ Definition of Done ¦ this README.
Acceptance criteria | Given/When/Then per story. The shared Definition of Done lives on its own tab and applies to every story.
How to import to ServiceNow Agile (rm_story / rm_epic)
1. Import EPICS first: Agile Development > Epics, or System Import Sets > Load Data from the 'Epics' tab into target table rm_epic. Coalesce on Number (short_description).
2. Import STORIES: Load the 'Application User Stories' and 'Integration User Stories' tabs into target table rm_story via Import Set + Transform Map.
3. Map columns to fields (see mapping below). Set Epic by display name/number; Sprint is optional until sprints exist.
4. Set State = Draft on import; refine Story Points and Assignment Group in ServiceNow.
5. Validate a sample, then commit. Re-run is safe if you coalesce on Number.
Field mapping (workbook column -> rm_story field)
number | Number (or u_external_id)
epic | Epic [reference rm_epic]
short_description | Short description
description | Description
acceptance_criteria | Acceptance criteria
story_points | Story points
priority | Priority
sprint | Sprint [reference rm_sprint]
assignment (role) | Assignment group / Assigned to
state | State
notes / OOTB reference | Work notes / comments
Conventions
Story points | Fibonacci (1,2,3,5,8). Estimates are starting points - refine in sprint planning.
Priority | 1 - Critical / 2 - High / 3 - Moderate / 4 - Low.
State | Draft on import; progress in ServiceNow (Ready > Work in progress > Complete).
Numbering | CONN-<MODULE>-NNN (local reference; map to Number or an external-id field).

## Epics
CONNECTION - EPICS (import first -> rm_epic)
One epic per in-scope module. Stories reference these.
number | short_description | description | state
CONN-EPIC-PF | Platform Foundation - Phase 1 Configuration | Phase 1 OOTB configuration of Platform Foundation for Connection - 8 default stories covering the contract-configurable decisions. Sprint 1 (primary). | Draft
CONN-EPIC-CSDM | CSDM - Phase 1 Configuration | Phase 1 OOTB configuration of CSDM for Connection - 8 default stories covering the contract-configurable decisions. Sprint 1 (primary). | Draft
CONN-EPIC-CMDB | CMDB - Phase 1 Configuration | Phase 1 OOTB configuration of CMDB for Connection - 8 default stories covering the contract-configurable decisions. Sprint 2 (primary). | Draft
CONN-EPIC-DISC | Discovery - Phase 1 Configuration | Phase 1 OOTB configuration of Discovery for Connection - 8 default stories covering the contract-configurable decisions. Sprint 2 (primary). | Draft
CONN-EPIC-INC | Incident - Phase 1 Configuration | Phase 1 OOTB configuration of Incident for Connection - 9 default stories covering the contract-configurable decisions. Sprint 3 (primary). | Draft
CONN-EPIC-MIM | Major Incident - Phase 1 Configuration | Phase 1 OOTB configuration of Major Incident for Connection - 7 default stories covering the contract-configurable decisions. Sprint 3 (primary). | Draft
CONN-EPIC-PRB | Problem - Phase 1 Configuration | Phase 1 OOTB configuration of Problem for Connection - 8 default stories covering the contract-configurable decisions. Sprint 3 (primary). | Draft
CONN-EPIC-CHG | Change - Phase 1 Configuration | Phase 1 OOTB configuration of Change for Connection - 9 default stories covering the contract-configurable decisions. Sprint 4 (primary). | Draft
CONN-EPIC-SCR | Service Catalog - Phase 1 Configuration | Phase 1 OOTB configuration of Service Catalog for Connection - 8 default stories covering the contract-configurable decisions. Sprint 4 (primary). | Draft
CONN-EPIC-KM | Knowledge - Phase 1 Configuration | Phase 1 OOTB configuration of Knowledge for Connection - 8 default stories covering the contract-configurable decisions. Sprint 5 (primary). | Draft
CONN-EPIC-EC | Employee Center - Phase 1 Configuration | Phase 1 OOTB configuration of Employee Center for Connection - 8 default stories covering the contract-configurable decisions. Sprint 5 (primary). | Draft
CONN-EPIC-VA | Virtual Agent - Phase 1 Configuration | Phase 1 OOTB configuration of Virtual Agent for Connection - 8 default stories covering the contract-configurable decisions. Sprint 5 (primary). | Draft
CONN-EPIC-PI | Predictive Intelligence - Phase 1 Configuration | Phase 1 OOTB configuration of Predictive Intelligence for Connection - 6 default stories covering the contract-configurable decisions. Sprint 5 (primary). | Draft
CONN-EPIC-HAM | HAM - Phase 1 Configuration | Phase 1 OOTB configuration of HAM for Connection - 8 default stories covering the contract-configurable decisions. Sprint 6 (primary). | Draft
CONN-EPIC-PA | Performance Analytics - Phase 1 Configuration | Phase 1 OOTB configuration of Performance Analytics for Connection - 8 default stories covering the contract-configurable decisions. Sprint 6 (primary). | Draft
CONN-EPIC-INT | Integrations - Phase 1 Configuration | Phase 1 OOTB configuration of Integrations for Connection - 8 default stories covering the contract-configurable decisions. Sprint 3 (primary). | Draft
CONN-EPIC-SGC | Service Graph Connectors - Phase 1 Configuration | Phase 1 OOTB configuration of Service Graph Connectors for Connection - 8 default stories covering the contract-configurable decisions. Sprint 4 (primary). | Draft
CONN-EPIC-CTI | Vonage CTI & Interactions - Phase 1 Configuration | Phase 1 OOTB configuration of Vonage CTI & Interactions for Connection - 6 default stories covering the contract-configurable decisions. Sprint 4 (primary). | Draft

## Application User Stories
CONNECTION - APPLICATION USER STORIES (SN Agile / rm_story import)
Default Phase 1 configuration stories for the contract-configurable decisions. Given/When/Then acceptance criteria; shared Definition of Done on its own tab. See README for import steps.
number | epic | short_description | description | acceptance_criteria | definition_of_done | story_points | priority | sprint | assignment (role) | state | notes / OOTB reference
CONN-PF-001 | Platform Foundation - Phase 1 Configuration | Configure sub-production and production instances | As a platform administrator, I want sub-production and production instances stood up with a naming standard and test-data approach, so that environments are governed, consistent, and ready for build and a clean cutover. | AC1: Given the dedicated instances are provisioned, When naming standards are applied, Then sub-prod and prod follow the agreed naming convention with ECS admin access. AC2: Given the move off domain separation, When the instances are configured, Then no domain-separation artifacts are carried into the new instances. AC3: Given a test-data approach is agreed, When build begins, Then sub-prod holds representative Connection data (not Lorem ipsum) for demos. | See 'Definition of Done' tab | 5 | 1 - Critical | Sprint 1 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PF-002 | Platform Foundation - Phase 1 Configuration | Configure AD/LDAP user import and ongoing sync | As a platform administrator, I want users imported from Active Directory via an OOTB scheduled import with ongoing sync, so that user records stay current without manual maintenance. | AC1: Given AD/LDAP connectivity, When the OOTB scheduled import runs, Then in-scope users are created/updated with required attributes. AC2: Given the sync schedule, When a user is disabled in AD, Then the ServiceNow record reflects the change on the next run. AC3: Given coalesce rules, When the import runs twice, Then no duplicate user records are created. | See 'Definition of Done' tab | 3 | 1 - Critical | Sprint 1 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PF-003 | Platform Foundation - Phase 1 Configuration | Load the OOTB location hierarchy | As a platform administrator, I want the location hierarchy (site, building, floor) loaded using OOTB structures, so that assignment, routing, and asset placement resolve to correct locations. | AC1: Given the location source data, When loaded, Then the site/building/floor hierarchy matches the agreed structure. AC2: Given a user with a location, When records are created, Then the location reference resolves correctly. AC3: Given OOTB location tables, When loaded, Then no custom location tables are introduced. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 1 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PF-004 | Platform Foundation - Phase 1 Configuration | Configure groups and roles at go-live | As a platform administrator, I want OOTB roles and assignment groups configured with least-privilege membership, so that day-one access is correct and upgrade-safe. | AC1: Given the agreed group/role model, When configured, Then OOTB roles (itil, admin, catalog_admin, asset, approver_user) are assigned via group membership. AC2: Given least privilege, When a member is added, Then they receive only the roles their group grants. AC3: Given role review, When audited, Then no custom roles exist without a documented business need. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 1 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PF-005 | Platform Foundation - Phase 1 Configuration | Configure business hour schedules and holiday calendars | As a platform administrator, I want OOTB business-hour schedules and holiday calendars per in-scope process area, so that SLAs and escalations compute against correct working time. | AC1: Given the agreed schedules, When configured, Then each process area references the correct OOTB schedule. AC2: Given a holiday, When an SLA spans it, Then elapsed time excludes non-working hours. AC3: Given OOTB schedules, When built, Then no scripted time calculations are introduced. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 1 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PF-006 | Platform Foundation - Phase 1 Configuration | Configure outbound and inbound email | As a platform administrator, I want OOTB outbound SMTP relay and inbound mailboxes/actions configured, so that notifications send and inbound email creates/updates records. | AC1: Given SMTP relay details, When configured, Then test notifications deliver to recipients. AC2: Given an inbound mailbox, When an email arrives, Then the OOTB inbound action creates/updates the correct record. AC3: Given email config, When reviewed, Then no custom mail scripts beyond OOTB inbound actions are used. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 1 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PF-007 | Platform Foundation - Phase 1 Configuration | Deploy and configure the MID Server(s) | As a platform administrator, I want MID Server(s) deployed with credentials and network paths verified, so that Discovery and integrations can reach in-scope targets. | AC1: Given MID Server host(s), When installed, Then they show Up and validated in ServiceNow. AC2: Given credentials in the vault, When a test probe runs, Then it connects without hard-coded credentials. AC3: Given placement, When reviewed, Then MID count/placement covers all in-scope subnets and integrations. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 1 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PF-008 | Platform Foundation - Phase 1 Configuration | Establish platform health baseline KPIs | As a platform administrator, I want baseline platform-health KPIs configured and tracked, so that platform health is visible from go-live. | AC1: Given the agreed KPIs, When configured, Then a baseline health view is available to the platform team. AC2: Given OOTB instance scan / health, When run, Then results are captured as the Phase 1 baseline. AC3: Given the baseline, When Hypercare begins, Then health is trended against it. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 1 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CSDM-001 | CSDM - Phase 1 Configuration | Set CSDM adoption scope to the foundation tier for Phase 1 | As a solution architect, I want CSDM adoption scoped to the foundation/design tiers appropriate for Phase 1, so that we build a healthy, right-sized service model without over-engineering. | AC1: Given the CSDM workshop decision, When scope is set, Then Foundation and Design domains are in scope and deeper tiers are deferred with rationale. AC2: Given CSDM 5.0, When applied, Then OOTB CSDM tables are used with no custom service tables. AC3: Given the scope, When documented, Then it is recorded in the Architecture & CSDM Alignment document. | See 'Definition of Done' tab | 5 | 1 - Critical | Sprint 1 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CSDM-002 | CSDM - Phase 1 Configuration | Load the Business Application inventory | As a solution architect, I want the Business Application inventory loaded into OOTB CSDM tables, so that services have an accurate top-level anchor for mapping. | AC1: Given the agreed inventory, When loaded, Then Business Application records exist with owners. AC2: Given coalesce keys, When loaded twice, Then no duplicates are created. AC3: Given OOTB tables, When loaded, Then cmdb_ci_business_app is used without extension. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 1 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CSDM-003 | CSDM - Phase 1 Configuration | Structure the service taxonomy mapped to OOTB CSDM tables | As a solution architect, I want a service taxonomy (Business/Application/Technical service) mapped to OOTB CSDM tables, so that services are classified consistently for maps and reporting. | AC1: Given the taxonomy decision, When configured, Then the hierarchy maps Business Application to Application Service to Technical Service via OOTB tables. AC2: Given a sample service, When classified, Then it resolves cleanly through the hierarchy. AC3: Given the taxonomy, When reviewed, Then it requires no custom classification fields. | See 'Definition of Done' tab | 5 | 2 - High | Sprint 1 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CSDM-004 | CSDM - Phase 1 Configuration | Assign Application Service ownership | As a solution architect, I want Application Service owners, managers, and support groups assigned via OOTB fields, so that accountability for each service is explicit and operational. | AC1: Given the ownership model, When assigned, Then each in-scope Application Service has owner, manager, and support group populated. AC2: Given an unowned service, When validated, Then it is flagged before sign-off. AC3: Given OOTB service fields, When used, Then no custom ownership fields are added. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 1 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CSDM-005 | CSDM - Phase 1 Configuration | Model service relationships to the agreed depth | As a solution architect, I want service relationships modeled using OOTB relationship types to the agreed depth, so that service maps are accurate without unbounded sprawl. | AC1: Given the depth decision, When relationships are built, Then OOTB relationship types are used to the agreed number of tiers. AC2: Given a sample service, When mapped, Then upstream/downstream dependencies render correctly. AC3: Given the model, When reviewed, Then no custom relationship types are introduced. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 1 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CSDM-006 | CSDM - Phase 1 Configuration | Align CSDM with CMDB to create accurate service maps | As a solution architect, I want CSDM service definitions aligned to CMDB CIs to produce accurate service maps, so that change impact and incident context are trustworthy. | AC1: Given CMDB CIs, When linked to services, Then service maps render with correct CI membership. AC2: Given a CI change, When impact is assessed, Then dependent services are identified. AC3: Given alignment, When validated, Then no orphaned services or CIs remain in scope. | See 'Definition of Done' tab | 5 | 2 - High | Sprint 1 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CSDM-007 | CSDM - Phase 1 Configuration | Link CSDM services to the Service Catalog | As a solution architect, I want CSDM services connected to catalog items where applicable, so that requests carry service context for routing and reporting. | AC1: Given in-scope catalog items, When associated to services, Then the service reference is populated. AC2: Given a request, When created, Then the related service is visible. AC3: Given the link, When reviewed, Then it uses OOTB service references. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 1 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CSDM-008 | CSDM - Phase 1 Configuration | Enable CSDM service maps for Change impact assessment | As a solution architect, I want CSDM service maps usable in Change for impact assessment, so that CAB sees affected services and CIs for each change. | AC1: Given a change tied to a CI, When assessed, Then affected services display from the service map. AC2: Given a high-impact service, When a change targets it, Then risk reflects the impact. AC3: Given the integration, When validated, Then it uses OOTB change-CMDB relationships. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 1 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CMDB-001 | CMDB - Phase 1 Configuration | Define in-scope CI classes for go-live | As a CMDB manager, I want the in-scope CI classes defined in OOTB CMDB Studio with deferred classes documented, so that the CMDB is populated to a useful, bounded scope at go-live. | AC1: Given the class decision, When configured, Then in-scope CI classes exist with mandatory attributes defined in CMDB Studio. AC2: Given deferred classes, When documented, Then they are recorded with rationale for a later phase. AC3: Given OOTB classes, When used, Then no custom CI tables are created without Council approval. | See 'Definition of Done' tab | 3 | 1 - Critical | Sprint 2 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CMDB-002 | CMDB - Phase 1 Configuration | Set the CMDB scope boundary | As a CMDB manager, I want the CMDB scope boundary defined for systems and networks, so that Discovery and connectors populate only in-scope CIs. | AC1: Given the boundary decision, When applied, Then in-scope systems/networks are documented and out-of-scope excluded. AC2: Given a discovered out-of-scope CI, When ingested, Then it is filtered or flagged per the boundary. AC3: Given the boundary, When reviewed, Then it aligns with the Architecture & CSDM Alignment document. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 2 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CMDB-003 | CMDB - Phase 1 Configuration | Configure CI relationship types and maintenance | As a CMDB manager, I want OOTB CI relationship types configured with a maintenance approach, so that service maps and impact analysis stay accurate over time. | AC1: Given the relationship decision, When configured, Then OOTB types (Runs on, Depends on, Hosted on) are used. AC2: Given automated sources, When data loads, Then relationships are maintained by Discovery/SGC, not manual edits. AC3: Given the model, When reviewed, Then no custom relationship types exist without business need. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 2 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CMDB-004 | CMDB - Phase 1 Configuration | Set CMDB health targets | As a CMDB manager, I want CMDB Health thresholds set for completeness, compliance, and correctness, so that CMDB quality is measurable and sufficient for AI ROI and risk scoring. | AC1: Given the target decision, When configured, Then OOTB CMDB Health metrics use the agreed thresholds. AC2: Given the first data load, When scored, Then a health baseline is captured. AC3: Given thresholds, When breached, Then the dashboard surfaces the gap. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 2 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CMDB-005 | CMDB - Phase 1 Configuration | Define the source of record per CI class | As a CMDB manager, I want an authoritative source of record set per CI class (Discovery, connector, or manual), so that CI data conflicts resolve predictably. | AC1: Given the source decision, When configured, Then IRE rules name the authoritative source per class. AC2: Given overlapping sources, When data loads, Then the authoritative source wins per the rules. AC3: Given the mapping, When documented, Then it is recorded for operations. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 2 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CMDB-006 | CMDB - Phase 1 Configuration | Configure CI lifecycle states and retired-CI management | As a CMDB manager, I want OOTB CI lifecycle states configured with a retired-CI process, so that stale and retired CIs are managed, not deleted ad hoc. | AC1: Given the lifecycle decision, When configured, Then OOTB states (Installed, In Maintenance, Retired) are used. AC2: Given a stale CI, When the policy runs, Then it is flagged inactive per the agreed window (deletion deferred to manual review). AC3: Given states, When reviewed, Then no custom lifecycle scripting is introduced. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 2 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CMDB-007 | CMDB - Phase 1 Configuration | Assign CI ownership | As a CMDB manager, I want CI ownership assigned via OOTB CI record fields with an operational definition, so that accountability for CIs is clear. | AC1: Given the ownership model, When applied, Then in-scope CIs have owner/stewardship populated. AC2: Given an unowned CI, When validated, Then it is flagged before sign-off. AC3: Given OOTB fields, When used, Then no custom ownership fields are added. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 2 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CMDB-008 | CMDB - Phase 1 Configuration | Integrate CMDB with Change and Incident | As a CMDB manager, I want CMDB CI context available to Change and Incident, so that change risk scoring and incident context use CI data. | AC1: Given a change tied to a CI, When created, Then affected CIs/services display. AC2: Given an incident on a CI, When created, Then related CI context is visible. AC3: Given the integration, When validated, Then it uses OOTB CMDB relationships. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 2 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-DISC-001 | Discovery - Phase 1 Configuration | Plan MID Server count and placement for Discovery | As a Discovery engineer, I want MID Servers sized and placed for Discovery coverage, so that all in-scope subnets are reachable for Discovery. | AC1: Given the subnet inventory, When MID placement is planned, Then every in-scope subnet has a reachable MID Server. AC2: Given a MID Server, When validated, Then it passes connectivity tests to sample targets. AC3: Given existing MID infrastructure, When reused, Then it is leveraged where it meets best practice. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 2 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-DISC-002 | Discovery - Phase 1 Configuration | Define Discovery IP ranges and subnets | As a Discovery engineer, I want Discovery IP ranges and subnets configured in OOTB Discovery Schedules, so that Discovery scans the right scope and nothing out of bounds. | AC1: Given the in-scope ranges, When configured, Then Discovery Schedules target only those ranges. AC2: Given out-of-scope ranges (lab/test), When excluded, Then they are not scanned. AC3: Given schedules, When reviewed, Then they use OOTB schedule configuration. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 2 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-DISC-003 | Discovery - Phase 1 Configuration | Activate OOTB Discovery patterns for in-scope classes | As a Discovery engineer, I want OOTB Discovery patterns activated for in-scope CI classes, so that CIs are discovered without custom patterns. | AC1: Given in-scope classes, When patterns are activated, Then OOTB patterns (Windows, Linux, VMware, network) populate them. AC2: Given a custom pattern need, When identified, Then it routes to the Customization Council. AC3: Given a test run, When executed, Then sample CIs populate with expected attributes. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 2 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-DISC-004 | Discovery - Phase 1 Configuration | Configure Discovery credentials in the vault | As a Discovery engineer, I want Discovery credentials stored in the OOTB Credential Vault, so that Discovery authenticates securely without hard-coded secrets. | AC1: Given credential records, When stored, Then they reside in the OOTB Credential store. AC2: Given a probe, When it runs, Then it uses vaulted credentials only. AC3: Given access, When reviewed, Then least-privilege service accounts are used. | See 'Definition of Done' tab | 2 | 2 - High | Sprint 2 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-DISC-005 | Discovery - Phase 1 Configuration | Set the Discovery schedule and maintenance windows | As a Discovery engineer, I want Discovery schedule frequency, timing, and maintenance-window exclusions configured, so that Discovery runs predictably without impacting operations. | AC1: Given the cadence decision, When configured, Then schedules run at the agreed frequency/timing. AC2: Given maintenance windows, When set, Then Discovery excludes them. AC3: Given OOTB scheduling, When used, Then no custom scheduling logic is introduced. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 2 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-DISC-006 | Discovery - Phase 1 Configuration | Configure IRE reconciliation and duplicate handling | As a Discovery engineer, I want IRE identification and reconciliation rules configured to prevent duplicate CIs, so that CMDB stays clean across multiple data sources. | AC1: Given IRE rules, When data loads from multiple sources, Then CIs are matched and reconciled, not duplicated. AC2: Given a potential duplicate, When ingested, Then IRE identifies the existing CI. AC3: Given the rules, When reviewed, Then they use OOTB IRE configuration. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 2 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-DISC-007 | Discovery - Phase 1 Configuration | Decide and configure cloud Discovery (if in scope) | As a Discovery engineer, I want cloud Discovery activated for agreed providers (or formally deferred), so that cloud CIs are captured if required for Phase 1. | AC1: Given the cloud decision, When made, Then cloud Discovery is activated for named providers or deferred with rationale. AC2: Given activation, When configured, Then OOTB cloud Discovery uses service-account credentials. AC3: Given a test run, When executed, Then sample cloud CIs populate. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 2 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-DISC-008 | Discovery - Phase 1 Configuration | Verify the CMDB after the first Discovery run | As a Discovery engineer, I want a CMDB verification process executed after the first Discovery run, so that Discovery results are trusted before downstream use. | AC1: Given the first full run, When complete, Then a sample of CIs is validated against source-of-truth. AC2: Given verification, When gaps are found, Then they are logged and remediated before sign-off. AC3: Given results, When validated, Then CMDB Health meets the agreed baseline. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 2 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INC-001 | Incident - Phase 1 Configuration | Configure incident priority via OOTB Impact x Urgency | As a service desk manager, I want incident priority driven by the OOTB 5-level Impact x Urgency matrix, so that priority is consistent and requires no scripting. | AC1: Given the priority decision, When configured, Then the OOTB Impact x Urgency matrix yields the 5 priority levels. AC2: Given an incident, When impact and urgency are set, Then priority calculates automatically. AC3: Given the matrix, When reviewed, Then no custom priority script is used. | See 'Definition of Done' tab | 3 | 1 - Critical | Sprint 3 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INC-002 | Incident - Phase 1 Configuration | Configure incident categories and subcategories | As a service desk manager, I want incident category/subcategory taxonomy configured, so that incidents are classified for routing and reporting. | AC1: Given the taxonomy decision, When configured, Then agreed categories/subcategories exist as OOTB choices. AC2: Given a new incident, When categorized, Then the subcategory list filters to the category. AC3: Given the taxonomy, When reviewed, Then it stays a routing taxonomy (service context lives on the CI). | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INC-003 | Incident - Phase 1 Configuration | Adopt the OOTB incident lifecycle states | As a service desk manager, I want the OOTB incident lifecycle states adopted, so that the process is upgrade-safe with no custom states. | AC1: Given the lifecycle decision, When configured, Then OOTB states are used with On Hold reasons. AC2: Given a custom-state request, When raised, Then it routes to the Customization Council. AC3: Given the lifecycle, When validated, Then state transitions follow OOTB rules. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 3 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INC-004 | Incident - Phase 1 Configuration | Activate in-scope incident intake channels | As a service desk manager, I want the agreed intake channels activated (Employee Center, email, Virtual Agent, phone/CTI), so that users can raise incidents through approved channels at go-live. | AC1: Given the channel decision, When activated, Then each agreed channel creates incidents correctly. AC2: Given a phone call, When handled, Then an Interaction can spawn an incident (see CTI stories). AC3: Given channels, When reviewed, Then they use OOTB intake. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 3 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INC-005 | Incident - Phase 1 Configuration | Configure incident SLAs by priority | As a service desk manager, I want response and resolution SLA targets configured by priority with schedules, so that commitments are tracked and breaches are visible. | AC1: Given the SLA decision, When configured, Then OOTB SLA definitions set response/resolution targets per priority. AC2: Given a business schedule, When applied, Then SLA elapsed time respects working hours. AC3: Given an at-risk SLA, When approaching breach, Then it surfaces on the workspace/dashboards. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 3 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INC-006 | Incident - Phase 1 Configuration | Configure incident routing/assignment | As a service desk manager, I want incidents routed to the correct support group via OOTB assignment rules, so that tickets reach the right team without manual triage. | AC1: Given assignment rules, When an incident is categorized, Then it routes to the correct group. AC2: Given an unmatched incident, When created, Then it lands in a defined catch-all group. AC3: Given rules, When reviewed, Then they use OOTB assignment (Decision Tables/conditions), not custom code. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 3 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INC-007 | Incident - Phase 1 Configuration | Configure Major Incident escalation from Incident | As a service desk manager, I want the criteria and action to escalate an incident to a Major Incident, so that major incidents are declared consistently. | AC1: Given the escalation decision, When configured, Then qualifying incidents can be promoted to Major Incident. AC2: Given a P1 meeting criteria, When promoted, Then the MIM process engages (see MIM stories). AC3: Given promotion, When validated, Then it uses the OOTB MIM trigger. | See 'Definition of Done' tab | 2 | 2 - High | Sprint 3 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INC-008 | Incident - Phase 1 Configuration | Configure incident notifications | As a service desk manager, I want notifications configured across the incident lifecycle, so that stakeholders are informed at the right moments. | AC1: Given the notification decision, When configured, Then OOTB notifications fire on the agreed events. AC2: Given an assignment, When made, Then the assignee is notified. AC3: Given notifications, When reviewed, Then OOTB notification records are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INC-009 | Incident - Phase 1 Configuration | Connect Predictive Intelligence and Knowledge to Incident | As a service desk manager, I want PI categorization/assignment and KB suggestions surfaced in Incident, so that agents resolve faster with AI and knowledge support. | AC1: Given PI enabled, When an incident is created, Then category/assignment predictions surface for agent review. AC2: Given KB integration, When working an incident, Then relevant articles are suggested. AC3: Given the integration, When validated, Then it uses OOTB PI and KB features (see PI/KM stories). | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 3 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-MIM-001 | Major Incident - Phase 1 Configuration | Define major incident criteria | As a major incident coordinator, I want major-incident criteria defined and frozen before plugin activation, so that major incidents are declared consistently without MIM fatigue. | AC1: Given the criteria decision, When configured, Then OOTB MIM criteria (priority/impact/EM/manual) reflect the agreement. AC2: Given an incident meeting criteria, When evaluated, Then it qualifies for major-incident declaration. AC3: Given the criteria, When frozen, Then changes route to governance. | See 'Definition of Done' tab | 3 | 1 - Critical | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-MIM-002 | Major Incident - Phase 1 Configuration | Configure MIM team roles | As a major incident coordinator, I want OOTB MIM roles configured (coordinator, technical lead, comms lead, exec sponsor), so that accountability in a major incident is clear. | AC1: Given the role decision, When configured, Then OOTB MIM roles exist with named (or draft) holders. AC2: Given a major incident, When declared, Then the coordinator owns the record. AC3: Given roles, When reviewed, Then OOTB role structure is used. | See 'Definition of Done' tab | 2 | 2 - High | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-MIM-003 | Major Incident - Phase 1 Configuration | Configure stakeholder communication templates | As a communications lead, I want stakeholder communication templates configured for major incidents, so that comms are timely, consistent, and approved. | AC1: Given the comms decision, When configured, Then templates exist per communication type (subject/body/audience). AC2: Given a major incident, When comms are sent, Then a template populates the message. AC3: Given templates, When reviewed, Then OOTB notification/template features are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-MIM-004 | Major Incident - Phase 1 Configuration | Configure major-incident SLAs | As a major incident coordinator, I want SLAs specific to major incidents configured, so that MIM response/restore times are tracked distinctly. | AC1: Given the MIM SLA decision, When configured, Then OOTB SLAs track major-incident response/restore. AC2: Given a major incident, When active, Then the MIM SLA clock runs. AC3: Given SLAs, When validated, Then they use OOTB SLA definitions. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-MIM-005 | Major Incident - Phase 1 Configuration | Configure the Post-Incident Review (PIR) process | As a major incident coordinator, I want the OOTB PIR workflow configured, so that every major incident drives learning and follow-up. | AC1: Given the PIR decision, When configured, Then a PIR is generated/required after a major incident. AC2: Given a closed major incident, When PIR runs, Then actions are captured and tracked. AC3: Given PIR, When reviewed, Then it uses OOTB PIR capability. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-MIM-006 | Major Incident - Phase 1 Configuration | Configure Event Management trigger to MIM (alignment note) | As a major incident coordinator, I want the EM-to-MIM promotion threshold aligned (EM is later-phase), so that if/when EM is enabled, promotion is consistent. | AC1: Given EM is out of Phase 1 scope, When documented, Then the EM-to-MIM threshold is recorded for a later phase. AC2: Given manual/priority criteria, When used now, Then MIM does not depend on EM in Phase 1. AC3: Given alignment, When validated, Then no EM customization is built in Phase 1. | See 'Definition of Done' tab | 1 | 4 - Low | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-MIM-007 | Major Incident - Phase 1 Configuration | Decide war-room tooling integration (Teams/Zoom/Slack) | As a major incident coordinator, I want a decision on war-room tooling integration for major incidents, so that collaboration during a major incident is effective. | AC1: Given the tooling decision, When made, Then either an OOTB collaboration integration is used or it is deferred with rationale. AC2: Given a custom integration request, When raised, Then it routes to the Customization Council. AC3: Given the decision, When documented, Then it is recorded in the Triage Log if a deviation. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PRB-001 | Problem - Phase 1 Configuration | Adopt the OOTB problem lifecycle | As a problem manager, I want the OOTB problem lifecycle states adopted, so that the process is upgrade-safe with no custom states. | AC1: Given the lifecycle decision, When configured, Then OOTB problem states and On Hold reasons are used. AC2: Given a custom-state request, When raised, Then it routes to the Customization Council. AC3: Given the lifecycle, When validated, Then transitions follow OOTB rules. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PRB-002 | Problem - Phase 1 Configuration | Align problem categories to the incident taxonomy | As a problem manager, I want problem categories aligned to the incident taxonomy, so that trends connect cleanly from incident to problem. | AC1: Given the taxonomy decision, When configured, Then problem categories mirror the incident taxonomy. AC2: Given a problem from incidents, When categorized, Then categories are consistent. AC3: Given alignment, When reviewed, Then OOTB category choices are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PRB-003 | Problem - Phase 1 Configuration | Configure the Known Error Database (KEDB) | As a problem manager, I want the KEDB configured so known errors and workarounds are surfaced, so that agents resolve repeat issues faster. | AC1: Given the KEDB decision, When configured, Then known errors/workarounds are captured on problem records. AC2: Given an incident matching a known error, When worked, Then the workaround is discoverable. AC3: Given KEDB, When reviewed, Then OOTB known-error capability is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PRB-004 | Problem - Phase 1 Configuration | Configure problem assignment and Problem Manager role | As a problem manager, I want problem assignment rules and the Problem Manager role configured, so that problems are owned and driven to root cause. | AC1: Given the assignment decision, When configured, Then problems route by category/CI/support group. AC2: Given the Problem Manager role, When assigned, Then ownership is clear. AC3: Given rules, When reviewed, Then OOTB assignment is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PRB-005 | Problem - Phase 1 Configuration | Configure problem SLAs and KPIs | As a problem manager, I want SLA targets and KPIs for problem investigation configured, so that investigation progress is measurable. | AC1: Given the SLA/KPI decision, When configured, Then time-to-root-cause and time-to-resolution are tracked. AC2: Given a problem, When active, Then the relevant SLA runs. AC3: Given KPIs, When reviewed, Then OOTB PA indicators support them. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PRB-006 | Problem - Phase 1 Configuration | Configure problem notifications | As a problem manager, I want notifications configured across the problem lifecycle, so that stakeholders stay informed. | AC1: Given the notification decision, When configured, Then OOTB notifications fire on agreed events. AC2: Given a root cause found, When recorded, Then stakeholders are notified. AC3: Given notifications, When reviewed, Then OOTB records are used. | See 'Definition of Done' tab | 1 | 3 - Moderate | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PRB-007 | Problem - Phase 1 Configuration | Link Problem to Change | As a problem manager, I want problems linked to change requests for permanent fixes, so that fixes are delivered through governed change. | AC1: Given a problem needing a fix, When raised, Then a change can be created/linked from the problem. AC2: Given the linked change, When progressed, Then the problem reflects fix status. AC3: Given the link, When validated, Then OOTB problem-change relationships are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PRB-008 | Problem - Phase 1 Configuration | Connect Predictive Intelligence to Problem | As a problem manager, I want PI similarity/clustering surfaced to support problem identification, so that recurring incident patterns become problems sooner. | AC1: Given PI enabled, When incidents cluster, Then candidate problems are surfaced for review. AC2: Given a cluster, When reviewed, Then a problem can be created from it. AC3: Given the integration, When validated, Then OOTB PI features are used (see PI stories). | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CHG-001 | Change - Phase 1 Configuration | Adopt the 3 OOTB change types | As a change manager, I want the OOTB change types (Normal, Standard, Emergency) adopted, so that change is governed with proven, upgrade-safe types. | AC1: Given the type decision, When configured, Then Normal, Standard, and Emergency are active with their OOTB workflows. AC2: Given a change, When created, Then the type drives the correct approval path. AC3: Given the types, When reviewed, Then no custom change types are introduced. | See 'Definition of Done' tab | 3 | 1 - Critical | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CHG-002 | Change - Phase 1 Configuration | Adopt the OOTB change lifecycle states | As a change manager, I want the OOTB change lifecycle states adopted, so that the process stays upgrade-safe. | AC1: Given the lifecycle decision, When configured, Then OOTB change states are used. AC2: Given a custom-state request, When raised, Then it routes to the Customization Council. AC3: Given the lifecycle, When validated, Then transitions follow OOTB rules. | See 'Definition of Done' tab | 2 | 2 - High | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CHG-003 | Change - Phase 1 Configuration | Configure CI-driven change risk scoring | As a change manager, I want change risk calculated using OOTB risk assessment with thresholds that trigger CAB, so that risk-appropriate changes get the right scrutiny. | AC1: Given the risk decision, When configured, Then the OOTB risk questionnaire/conditions produce a risk score. AC2: Given a CI-tied change, When assessed, Then CMDB context informs the risk. AC3: Given thresholds, When exceeded, Then the change is routed to CAB. | See 'Definition of Done' tab | 5 | 1 - Critical | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CHG-004 | Change - Phase 1 Configuration | Stand up the CAB Workbench | As a change manager, I want the OOTB CAB Workbench configured for the agreed CAB structure, so that CAB reviews are efficient and consistent. | AC1: Given the CAB decision, When configured, Then the CAB Workbench reflects the meeting cadence and membership. AC2: Given non-standard changes, When scheduled, Then they appear on the CAB agenda. AC3: Given the workbench, When validated, Then OOTB CAB capability is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CHG-005 | Change - Phase 1 Configuration | Configure the Standard Change Catalog | As a change manager, I want 2-3 well-defined standard change templates configured with template approvers, so that low-risk repeatable changes are pre-approved and fast. | AC1: Given the standard-change decision, When configured, Then the agreed templates exist in the Standard Change Catalog. AC2: Given a standard change, When raised from a template, Then it follows the pre-approved path. AC3: Given templates, When created, Then template approval is governed. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CHG-006 | Change - Phase 1 Configuration | Configure change approvals and sequence | As a change manager, I want change approval policies and sequence configured, so that the right approvers act in the right order. | AC1: Given the approval decision, When configured, Then OOTB Approval Definitions route by type/risk. AC2: Given a change, When submitted, Then approvals occur in the agreed sequence. AC3: Given approvals, When reviewed, Then OOTB approval engine is used (no custom code). | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CHG-007 | Change - Phase 1 Configuration | Configure change conflict detection and blackout windows | As a change manager, I want OOTB conflict detection and blackout/maintenance windows configured, so that conflicting or risky-timed changes are caught. | AC1: Given the schedule decision, When configured, Then OOTB conflict detection flags overlapping changes on shared CIs. AC2: Given a blackout window, When a change targets it, Then it is flagged. AC3: Given the config, When validated, Then OOTB change schedule features are used. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CHG-008 | Change - Phase 1 Configuration | Configure change notifications | As a change manager, I want notifications configured across the change lifecycle, so that stakeholders are informed at approvals and implementation. | AC1: Given the notification decision, When configured, Then OOTB notifications fire on agreed events. AC2: Given an approval request, When raised, Then approvers are notified. AC3: Given notifications, When reviewed, Then OOTB records are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CHG-009 | Change - Phase 1 Configuration | Connect Predictive Intelligence/Now Assist to Change (alignment) | As a change manager, I want the PI/Now Assist hooks for Change documented (Now Assist later-phase), so that Change is ready for AI assistance without Phase 1 customization. | AC1: Given Now Assist is later-phase, When documented, Then the Change hooks are recorded for a future phase. AC2: Given PI in Phase 1, When applicable, Then only OOTB PI features are used. AC3: Given alignment, When validated, Then no AI customization is built in Phase 1. | See 'Definition of Done' tab | 1 | 4 - Low | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SCR-001 | Service Catalog - Phase 1 Configuration | Define and bound the Phase 1 catalog item list | As a catalog manager, I want the top 10-15 highest-impact items plus 2-3 generic catch-all items defined, so that value is delivered without unbounded catalog scope. | AC1: Given the item decision, When configured, Then the agreed 10-15 items plus 2-3 catch-all items are in scope. AC2: Given prioritization, When applied, Then items are ranked by impact and bounded for Phase 1. AC3: Given existing items, When reused, Then only those without technical debt are leveraged. | See 'Definition of Done' tab | 5 | 1 - Critical | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SCR-002 | Service Catalog - Phase 1 Configuration | Design catalog variables and variable sets | As a catalog manager, I want variables designed using shared variable sets where appropriate, so that catalog items are consistent and maintainable. | AC1: Given the variable decision, When configured, Then shared variable sets are used for common fields. AC2: Given an item, When built, Then item-level variables are used only where unique. AC3: Given the design, When reviewed, Then no scripted client logic beyond UI Policies is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SCR-003 | Service Catalog - Phase 1 Configuration | Configure the catalog approval model | As a catalog manager, I want the approval model configured (who approves what; auto vs manual), so that requests are approved appropriately and quickly. | AC1: Given the approval decision, When configured, Then OOTB approval rules trigger by item type or cost threshold. AC2: Given a low-cost item, When ordered, Then it follows the agreed auto/manual path. AC3: Given approvals, When reviewed, Then OOTB approval engine is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SCR-004 | Service Catalog - Phase 1 Configuration | Structure catalog fulfillment tasks | As a catalog manager, I want fulfillment tasks structured for common request types, so that fulfillment teams have clear, repeatable work. | AC1: Given the fulfillment decision, When configured, Then OOTB fulfillment task templates exist for common items. AC2: Given a request, When approved, Then fulfillment tasks generate to the right groups. AC3: Given the model, When reviewed, Then OOTB workflow/flow is used. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SCR-005 | Service Catalog - Phase 1 Configuration | Configure catalog request SLAs | As a catalog manager, I want SLAs configured for catalog requests, so that request commitments are defined and tracked. | AC1: Given the SLA decision, When configured, Then OOTB SLAs track request fulfillment by item/type. AC2: Given a request, When active, Then the SLA clock runs against the schedule. AC3: Given SLAs, When reviewed, Then OOTB SLA definitions are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SCR-006 | Service Catalog - Phase 1 Configuration | Configure catalog categorization for AI and reporting | As a catalog manager, I want catalog taxonomy configured to support AI and reporting, so that requests classify cleanly for analytics and automation. | AC1: Given the taxonomy decision, When configured, Then categories support reporting and future AI. AC2: Given an item, When categorized, Then it resolves to the agreed taxonomy. AC3: Given the taxonomy, When reviewed, Then OOTB category structures are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SCR-007 | Service Catalog - Phase 1 Configuration | Define the catalog post-launch governance model | As a catalog manager, I want a governance model for catalog item retirement and additions, so that the catalog stays healthy after go-live. | AC1: Given the governance decision, When documented, Then an item review/retirement process is defined. AC2: Given a new-item request post-launch, When raised, Then it follows the governance path. AC3: Given the model, When handed over, Then it is captured in the Admin Guide. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SCR-008 | Service Catalog - Phase 1 Configuration | Define catalog performance measurement (30/60/90) | As a catalog manager, I want catalog performance measures defined for 30/60/90 days, so that success is measurable after launch. | AC1: Given the measurement decision, When configured, Then PA indicators track request volume, cycle time, and satisfaction. AC2: Given the 30/60/90 cadence, When reviewed, Then results are reported. AC3: Given measures, When reviewed, Then OOTB PA is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-KM-001 | Knowledge - Phase 1 Configuration | Configure knowledge bases and access model | As a knowledge manager, I want the agreed knowledge bases created with an access model per KB, so that content is organized and access-appropriate. | AC1: Given the KB decision, When configured, Then the agreed KBs exist with OOTB access controls (public/authenticated/role-based). AC2: Given a user, When they browse, Then they see only KBs they are entitled to. AC3: Given KBs, When reviewed, Then OOTB KB records are used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 5 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-KM-002 | Knowledge - Phase 1 Configuration | Configure the article lifecycle workflow | As a knowledge manager, I want the article lifecycle configured (OOTB review workflow or direct publish per KB), so that articles are governed appropriately. | AC1: Given the lifecycle decision, When configured, Then the agreed workflow (1-stage/2-stage or direct) is active per KB. AC2: Given an article, When submitted, Then it follows the configured workflow. AC3: Given the workflow, When reviewed, Then OOTB article workflow is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-KM-003 | Knowledge - Phase 1 Configuration | Define knowledge ownership and authorship | As a knowledge manager, I want KB Owner/Manager roles and an authorship model assigned, so that accountability for content is clear. | AC1: Given the ownership decision, When configured, Then each KB has Owner and Manager assigned via OOTB roles. AC2: Given a new article, When created, Then the author/owner is captured. AC3: Given roles, When reviewed, Then OOTB KB roles are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-KM-004 | Knowledge - Phase 1 Configuration | Activate article templates | As a knowledge manager, I want the agreed article templates activated, so that articles are consistent and easy to author. | AC1: Given the template decision, When configured, Then templates (How-To, FAQ, Policy, Resolution) are available. AC2: Given an author, When creating an article, Then they can select a template. AC3: Given templates, When reviewed, Then OOTB template capability is used. | See 'Definition of Done' tab | 1 | 3 - Moderate | Sprint 5 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-KM-005 | Knowledge - Phase 1 Configuration | Configure article feedback capture | As a knowledge manager, I want article feedback (useful/not, comments, flagging) enabled and actioned, so that content quality improves from user input. | AC1: Given the feedback decision, When configured, Then OOTB feedback is enabled on articles. AC2: Given negative feedback, When submitted, Then it flags the article for review. AC3: Given feedback, When reviewed, Then OOTB feedback features are used. | See 'Definition of Done' tab | 1 | 3 - Moderate | Sprint 5 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-KM-006 | Knowledge - Phase 1 Configuration | Integrate Knowledge with Virtual Agent and Employee Center search | As a knowledge manager, I want knowledge surfaced through VA and Employee Center / AI Search, so that users self-serve and deflect tickets. | AC1: Given the integration decision, When configured, Then articles surface in EC search and VA responses. AC2: Given a user query, When searched, Then relevant articles are returned. AC3: Given integration, When validated, Then OOTB AI Search/VA-KB features are used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 5 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-KM-007 | Knowledge - Phase 1 Configuration | Define knowledge governance KPIs and review | As a knowledge manager, I want KM governance KPIs and a monthly review owner defined, so that knowledge stays current and valuable. | AC1: Given the governance decision, When configured, Then KPIs (usage, freshness, feedback) are tracked. AC2: Given the monthly review, When scheduled, Then an owner is named. AC3: Given KPIs, When reviewed, Then OOTB PA/KM reporting is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-KM-008 | Knowledge - Phase 1 Configuration | Plan and execute initial knowledge content seeding | As a knowledge manager, I want baseline content ported from the legacy platform for go-live, so that users have useful content on day one. | AC1: Given the seeding plan, When executed, Then the agreed baseline articles are ported and reviewed. AC2: Given ported articles, When validated, Then they meet the article standard before publish. AC3: Given seeding, When complete, Then KBs are populated for go-live. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 5 | Process Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-EC-001 | Employee Center - Phase 1 Configuration | Configure Employee Center topic categories and owners | As a EC product owner, I want the launch topic categories configured with named owners, so that employees find services in a clear structure. | AC1: Given the topic decision, When configured, Then the agreed categories (IT, HR, Facilities, Finance...) exist with owners. AC2: Given a category, When browsed, Then it surfaces the right content and items. AC3: Given topics, When reviewed, Then OOTB taxonomy is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 5 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-EC-002 | Employee Center - Phase 1 Configuration | Apply Connection branding via the OOTB theme engine | As a EC product owner, I want Connection branding/theming applied within OOTB limits, so that the portal feels like Connection without custom UI. | AC1: Given the branding decision, When applied, Then OOTB theming (logo, colors, layout) reflects Connection branding. AC2: Given a full-custom-UI request, When raised, Then it routes to the Customization Council. AC3: Given branding, When reviewed, Then the OOTB theme engine is used (no custom portal UI). | See 'Definition of Done' tab | 3 | 2 - High | Sprint 5 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-EC-003 | Employee Center - Phase 1 Configuration | Curate the home page and promoted items | As a EC product owner, I want home page promoted items and banners curated, so that employees see the most relevant services first. | AC1: Given the curation decision, When configured, Then promoted items/banners reflect the agreed priorities. AC2: Given a launch, When viewed, Then the home page surfaces top services. AC3: Given curation, When reviewed, Then OOTB promoted-content features are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-EC-004 | Employee Center - Phase 1 Configuration | Configure Employee Center search | As a EC product owner, I want search configured with synonyms, promoted results, and relevance tuning, so that users find answers quickly. | AC1: Given the search decision, When configured, Then synonyms and promoted results are set. AC2: Given a query, When searched, Then relevant results (KB, catalog) return. AC3: Given search, When reviewed, Then OOTB search config (no custom indexing) is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 5 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-EC-005 | Employee Center - Phase 1 Configuration | Surface knowledge in Employee Center | As a EC product owner, I want in-scope knowledge surfaced through Employee Center, so that self-service deflects tickets. | AC1: Given the content decision, When configured, Then the agreed KBs surface in EC. AC2: Given a topic, When browsed, Then related articles display. AC3: Given surfacing, When validated, Then OOTB KB-EC integration is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-EC-006 | Employee Center - Phase 1 Configuration | Define Employee Center migration from the existing portal | As a EC product owner, I want the migration approach from the existing intranet/portal defined, so that the transition is clean for users. | AC1: Given the migration decision, When documented, Then in-scope content/links to migrate are listed. AC2: Given go-live, When cutover, Then the agreed redirect/migration plan is followed. AC3: Given migration, When validated, Then OOTB EC replaces the prior self-service path. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-EC-007 | Employee Center - Phase 1 Configuration | Integrate Virtual Agent into Employee Center | As a EC product owner, I want Virtual Agent embedded in Employee Center for the in-scope conversations, so that users get conversational self-service. | AC1: Given the VA decision, When configured, Then the OOTB VA launcher is available in EC. AC2: Given a user, When they open VA, Then in-scope topics are available. AC3: Given integration, When validated, Then OOTB EC-VA integration is used (see VA stories). | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-EC-008 | Employee Center - Phase 1 Configuration | Define Employee Center adoption measurement | As a EC product owner, I want adoption metrics defined for Employee Center, so that success and deflection are measurable. | AC1: Given the metric decision, When configured, Then PA tracks visits, self-service rate, and deflection. AC2: Given launch, When reviewed, Then adoption is reported. AC3: Given metrics, When reviewed, Then OOTB PA is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Process Consultant / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-VA-001 | Virtual Agent - Phase 1 Configuration | Activate the 5 baseline Virtual Agent topics | As a VA administrator, I want the 5 baseline VA topics activated and configured, so that users get conversational self-service at go-live. | AC1: Given the topic decision, When configured, Then 5 baseline OOTB topics (e.g., incident, catalog, RITM status, KB search, password reset) are active. AC2: Given a user, When they invoke a topic, Then the conversation completes successfully. AC3: Given topics, When reviewed, Then OOTB VA topics are used (no NLU model rebuild). | See 'Definition of Done' tab | 3 | 2 - High | Sprint 5 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-VA-002 | Virtual Agent - Phase 1 Configuration | Configure NLU vs menu-driven matching | As a VA administrator, I want the matching approach configured (OOTB NLU intent matching or menu-driven), so that users are understood and routed correctly. | AC1: Given the matching decision, When configured, Then the agreed approach is active. AC2: Given a user utterance, When matched, Then the correct topic launches. AC3: Given utterances, When added, Then custom utterances extend OOTB NLU without a model rebuild. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 5 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-VA-003 | Virtual Agent - Phase 1 Configuration | Configure VA live-agent escalation | As a VA administrator, I want escalation from VA to a live agent configured to the right teams, so that users reach a human when self-service cannot help. | AC1: Given the escalation decision, When configured, Then OOTB live-agent handoff routes to the agreed teams. AC2: Given a failed self-service, When escalated, Then the conversation/context transfers. AC3: Given escalation, When validated, Then OOTB Connect/Advanced Work Assignment is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 5 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-VA-004 | Virtual Agent - Phase 1 Configuration | Activate VA channels for go-live | As a VA administrator, I want the agreed VA channels activated (Employee Center; others as scoped), so that users access VA where they work. | AC1: Given the channel decision, When configured, Then VA is active in the agreed channels. AC2: Given a channel, When used, Then VA responds correctly. AC3: Given channels, When reviewed, Then OOTB channel configuration is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-VA-005 | Virtual Agent - Phase 1 Configuration | Configure VA authentication | As a VA administrator, I want authentication within VA sessions configured, so that personalized, secure self-service is possible. | AC1: Given the auth decision, When configured, Then authenticated VA sessions identify the user. AC2: Given an authenticated user, When they ask about their tickets, Then VA returns their records. AC3: Given auth, When validated, Then OOTB VA authentication is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-VA-006 | Virtual Agent - Phase 1 Configuration | Integrate VA with the Service Catalog | As a VA administrator, I want VA connected to the catalog for request fulfillment, so that users can order in-scope items conversationally. | AC1: Given the integration decision, When configured, Then VA can submit agreed catalog requests. AC2: Given a user, When ordering via VA, Then a request is created correctly. AC3: Given integration, When validated, Then OOTB VA-catalog topics are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-VA-007 | Virtual Agent - Phase 1 Configuration | Document Now Assist enhancement for VA (later-phase) | As a VA administrator, I want the Now Assist enhancements for VA documented for a later phase, so that VA is ready for GenAI without Phase 1 customization. | AC1: Given Now Assist is later-phase, When documented, Then the enhancement plan is recorded. AC2: Given Phase 1, When delivered, Then only OOTB VA is configured. AC3: Given alignment, When validated, Then no GenAI customization is built in Phase 1. | See 'Definition of Done' tab | 1 | 4 - Low | Sprint 5 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-VA-008 | Virtual Agent - Phase 1 Configuration | Define VA performance measurement and governance | As a VA administrator, I want VA performance metrics and governance defined, so that VA effectiveness is measured and improved. | AC1: Given the metric decision, When configured, Then PA tracks containment, escalation, and satisfaction. AC2: Given launch, When reviewed, Then VA performance is reported. AC3: Given governance, When defined, Then a review owner is named. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PI-001 | Predictive Intelligence - Phase 1 Configuration | Select and activate the PI use cases | As a platform owner, I want the agreed PI use cases activated for Phase 1, so that AI assists where data supports it, without over-reach. | AC1: Given the use-case decision, When configured, Then OOTB PI solutions (e.g., categorization, assignment, similarity) are activated for the agreed scope. AC2: Given an out-of-scope use case, When requested, Then it is deferred with rationale. AC3: Given activation, When validated, Then only OOTB PI capabilities are used (no custom ML). | See 'Definition of Done' tab | 3 | 2 - High | Sprint 5 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PI-002 | Predictive Intelligence - Phase 1 Configuration | Assess training data quality and volume | As a platform owner, I want training data quality and volume assessed before model training, so that models are trained on sufficient, clean data. | AC1: Given the data assessment, When complete, Then volume/quality is documented per use case. AC2: Given insufficient data, When found, Then the use case is deferred or scoped down. AC3: Given filters, When applied, Then training data uses OOTB training filters. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 5 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PI-003 | Predictive Intelligence - Phase 1 Configuration | Set PI confidence thresholds | As a platform owner, I want confidence thresholds set for auto-population vs agent review, so that predictions help without eroding trust. | AC1: Given the threshold decision, When configured, Then high-confidence predictions auto-populate and lower-confidence ones surface for review. AC2: Given a prediction, When below threshold, Then the agent confirms. AC3: Given thresholds, When validated, Then OOTB PI configuration is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PI-004 | Predictive Intelligence - Phase 1 Configuration | Configure similar-incident surfacing | As a platform owner, I want similar-incident matching configured and surfaced to agents, so that agents resolve faster using prior resolutions. | AC1: Given the similarity decision, When configured, Then OOTB similarity surfaces related incidents/resolutions. AC2: Given an incident, When worked, Then similar incidents display. AC3: Given the config, When validated, Then OOTB PI similarity is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PI-005 | Predictive Intelligence - Phase 1 Configuration | Decide and configure incident clustering | As a platform owner, I want incident clustering activated (or deferred) with a reviewer named, so that recurring patterns become problems sooner. | AC1: Given the clustering decision, When made, Then clustering is activated with a named reviewer or deferred with rationale. AC2: Given a cluster alert, When raised, Then the reviewer triages it. AC3: Given the config, When validated, Then OOTB clustering is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PI-006 | Predictive Intelligence - Phase 1 Configuration | Define PI model governance | As a platform owner, I want PI model ownership, training cadence, and monitoring defined, so that models stay accurate and accountable. | AC1: Given the governance decision, When documented, Then owners, retrain cadence, and monitoring are defined. AC2: Given model drift, When detected, Then the retrain process triggers. AC3: Given governance, When handed over, Then it is captured in the Admin Guide. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 5 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-HAM-001 | HAM - Phase 1 Configuration | Configure asset classes and models for go-live | As a asset manager, I want the in-scope asset classes and models configured, so that hardware assets are tracked consistently. | AC1: Given the class decision, When configured, Then OOTB asset classes/models reflect the in-scope hardware. AC2: Given an asset, When created, Then it maps to the correct class/model. AC3: Given the config, When reviewed, Then OOTB HAM tables are used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 6 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-HAM-002 | HAM - Phase 1 Configuration | Configure asset lifecycle states and transitions | As a asset manager, I want OOTB asset lifecycle states and valid transitions configured, so that asset status reflects reality through its life. | AC1: Given the lifecycle decision, When configured, Then OOTB states and transitions are active. AC2: Given an asset, When it moves stages, Then only valid transitions are allowed. AC3: Given the config, When reviewed, Then no custom lifecycle scripting is added. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-HAM-003 | HAM - Phase 1 Configuration | Configure stockrooms | As a asset manager, I want the agreed stockrooms configured with managers, so that asset inventory is organized and owned. | AC1: Given the stockroom decision, When configured, Then the agreed stockrooms exist with managers. AC2: Given an asset receipt, When recorded, Then it lands in the correct stockroom. AC3: Given stockrooms, When reviewed, Then OOTB stockroom capability is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-HAM-004 | HAM - Phase 1 Configuration | Activate the agreed IMAC workflows | As a asset manager, I want the in-scope IMAC (install/move/add/change) workflows activated, so that asset moves are governed. | AC1: Given the IMAC decision, When configured, Then the agreed workflows are active at the agreed scope. AC2: Given an asset move, When initiated, Then the workflow drives the tasks. AC3: Given workflows, When reviewed, Then OOTB asset workflows are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-HAM-005 | HAM - Phase 1 Configuration | Configure the asset intake process | As a asset manager, I want the asset intake process (purchase order to stockroom) configured, so that new assets enter the system cleanly. | AC1: Given the intake decision, When configured, Then assets flow from receipt to stockroom via OOTB process. AC2: Given a received asset, When intaken, Then it is recorded with required attributes. AC3: Given intake, When reviewed, Then OOTB intake is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-HAM-006 | HAM - Phase 1 Configuration | Configure asset retirement and disposal | As a asset manager, I want the asset retirement and disposal process configured, so that end-of-life assets are handled and recorded. | AC1: Given the disposal decision, When configured, Then OOTB retirement/disposal steps are active with disposal vendors. AC2: Given a retired asset, When disposed, Then the record reflects disposal and compliance. AC3: Given the process, When reviewed, Then OOTB capability is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-HAM-007 | HAM - Phase 1 Configuration | Define the asset ownership model | As a asset manager, I want the asset ownership model defined (user, department, or cost center), so that assets roll up to the right accountability. | AC1: Given the ownership decision, When configured, Then assets carry the agreed ownership dimension. AC2: Given an asset, When assigned, Then ownership resolves correctly. AC3: Given OOTB fields, When used, Then no custom ownership fields are added. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-HAM-008 | HAM - Phase 1 Configuration | Link HAM assets to CMDB CIs | As a asset manager, I want assets linked to CMDB CIs with a clear management boundary, so that asset and CI data stay aligned for CSDM. | AC1: Given the link decision, When configured, Then in-scope assets relate to their CMDB CIs. AC2: Given an asset/CI pair, When viewed, Then the asset-vs-CI managed attributes are clear. AC3: Given the link, When validated, Then OOTB asset-CI relationship is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 6 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PA-001 | Performance Analytics - Phase 1 Configuration | Activate the baseline OOTB indicators | As a analytics lead, I want the agreed OOTB PA indicators activated for go-live, so that operational performance is measured from day one. | AC1: Given the indicator decision, When configured, Then OOTB indicators (MTTR, SLA attainment, change success...) are active. AC2: Given the first collection, When run, Then indicators populate with data. AC3: Given indicators, When reviewed, Then OOTB content packs are used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 6 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PA-002 | Performance Analytics - Phase 1 Configuration | Configure breakdown dimensions | As a analytics lead, I want breakdown dimensions configured for indicator segmentation, so that metrics can be sliced by the dimensions that matter. | AC1: Given the breakdown decision, When configured, Then indicators segment by the agreed dimensions (group, category, priority). AC2: Given an indicator, When viewed, Then breakdowns render correctly. AC3: Given breakdowns, When reviewed, Then OOTB breakdown sources are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PA-003 | Performance Analytics - Phase 1 Configuration | Build the agreed scorecards | As a analytics lead, I want scorecards built for the agreed audiences, so that leaders and teams see the metrics they need. | AC1: Given the scorecard decision, When configured, Then scorecards exist per audience. AC2: Given an audience, When they open a scorecard, Then it shows their indicators. AC3: Given scorecards, When reviewed, Then OOTB PA is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PA-004 | Performance Analytics - Phase 1 Configuration | Set indicator thresholds (green/yellow/red) | As a analytics lead, I want thresholds set for each indicator, so that performance status is visible at a glance. | AC1: Given the threshold decision, When configured, Then each indicator has green/yellow/red bands. AC2: Given a breach, When it occurs, Then the indicator shows the correct status. AC3: Given thresholds, When reviewed, Then OOTB threshold config is used. | See 'Definition of Done' tab | 1 | 3 - Moderate | Sprint 6 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PA-005 | Performance Analytics - Phase 1 Configuration | Configure the data collection cadence | As a analytics lead, I want data collection jobs scheduled at the agreed cadence, so that metrics are timely and consistent. | AC1: Given the cadence decision, When configured, Then collection jobs run at the agreed times. AC2: Given a job, When it runs, Then it completes without errors. AC3: Given jobs, When reviewed, Then OOTB PA jobs are used. | See 'Definition of Done' tab | 1 | 3 - Moderate | Sprint 6 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PA-006 | Performance Analytics - Phase 1 Configuration | Publish dashboards with the right access | As a analytics lead, I want PA dashboards published with role-based access, so that the right people see the right dashboards. | AC1: Given the access decision, When configured, Then dashboards are shared per role. AC2: Given a user, When they open a dashboard, Then they see only what they are entitled to. AC3: Given publishing, When reviewed, Then OOTB sharing/ACLs are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PA-007 | Performance Analytics - Phase 1 Configuration | Decide trending and forecasting activation | As a analytics lead, I want trending/forecasting activated at the agreed horizon (or deferred), so that leaders can see direction, not just current state. | AC1: Given the forecasting decision, When made, Then trending/forecasting is activated at the agreed horizon or deferred. AC2: Given an indicator, When forecast, Then the projection renders. AC3: Given the config, When validated, Then OOTB PA forecasting is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-PA-008 | Performance Analytics - Phase 1 Configuration | Migrate or retire Classic Reports | As a analytics lead, I want in-scope Classic Reports migrated to PA or retired, so that reporting consolidates on PA without clutter. | AC1: Given the migration decision, When made, Then each in-scope Classic Report is migrated to PA or retired with rationale. AC2: Given a migrated report, When validated, Then the PA equivalent matches. AC3: Given the work, When reviewed, Then OOTB PA/reporting is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Solution Architect | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.

## Integration User Stories
CONNECTION - INTEGRATION USER STORIES (SN Agile / rm_story import)
Default Phase 1 configuration stories for the contract-configurable decisions. Given/When/Then acceptance criteria; shared Definition of Done on its own tab. See README for import steps.
number | epic | short_description | description | acceptance_criteria | definition_of_done | story_points | priority | sprint | assignment (role) | state | notes / OOTB reference
CONN-INT-001 | Integrations - Phase 1 Configuration | Configure Active Directory / Entra ID user sync | As a integration engineer, I want AD/Entra ID user synchronization configured via OOTB scheduled import, so that user data stays accurate from the authoritative source. | AC1: Given AD/Entra connectivity, When the OOTB import runs, Then in-scope users sync with required attributes. AC2: Given coalesce rules, When the import repeats, Then no duplicates are created. AC3: Given the integration, When validated, Then OOTB LDAP/Graph import is used (no custom sync code). | See 'Definition of Done' tab | 3 | 1 - Critical | Sprint 3 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INT-002 | Integrations - Phase 1 Configuration | Configure SSO (SAML 2.0 / OIDC) | As a integration engineer, I want SSO configured with the Connection IdP using OOTB SAML 2.0 (or OIDC), so that users authenticate securely via single sign-on. | AC1: Given IdP metadata, When configured, Then OOTB SSO authenticates users against the Connection IdP. AC2: Given a login, When SSO completes, Then the user lands authenticated. AC3: Given SSO, When validated, Then OOTB multi-provider SSO is used. | See 'Definition of Done' tab | 3 | 1 - Critical | Sprint 3 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INT-003 | Integrations - Phase 1 Configuration | Configure the SCCM / MECM Service Graph Connector | As a integration engineer, I want the SCCM/MECM connector configured to populate CMDB, so that client/server CI data flows from SCCM into a CSDM-aligned CMDB. | AC1: Given SCCM connection details, When configured, Then the OOTB SGC for SCCM connects and tests successfully. AC2: Given a scheduled import, When run, Then in-scope CIs populate per the class mapping. AC3: Given the connector, When validated, Then OOTB SGC is used (no custom JDBC pipeline). | See 'Definition of Done' tab | 5 | 2 - High | Sprint 3 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INT-004 | Integrations - Phase 1 Configuration | Configure the Microsoft Intune connector | As a integration engineer, I want the Intune connector configured to populate mobile/endpoint CI data, so that Intune-managed devices appear in the CMDB. | AC1: Given Intune/Graph credentials, When configured, Then the OOTB Intune connector connects and tests successfully. AC2: Given a scheduled import, When run, Then in-scope devices populate. AC3: Given the connector, When validated, Then OOTB connector is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 3 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INT-005 | Integrations - Phase 1 Configuration | Map AD groups to ServiceNow groups and roles | As a integration engineer, I want AD group-to-ServiceNow group/role mapping configured, so that access derives from directory membership. | AC1: Given the group mapping, When configured, Then AD groups sync to the agreed ServiceNow groups/roles. AC2: Given a membership change in AD, When synced, Then ServiceNow membership updates. AC3: Given mapping, When validated, Then OOTB group import is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 3 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INT-006 | Integrations - Phase 1 Configuration | Configure email integration | As a integration engineer, I want outbound SMTP relay and inbound mailboxes/actions configured, so that notifications send and inbound email creates/updates records. | AC1: Given relay/mailbox details, When configured, Then outbound notifications deliver and inbound actions process mail. AC2: Given an inbound email, When received, Then the correct record is created/updated. AC3: Given email, When validated, Then OOTB email and inbound actions are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INT-007 | Integrations - Phase 1 Configuration | Configure integration health monitoring | As a integration engineer, I want integration health monitoring configured for all connectors, so that integration failures are detected early. | AC1: Given the monitoring decision, When configured, Then connector run status and failures are visible. AC2: Given a failed import, When it occurs, Then it surfaces to the platform team. AC3: Given monitoring, When validated, Then OOTB integration logs/dashboards are used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 3 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-INT-008 | Integrations - Phase 1 Configuration | Confirm certificate and security requirements | As a integration engineer, I want certificate and security requirements satisfied for all integrations, so that integrations meet Connection security standards. | AC1: Given security requirements, When applied, Then certificates and credentials meet Connection standards (vaulted, least-privilege). AC2: Given a connection, When established, Then it uses approved encryption. AC3: Given security, When reviewed, Then no secrets are hard-coded. | See 'Definition of Done' tab | 2 | 2 - High | Sprint 3 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SGC-001 | Service Graph Connectors - Phase 1 Configuration | Activate the in-scope Service Graph Connectors | As a integration engineer, I want the agreed Service Graph Connectors (SCCM, Intune) activated, so that authoritative CI data flows into the CMDB. | AC1: Given the connector decision, When activated, Then SCCM and Intune SGCs are live for the agreed scope. AC2: Given activation, When run, Then in-scope CIs populate. AC3: Given connectors, When validated, Then OOTB SGC apps are used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SGC-002 | Service Graph Connectors - Phase 1 Configuration | Set the source of record per CI class across connectors | As a integration engineer, I want an authoritative source of record set per CI class where connectors and Discovery overlap, so that CI conflicts resolve predictably. | AC1: Given overlap, When IRE rules are set, Then the authoritative source wins per class. AC2: Given a CI from two sources, When ingested, Then it reconciles to one record. AC3: Given the rules, When validated, Then OOTB IRE is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SGC-003 | Service Graph Connectors - Phase 1 Configuration | Configure connector sync frequency | As a integration engineer, I want each connector's sync frequency configured, so that CI freshness matches operational need without overload. | AC1: Given the cadence decision, When configured, Then each connector runs at the agreed frequency. AC2: Given a run, When complete, Then data is current within the agreed window. AC3: Given schedules, When validated, Then OOTB scheduling is used. | See 'Definition of Done' tab | 1 | 3 - Moderate | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SGC-004 | Service Graph Connectors - Phase 1 Configuration | Map source attributes to ServiceNow CI fields | As a integration engineer, I want connector source fields mapped to OOTB CI fields, so that CI attributes are accurate and normalized. | AC1: Given the mapping decision, When configured, Then source fields map to OOTB CI fields. AC2: Given a CI, When imported, Then key attributes populate correctly. AC3: Given mapping, When validated, Then OOTB connector mapping is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SGC-005 | Service Graph Connectors - Phase 1 Configuration | Configure Content Library normalization | As a integration engineer, I want OOTB Content/Context Service normalization configured, so that hardware/software names are normalized to prevent sprawl. | AC1: Given the normalization decision, When configured, Then OOTB normalization standardizes product names. AC2: Given inconsistent source names, When imported, Then they normalize. AC3: Given normalization, When validated, Then OOTB Content Library is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SGC-006 | Service Graph Connectors - Phase 1 Configuration | Define the deduplication strategy across connectors | As a integration engineer, I want a deduplication strategy configured to prevent CI proliferation, so that the CMDB stays clean as connectors expand it. | AC1: Given the dedup decision, When configured, Then IRE prevents duplicate CIs across connectors. AC2: Given a duplicate candidate, When ingested, Then it matches the existing CI. AC3: Given the strategy, When validated, Then OOTB IRE is used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SGC-007 | Service Graph Connectors - Phase 1 Configuration | Configure connector health monitoring and escalation | As a integration engineer, I want connector health monitoring with escalation configured, so that connector failures are caught and escalated. | AC1: Given the monitoring decision, When configured, Then connector health is visible with escalation on failure. AC2: Given a failed run, When it occurs, Then escalation triggers. AC3: Given monitoring, When validated, Then OOTB monitoring is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-SGC-008 | Service Graph Connectors - Phase 1 Configuration | Validate the expanded CMDB before sprint close | As a integration engineer, I want the connector-expanded CMDB validated before sprint close, so that downstream processes trust the CI data. | AC1: Given the connectors live, When validation runs, Then a sample of CIs is checked against source. AC2: Given gaps, When found, Then they are logged and remediated before close. AC3: Given validation, When complete, Then CMDB Health meets the agreed target. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CTI-001 | Vonage CTI & Interactions - Phase 1 Configuration | Install and configure the OOTB OpenFrame softphone | As a CTI engineer, I want OpenFrame configured to host the Vonage softphone in the workspace, so that agents have a CTI softphone without a separate app. | AC1: Given OpenFrame activated, When configured, Then the Vonage softphone loads in the Agent/SO Workspace. AC2: Given an agent, When they log in, Then the softphone is available with the right roles. AC3: Given OpenFrame, When validated, Then OOTB OpenFrame + the Vonage adapter are used (no custom softphone). | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CTI-002 | Vonage CTI & Interactions - Phase 1 Configuration | Map agents to Vonage extensions | As a CTI engineer, I want agents mapped to Vonage extensions/agent IDs, so that calls route to the correct ServiceNow agent. | AC1: Given the agent mapping, When configured, Then each agent maps to their Vonage extension. AC2: Given an inbound call, When routed, Then it reaches the mapped agent. AC3: Given mapping, When validated, Then OOTB CTI mapping is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CTI-003 | Vonage CTI & Interactions - Phase 1 Configuration | Configure inbound screen-pop and caller matching | As a CTI engineer, I want inbound screen-pop configured to open an Interaction with caller match, so that agents get caller context automatically. | AC1: Given an inbound call, When it rings, Then an Interaction opens with the caller matched by phone number. AC2: Given no match, When the call arrives, Then a guest Interaction opens. AC3: Given matching, When validated, Then OOTB CTI/Interaction config is used (no scripted screen-pop). | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CTI-004 | Vonage CTI & Interactions - Phase 1 Configuration | Configure Interaction to Incident/Request creation | As a CTI engineer, I want agents able to create or link an Incident/Request from the Interaction, so that calls convert to the right ITSM record. | AC1: Given an Interaction, When the agent acts, Then they create or link an Incident or Request via OOTB actions. AC2: Given the created record, When saved, Then interaction_related_record links it to the Interaction. AC3: Given the flow, When validated, Then OOTB Interaction relationships are used. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CTI-005 | Vonage CTI & Interactions - Phase 1 Configuration | Map Vonage queues to assignment groups | As a CTI engineer, I want Vonage queues/skills mapped to ServiceNow assignment groups, so that routing context carries from telephony to ITSM. | AC1: Given the queue mapping, When configured, Then Vonage queues map to the agreed assignment groups. AC2: Given a queued call, When handled, Then the Interaction/record reflects the routing context. AC3: Given mapping, When validated, Then OOTB configuration is used. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.
CONN-CTI-006 | Vonage CTI & Interactions - Phase 1 Configuration | Port the legacy Vonage configuration | As a CTI engineer, I want the legacy Vonage integration ported onto OOTB OpenFrame + connector, so that parity with the legacy phone experience without custom middleware. | AC1: Given the legacy inventory, When reviewed, Then config is rebuilt OOTB and bespoke middleware is not ported. AC2: Given a custom legacy script, When found, Then it is evaluated vs OOTB and routed to Council if needed. AC3: Given parity testing, When run, Then inbound call to screen-pop to Incident/Request matches the legacy experience. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 4 | Solution Architect / Technical Consultant | Draft | OOTB-first: configure within the Rule of Three; any delta routes to the Customization Council.

## Definition of Done
CONNECTION - DEFINITION OF DONE (applies to every story)
From the Engagement Delivery Guidelines + SOW. A story is Done only when all gates pass.
DoD | Acceptance criteria were reviewed and approved by the Product Owner BEFORE build began.
DoD | All acceptance criteria are met and validated by the Product Owner (or delegate) at close.
DoD | Built OOTB-first within the Rule of Three (Configuration / UI Policy / Flow Designer); any deviation cleared the Customization Council via the two-key decision.
DoD | Peer configuration/code review complete.
DoD | Integration touchpoints exercised in sub-production (if the story touches integrations).
DoD | No P1 defects open against the story; P2s triaged.
DoD | Configuration captured in an update set and promotable; no development left in production.
DoD | Any deviation logged in the Governance Triage Log with scope/budget/upgrade impact and PCR status.
DoD | Demo-ready: the story can be shown against real Connection data in the sprint demo.