## Slide 1
Modernizing the Core
Connection + ECS - Project Kickoff
An 18-week, OOTB-first ServiceNow reimplementation - a clean, AI-ready platform, delivered together.
Prepared by Everforth ECS Federal | ServiceNow Practice | Confidential
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
1

## Slide 2
TODAY
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
2
Kickoff Agenda
Why we're here - the goal and the outcomes
What Phase 1 delivers
The 18-week journey
How we work: the OOTB-First approach
Who does what - roles and accountability
How we keep on track - governance and checks
What we need from you, and your first two weeks

## Slide 3
THE GOAL
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
3
Why We're Here
Exit the domain-separated shared instance - move to a modern, governed, dedicated platform.
Stand up a proven, OOTB-aligned baseline that is upgrade-friendly and ready for AI.
Establish a healthy, CSDM-aligned CMDB - the foundation for change risk scoring and clean data.
Deliver a modern Employee Center that deflects tickets and helps employees self-serve.
Track real operational gains from day one.
The theme: We modernize the core first, then improve from there. Deviations are managed - never lost.

## Slide 4
OUTCOMES
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
4
What Success Looks Like
MTTR
Faster mean time to resolution
SLA
Higher SLA attainment
CHANGE
Higher change success rate
DEFLECTION
More tickets self-served
Tracked transparently in Platform Analytics from day one.
Exit domain separation
AI-ready foundation
Clean CSDM CMDB
Modern Employee Center

## Slide 5
The 18-Week Journey
Two-week sprints | four stages | Go-Live at Week 16
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
5

## Slide 6
THE PLAN
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
6
Four Stages, Eight Sprints
STAGE 1 Initiate & Plan Sprints 0-2 Weeks 1-6
Governance, greenfield stand-up, CSDM data foundation
STAGE 2 Execute Sprints 3-5 Weeks 7-12
ITSM Core & Change/CAB; Employee Center, VA & Knowledge
STAGE 3 Deliver Sprints 6-7 Weeks 13-16
HAM, analytics, SIT/UAT, governed cutover
STAGE 4 Close Sprint 8 Weeks 17-18
Hypercare, KT, roadmap
GO-LIVE | Wk 16

## Slide 7
SCOPE
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
7
What Phase 1 Delivers
ITSM Core
Incident, Request, Knowledge, Problem & Change/CAB in Service Operations Workspace
Service Catalog
Your 10-15 highest-impact items + generic catch-all requests
Employee Experience
Employee Center, Virtual Agent, AI Search & Knowledge Management
Platform Baselines
Subscription Mgmt, Security Center, Predictive Intelligence, Platform Analytics
CMDB & CSDM
CSDM alignment, Service Graph Connectors (SCCM, Intune), Discovery
Hardware Asset Mgmt
Stockrooms + foundational HAM to keep CSDM aligned for Phase 2
Integrations
AD / SSO, SCCM, Intune & Vonage - leveraging your existing setup
Later Phases
P2 - UX expansion | P3 - ITOM & intelligence | P4+ - full AI

## Slide 8
HOW WE WORK
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
8
The OOTB-First Approach
Every build starts from standard ServiceNow, demonstrated first. We meet the need the standard way before considering any change - protecting your investment and keeping the platform upgradeable.
THE RULE OF THREE
1 Configuration
2 UI Policy
3 No-code Flow Designer
Customization Transparent review + Two-Key sign-off before any work
Nothing is lost: Every deviation request is logged, assessed, and decided in the open via the Governance Triage Log.

## Slide 9
Working Together
Clear roles, simple checks, transparent decisions
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
9

## Slide 10
ROLES & ACCOUNTABILITY
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
10
Who Does What
CONNECTION
ECS FEDERAL
Project Sponsor - decisions, budget, business-need approval, Go-Live
Project Manager - coordination, SME scheduling, status
Technical Lead - access, credentials, technical approvals
Process SMEs - process decisions & workshops
UAT Testers - acceptance testing (Wks 13-16)
Engagement Manager - delivery, governance, schedule, risk
Solution Architect - architecture, CSDM, impact assessments
Process Consultant - workshops, OOTB guidance, training
Technical Consultant(s) - configuration, data, integrations
Practice Lead - quality oversight, technical-path approval

## Slide 11
STAYING ON TRACK
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
11
How We Keep on Track
THE TWO-KEY DECISION MODEL
FIRST KEY Connection Sponsor - business need
SECOND KEY ECS Practice - technical path
Both keys required, decision in ~48 hours Logged in the Governance Triage Log within 24 hrs, visible to both teams - nothing is built that isn't both a real business need and a real technical necessity.
THE RHYTHM
Weekly - status report
Every 2 weeks - sprint demo + Sponsor sync
As needed (48h) - Customization Council
Monthly - steering & KPIs
Your weekly check: See progress (status), see it working (demo), see every open decision (triage log).

## Slide 12
GETTING STARTED
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
12
What We Need From You - Sprint 0
Empowered process owners who can decide in workshops
The Foundation Data Pack completed (users, locations, groups, assignment rules, SLAs)
Environment access and integration credentials
SME availability during their process-area sprints
Prompt feedback during demos and acceptance testing
First two weeks: Kickoff, confirm Sponsor & sign the Council charter, provision access, distribute the data pack, map SMEs.

## Slide 13
Let's Modernize the Core
Next step: confirm names, schedule Sprint 0 workshops, and begin.
Questions? Your ECS Engagement Manager is your first point of contact.
Everforth ECS Federal
MODERNIZING THE CORE | CONNECTION | CONFIDENTIAL
13