INTERNAL - DELIVERY GUIDELINES

Connection Engagement

Delivery Guidelines

How we operate on Connection - the discipline, the gates, and the conversations

ECS Federal - ServiceNow Practice

Audience: ECS delivery team - EM, Solution Architect, Process Consultant, Technical Consultant(s), Practice Lead

Companion to: Team Onboarding & Vision - OOTB Delivery Playbook - Internal Governance Operating Guide - SOW v2.0

Document ID: INT-CONN-GDL-01     ·     Version: 1.0     ·     Status: Draft

Internal Use Only · Confidential

# How to Use This Document

These are the operating rules for the Connection engagement - the practical mechanics behind the OOTB-first discipline. Read the Team Onboarding & Vision Guide first for the why; this document is the how. It is the engagement-specific companion to the OOTB Delivery Playbook and the Internal Governance Operating Guide; where this document and the SOW differ, the SOW (the Project Charter) governs.

# 1.  The OOTB-First Operating Model

Default to OOTB. Every in-scope build begins with a demonstration of standard ServiceNow functionality. A delta from the baseline is acceptable only when it is (a) tied to a documented business outcome, (b) not achievable by configuring an OOTB capability, and (c) signed off through the two-key decision. We present the OOTB alternative first, every time - including to a Sponsor who asks for the legacy pattern.

Frame outcomes, not features, with the customer: "Your outcome is faster change cycle time; OOTB delivers it; the legacy seven-step workflow does not."

# 2.  The Rule of Three

Before anything is treated as a customization, it must fail all three tests. If a requirement can be met by any of these, it is a standard story - no Customization Request needed:

| # | Test | If it fits |
| --- | --- | --- |
| 1 | Configuration | Build it as a standard story; straight to the sprint. |
| 2 | UI Policy | Build it as a standard story; straight to the sprint. |
| 3 | Flow Designer (no-code) | Build it as a standard story; straight to the sprint. |

Only a requirement that fails all three is a customization, and customizations follow the deviation path below.

# 3.  The Deviation Path

When a requirement fails the Rule of Three, the Solution Architect drafts an impact assessment - business need, OOTB alternatives considered, scope and budget estimate, and upgrade impact - before any decision is made. The request then goes to the two-key decision: the Connection Sponsor approves the business need, and the ECS Practice Lead approves the technical path. Both keys are required.

## Service levels

Two-key decision within 48 hours of the impact assessment being published.

Total wall-clock time from surface to decision: 5 business days maximum.

If it is blocking active sprint work, the SA flags it urgent and the SLAs compress to 24 hours total.

# 4.  The Customization Council

The Council gates every Customization Request to keep the discipline intact. No exceptions, no "just this one," and no decisions in hallway conversations.

| Aspect | Rule |
| --- | --- |
| Cadence | Weekly, 30 minutes, Customization Requests only. If none are pending, the meeting is canceled. |
| Chair | Engagement Manager. Solution Architect presents the impact assessment. |
| Decision cap | Cumulative cap of 5 approved customizations across Phase 1. |
| At customization #6 | Triggers a PCR conversation: the customer descopes to compensate, accepts a PCR, or reverses recent approvals. |
| Logging | Every request - approved, rejected, or deferred - is logged in the Governance Triage Log within 24 hours. |

# 5.  Definition of Done

The SOW's Definition of Done is contractual. These operational gates are how the team enforces it on every story:

Acceptance criteria were approved by the Product Owner before build began, and all are met and validated at close.

Integration touchpoints exercised in sub-production (if the story touches integrations).

Peer code/config review complete; no P1 defects open against the story.

Any deviation logged in the Triage Log with its scope/budget/upgrade implications and PCR status.

# 6.  Trust-but-Verify - Engagement Health

Health is reported weekly so problems surface early. The Engagement Manager sends the metrics to practice management every Friday by close of business. Yellow or Red status triggers a Monday 1:1 to plan the response.

| Signal | Watch for |
| --- | --- |
| Sprint velocity | 3-sprint average vs. planned; sustained drop below 75% is a red flag. |
| Customization count | Approaching the cap of 5; reaching 6 forces a PCR conversation. |
| Dependency slips | Unchecked Sprint 0/1 readiness items; three or more slips is a red flag. |

Engagement is RED if any of: two or more red metrics; customization count >= 6 mid-Phase; three or more dependency slips; or velocity below 75% for three consecutive sprints.

# 7.  Working With the Client - Do's and Don'ts

The conversations decide engagement health more than the technical execution does. Hold the discipline with partnership, not preaching.

## Do

Demonstrate the OOTB pattern first, then discuss - end each workshop with a signed-off story, not a list of "things to think about."

Capture every deviation request transparently in the Triage Log, even the ones you expect to reject.

Have the hard conversation early - a dependency slip or scope drift named in week 3 is cheap; named at UAT it is not.

Frame to the Sponsor in terms of their outcomes and the maintenance burden avoided.

## Don't

Don't accept a customization in the room - it goes to the Council, every time.

Don't let "Internal Use Only" material or candid internal framing reach the client.

Don't frame the customer's prior choices as wrong - we are modernizing the core, not litigating the past.

Don't silently absorb scope - log it, surface it, and let governance decide.