INTERNAL - SPRINT OPERATING KIT

Connection Engagement

Sprint Operating Kit

Definition of Ready, ceremonies, and cadence - how we run each sprint

ECS Federal - ServiceNow Practice

Audience: ECS delivery team - EM, SA, PC, TC

Companion to: Engagement Delivery Guidelines - Sprint Demo template - User Story backlog

Document ID: INT-CONN-SOK-01     ·     Version: 1.0     ·     Status: Draft

Internal Use Only · Confidential

# How to Use This Kit

This kit standardizes how we run each two-week sprint on Connection: when a story is Ready, how we plan, demo, and retro, and the weekly cadence. It complements the Definition of Done in the Delivery Guidelines.

# 1.  Definition of Ready (DoR)

A story may enter a sprint only when:

It traces to a workshop decision (or a clear configuration need) and an epic.

Acceptance criteria are written (Given/When/Then) and reviewed with the Product Owner.

Dependencies (data, access, prior stories) are identified and met or scheduled.

It is estimated (story points) and small enough to finish in the sprint.

It is OOTB-first; any likely deviation is flagged for the Council before build.

# 2.  Sprint Planning Agenda (90 min)

Review sprint goal and capacity (see Sprint Plan & Capacity Model).

Walk the candidate stories; confirm each meets the DoR.

Confirm acceptance criteria and estimates; assign owners.

Identify dependencies and customer inputs needed this sprint (update the Dependency Tracker).

Commit the sprint backlog; record in SN Agile.

# 3.  Sprint Demo / Review

Use the Sprint Demo template. Demo working stories against real Connection data; secure Product Owner acceptance (3-business-day window) and record it in the Acceptance & Sign-off Log.

# 4.  Sprint Retrospective (45 min)

What went well; what to keep.

What slowed us; root cause (esp. dependency slips or OOTB-defense churn).

Actions with owners and due dates; carry into the next sprint.

Feed material risks/decisions into the RAID and Decision Register.

# 5.  Weekly Cadence

| When | Ceremony / Touchpoint | Owner |
| --- | --- | --- |
| Daily | Standup (15 min) | PC |
| Weekly | Status report to Sponsor/PM; health report to practice mgmt (Fri COB) | EM |
| Bi-weekly | Sprint demo + Sponsor sync; planning + retro at sprint boundary | EM/PC |
| As needed | Customization Council (48-hr SLA) | EM |
| Monthly | Steering review | EM |

The cadence exists to surface issues early. A dependency slip named at standup is cheap; one discovered at the demo is not.