## Instructions
04 — Technical Services & Applications
CMDB-CSDM Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Technical Service and Application Service CIs that underpin each Business Service. Technical Services group the infrastructure and software components that together deliver a Business Service. This workbook drives the CMDB relationship layer that enables service impact analysis, Major Incident routing, and CMDB health scoring.
Who fills this out | Customer-side: Infrastructure Lead and Application Owners, facilitated by ECS SA. One row per Technical Service or Application Service. Can be completed iteratively as Discovery data becomes available in Sprint 2.
Sprint window | Sprint 1 Week 2 (draft structure) — Sprint 2 Week 2 (confirmed after first Discovery run)
Estimated effort | 3–5 hours. Draft in Sprint 1; refine after Discovery in Sprint 2.
Related workbooks | 01 CSDM Service Taxonomy · 03 Business Service Definitions · 05 Service-CI Relationships · 02 CI Class Selection
Success criteria
• | Every Business Service from Workbook 03 has at least one Technical Service mapped to it.
• | Key managed applications (from cmdb_ci_appl scope in Workbook 02) are represented as Application Service CIs.
• | Technical Service CIs are loaded in ServiceNow before Sprint 2 Discovery runs.
• | Discovery-identified CIs can be related to Technical Services within Sprint 2.

## Process Decisions
04 — Technical Services & Applications — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | How granular should Technical Services be? | Group by infrastructure domain: one Technical Service per logical infrastructure grouping (e.g., 'Windows Server Infrastructure', 'Network Core', 'Microsoft 365 Platform'). Avoid one Technical Service per physical server. |  | A Technical Service per physical server creates maintenance overhead that destroys CMDB health scores. The correct level of granularity is: 'What group of CIs would I notify if this Technical Service were degraded?'
2 | Should application servers and their applications be separate Technical Services? | Yes. Create one Technical Service for the server infrastructure tier and a separate Application Service CI for each managed application. Relate the Application Service to both the server Technical Service and the Business Service it supports. |  | The CSDM model separates infrastructure from application for a reason: different teams manage them, they have different maintenance windows, and they fail independently. Mixing them breaks service impact analysis.
3 | How do we handle shared infrastructure (e.g., a server that supports multiple Business Services)? | The shared server CI is related to a Technical Service. That Technical Service is then related to multiple Business Services. The server CI is related to the Technical Service once — not duplicated per Business Service. |  | OOTB relationship modelling handles fan-out naturally. Duplicating CIs to represent shared infrastructure creates orphaned duplicates after Discovery reconciliation.
4 | Do we need Technical Service CIs before Discovery runs? | Yes. Create the Technical Service CIs manually in Sprint 1 so that Discovery-found CIs can be related to them in Sprint 2. An empty service hierarchy means Discovery-found CIs have no service context. |  | CIs without service relationships are invisible to service impact analysis. Creating the Technical Service shells early means Sprint 2 Discovery produces immediately useful data.

## Dependencies
04 — Technical Services & Applications — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Business Service Definitions (Workbook 03) approved | Required | Customer IT Director | Sprint 1 Wk 2 | Technical Services must link upward to approved Business Services.
2 | CI Class Selection (Workbook 02) confirmed | Required | ECS SA + Customer IT Ops | Sprint 1 Wk 2 | Technical Service scope is bounded by the agreed CI classes.
3 | First Discovery run results | Recommended | ECS Architect | Sprint 2 Wk 1 | Discovery results allow Technical Services to be validated against actual CI population.
4 | Application inventory (spreadsheet or legacy CMDB export) | Recommended | Customer App Owners | Sprint 1 Wk 2 | Needed to identify Application Service CIs before Discovery finds them.

## Configuration Data
04 — Technical Services & Applications — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Technical Service Template Fields
Technical Service Name | [Customer to complete] | Format: [Domain] + 'Infrastructure' e.g., 'Windows Server Infrastructure'.
Description | [Customer to complete] | What infrastructure components does this service group?
Support Group | [Customer to complete] | The team responsible for this infrastructure domain.
Parent Business Service(s) | [Customer to complete — link to Workbook 03 rows] | One or more Business Services this Technical Service supports.
Operational Status | 1 — Operational
2. Application Service Template Fields
Application Name | [Customer to complete] | The managed application name. Use the business name, not the executable name.
Application Version (if fixed) | [Customer to complete or 'multi-version']
Application Owner / Team | [Customer to complete] | The team responsible for the application.
Parent Technical Service | [Customer to complete — link above] | The infrastructure domain this application runs on.
Parent Business Service | [Customer to complete — link to Workbook 03] | The Business Service this application supports.

## R&R
04 — Technical Services & Applications — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Draft Technical Service list (infrastructure domains) | R/A | C | ECS SA drafts based on CSDM taxonomy; customer confirms infrastructure groupings.
Identify managed Application Services | C | R/A | Customer Application Owners list managed apps; ECS validates against CSDM model.
Load Technical Service CIs into ServiceNow | R/A | I | ECS SA loads before Sprint 2 Discovery begins.
Load Application Service CIs into ServiceNow | R/A | C | ECS SA loads after customer confirms list.
Relate Technical Services to Business Services | R/A | C | ECS SA configures relationships; customer validates in dependency view.
Validate Technical Service coverage after Discovery | R | C | ECS SA validates that Discovery-found CIs map to Technical Services.

## Consultant Guide
04 — Technical Services & Applications — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Creating Technical Service shells before Discovery
The most important sequencing decision is loading Technical Service CI shells before Discovery runs. Without them, Discovery-found CIs have no service context and the CMDB health score starts low. Create 5–10 Technical Service CIs manually in Sprint 1 Week 2. These are just shell records with a name, description, and support group — Discovery fills in the CI relationships later.
Application Service scoping
Not every installed application should be an Application Service CI. Scope Application Services to applications that: (a) have a named owner, (b) have or should have an SLA, or (c) appear in incidents frequently enough to benefit from service impact analysis. Rule of thumb: if nobody would notice it was missing from the CMDB, it shouldn't be an Application Service CI.
The relationship between Application Services and SAM
Application Service CIs in the CMDB represent managed applications at the service level. SAM's software normalisation covers installed binaries at the asset level. These are complementary, not overlapping. An Application Service CI for 'Microsoft SQL Server' represents the managed database service; SAM tracks every SQL Server installation across the fleet. Don't conflate them.

## Adoption vs Re-engineering
04 — Technical Services & Applications — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want a separate Technical Service for every physical server | Group servers into Technical Services by infrastructure domain. One Technical Service per server defeats the purpose of service-level modelling. | Service impact analysis requires service-level groupings, not CI-level CIs at the top of the hierarchy. Grouping by domain means one incident can correctly flag the Technical Service as degraded without requiring manual correlation across 200 individual server CIs. | 'If we create one Technical Service per server, you'd have hundreds of services to maintain and monitor. What you actually want to know is: is my Windows server infrastructure healthy? That's one Technical Service that covers all your Windows servers — and when one fails, the service health rolls up automatically.' | Only for strategically critical single servers (e.g., a legacy mainframe with no peers). Discuss with Practice Lead.

## ServiceNow Mapping
04 — Technical Services & Applications — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Target Tables
Technical Service CI | cmdb_ci_service_technical | One record per infrastructure domain group.
Application Service CI | cmdb_ci_appl | One record per managed application.
Service Relationship | cmdb_rel_ci | Links: Application Service → Technical Service → Business Service.
2. Relationship Types
Depends on | cmdb_rel_type: Depends on::Used by | Application Service depends on Technical Service.
Hosted on | cmdb_rel_type: Hosted on::Hosts | Application Service hosted on server CI.
Runs on | cmdb_rel_type: Runs on::Runs | Server CI runs on VM Instance CI.