## Instructions
06 — CMDB Governance Baseline
CMDB-CSDM Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Establishes the governance framework for the CMDB: data steward assignments, staleness thresholds, CMDB health KPIs, the review cadence, and the process for adding new CI classes post-MVP. Without a governance baseline, even a well-configured CMDB degrades within 3–6 months of go-live.
Who fills this out | ECS SA drafts the framework with the customer IT Operations Manager. The IT Director approves the KPI targets. Finalised before Sprint 2 ends so governance is in place when Discovery runs continuously.
Sprint window | Sprint 2 Weeks 1–2 (draft) — confirmed by end of Sprint 2
Estimated effort | 2–3 hours (one governance workshop with IT Ops Manager and IT Director)
Related workbooks | 02 CI Class Selection · 05 Service-CI Relationships · Foundation Data Pack — Groups
Success criteria
• | A named data steward is assigned to each in-scope CI class.
• | Staleness thresholds (last_discovered > N days = stale) are defined per CI class.
• | CMDB Health KPI targets are agreed and baselined.
• | A CMDB governance review cadence (monthly recommended) is scheduled and has an owner.
• | The process for requesting new CI classes post-MVP is documented.

## Process Decisions
06 — CMDB Governance Baseline — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What staleness threshold should apply to Discovery-managed CIs? | 30 days for computer and server CIs (Discovery runs at least weekly). 90 days for manually maintained CIs. CIs not updated within the threshold are flagged as stale and should be reviewed for retirement. |  | The OOTB CMDB Health dashboard uses the last_discovered date to calculate staleness. A 30-day threshold for Discovery-managed CIs is standard — it allows for Discovery interruptions without false positives.
2 | Who is the CMDB data steward for each CI class? | Assign a named individual from the IT Ops team to each in-scope CI class. The steward is responsible for reviewing CMDB Health reports monthly and actioning stale or orphaned CIs. |  | Without named stewards, CMDB health reports generate alerts that nobody acts on. The steward role is operational, not technical — it requires 1–2 hours per month per class.
3 | What CMDB Health score targets should we commit to? | Completeness: 85%+ for mandatory attributes on in-scope CI classes. Relationship completeness: 80%+ for in-scope classes. Staleness: <5% of CIs stale at any given time. These are Sprint 2 targets; aim for 90%+ by Sprint 6. |  | These targets are OOTB CMDB Health dashboard metrics. Starting at 85% gives realistic headroom for the first Discovery pass while still requiring a functional CMDB.
4 | How should new CI classes be added after MVP? | Any new CI class must go through a governance request: (1) business case (why is this needed?), (2) data source confirmed (how will it be populated?), (3) named data steward assigned, (4) CMDB impact assessed (does this require new Discovery patterns?). Approved by IT Director or IT Operations Manager. |  | Ad-hoc CI class additions are the primary source of CMDB sprawl. A lightweight governance gate prevents low-value classes from being added without a data source.
5 | What happens to a CI that Discovery cannot find for 90+ days? | Flag for retirement review. The data steward reviews: is the asset still deployed? If yes, investigate why Discovery cannot find it (credential issue, subnet exclusion). If no, retire the CI record. Never auto-delete — always human review first. |  | Auto-deleting CIs creates audit risk and breaks incident history. The OOTB retire workflow preserves the record and its history while removing it from active service impact analysis.

## Dependencies
06 — CMDB Governance Baseline — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | CI Class Selection (Workbook 02) confirmed | Required | ECS SA + Customer | Sprint 1 Wk 2 | Governance applies to agreed CI classes only.
2 | First Discovery run completed | Required | ECS Architect | Sprint 2 Wk 1 | Baseline CMDB Health score requires CI data.
3 | Foundation Data Pack — Groups (data steward groups) loaded | Required | ECS SA | Sprint 0 | Steward assignment groups must exist.
4 | IT Director available for KPI target approval | Required | Customer Project Sponsor | Sprint 2 Wk 2 | KPI targets require business stakeholder sign-off.

## Configuration Data
06 — CMDB Governance Baseline — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Data Steward Assignments
cmdb_ci_computer — Data Steward | [Customer to complete — name and group] | Typically the End User Computing team lead.
cmdb_ci_server — Data Steward | [Customer to complete — name and group] | Typically the Server/Infrastructure team lead.
cmdb_ci_vm_instance — Data Steward | [Customer to complete] | May be the same as server steward if same team manages VMs.
cmdb_ci_appl — Data Steward | [Customer to complete] | Application owners team or ITSM team.
CSDM Service CIs — Data Steward | [Customer to complete] | ITSM Process Owner. Responsible for service record accuracy.
2. Staleness Thresholds
cmdb_ci_computer — staleness threshold | 30 days (Discovery-managed) | CMDB Health flags as stale if last_discovered > 30 days.
cmdb_ci_server — staleness threshold | 30 days (Discovery-managed)
cmdb_ci_vm_instance — staleness threshold | 30 days (Discovery-managed)
cmdb_ci_appl — staleness threshold | 30 days (SGC-managed)
CSDM Service CIs — staleness threshold | 90 days (manually maintained) | Service records do not have a last_discovered date. Review quarterly.
3. CMDB Health KPI Targets
Mandatory attribute completeness (in-scope classes) | 85% by end Sprint 2 / 90%+ by Sprint 6
Relationship completeness (CIs with ≥1 service relationship) | 80% by end Sprint 2 / 90%+ by Sprint 6
Staleness rate (% of CIs stale) | < 5% at any time
Orphaned CI rate (% with no service relationship) | < 5% at any time
4. Governance Review Cadence
CMDB Health review frequency | Monthly | Data stewards review CMDB Health dashboard and action stale/orphaned CIs.
Governance review owner | [Customer to complete — name and role] | IT Operations Manager recommended.
New CI class request process | Business case → data source confirmed → steward assigned → IT Director approval | Document in customer runbook. ECS SA to provide runbook template.
CI retirement review process | Flagged by CMDB Health → steward reviews → retires or investigates Discovery gap | Use OOTB Retire workflow. Do not delete CI records.

## R&R
06 — CMDB Governance Baseline — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Draft CMDB governance framework | R/A | C | ECS SA drafts; customer reviews and confirms ownership commitments.
Assign CI class data stewards | I | R/A | Customer IT Operations Manager assigns stewards.
Configure CMDB Health KPI thresholds in ServiceNow | R/A | I | ECS SA configures CMDB Health dashboard targets.
Obtain IT Director approval of KPI targets | I | R/A | Customer governance step.
Document CI retirement process in customer runbook | R/A | I | ECS SA documents; hands off to IT Ops at end of engagement.
Conduct first monthly CMDB health review (post go-live) | C | R/A | Customer IT Ops runs monthly reviews; ECS advises for first 2 cycles.
Review and action stale CI reports | I | R/A | Customer data stewards action stale CIs monthly.

## Consultant Guide
06 — CMDB Governance Baseline — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Why governance must be in place before go-live
CMDB governance is the unsexy deliverable that determines whether the CMDB is still useful 12 months after go-live. Every engagement that skips this step ends up with a CMDB re-scope engagement 18 months later. Use the governance workshop to get the customer to name specific people (not just roles) who will run the monthly health review. If no name can be attached, the governance framework is aspirational, not operational.
CMDB Health dashboard configuration
Configure the CMDB Health dashboard in Sprint 2 with the agreed KPI targets. Set the staleness rules, mandatory attribute checks, and relationship completeness rules. Schedule the Health Score Calculation job to run daily. Show the customer the dashboard before Sprint 2 ends — they need to see a score, even if it's 70%, to understand what they're managing toward.
The retirement process is critical
The single most common cause of CMDB health degradation after go-live is retired assets that were never retired in ServiceNow. Configure the retirement workflow to be triggered by: (a) the CMDB Health stale CI report, (b) the HAM asset disposition process (if HAM is in scope), and (c) an offboarding checklist item. Three triggers means CIs are retired when any of the three processes runs — reducing the chance of orphaned records.
Handoff preparation
By the end of Sprint 6, the CMDB governance runbook must be handed to the customer IT Ops team. The runbook should cover: how to run the monthly health review, how to action stale CIs, how to request a new CI class, and how to retire a CI. This is not a technical document — write it for the IT Ops Manager who has never configured ServiceNow.

## Adoption vs Re-engineering
06 — CMDB Governance Baseline — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We don't need a formal governance process — our team will just keep it updated | Implement the formal monthly CMDB Health review with named stewards and documented process. | Informal governance works for 2–3 months after go-live when the engagement is fresh. It fails when team members change, when priorities shift, or when Discovery starts finding CIs from a new subnet that nobody remembers to relate to a service. | 'Formal governance doesn't mean bureaucracy — it means a 30-minute monthly meeting where someone looks at the CMDB Health dashboard and actions anything that's red. Without that scheduled touchpoint, CMDB health problems accumulate invisibly until they're large enough to break incident management.' | Only for very small teams (<5 IT staff) with a genuinely stable environment. Still document the informal process.
We want to add CI classes whenever we need them | Implement the CI class governance gate: business case, data source, steward, approval. | Ad-hoc CI class additions without data sources create stub CI records that immediately become stale. The governance gate is 15 minutes of overhead per request — far less than the cleanup cost of an ungoverned CMDB. | 'The governance gate isn't about slowing you down — it's about making sure every CI class you add is actually maintained. The question we ask is simple: how will these CIs stay accurate after we add them? If that question has a clear answer, approval takes minutes.' | The governance gate is non-negotiable. Simplify it for small teams, but never eliminate it.

## ServiceNow Mapping
06 — CMDB Governance Baseline — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. CMDB Health Configuration
CMDB Health dashboard | CMDB > CMDB Health | Configure KPI targets, staleness rules, and mandatory attribute checks here.
Health Score Calculation job | CMDB > Health Calculation Job | Schedule to run daily. Results feed the CMDB Health dashboard.
Staleness rule | CMDB Health > Staleness Rules | Configure per CI class with agreed thresholds from this workbook.
2. CI Lifecycle Management
Retire workflow | CMDB > CI Lifecycle > Retire | OOTB workflow for retiring CIs. Preserves record and history.
operational_status field | cmdb_ci.operational_status | 1=Operational, 2=Non-Operational, 3=Repair in Progress, 6=End of Life, 7=Installed, 8=Retired. Use Retired (8) for decommissioned CIs.