## Instructions
02 — MID Server Configuration
Discovery Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the MID Server deployment plan: server sizing, placement, Windows vs Linux, redundancy, and validation requirements. The MID Server is the single point of failure for Discovery — getting it right in Sprint 1 prevents Discovery failures throughout the engagement.
Who fills this out | ECS Architect designs the MID Server plan; customer Infrastructure team provisions the VM and network access.
Sprint window | Sprint 1 Weeks 1–2 (must be deployed before Sprint 2 Discovery runs)
Estimated effort | 4–8 hours for VM provisioning and MID Server installation/validation
Related workbooks | 01 Discovery Scope · 03 Credential Management
Success criteria
• | MID Server VM is provisioned and meets sizing requirements.
• | MID Server is installed, registered, and validated (green status in ServiceNow).
• | MID Server can reach all in-scope IP ranges from its network position.
• | MID Server has outbound HTTPS access to the ServiceNow instance.
• | Redundant MID Server (or failover plan) is documented.

## Process Decisions
02 — MID Server Configuration — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Windows or Linux MID Server? | Windows MID Server if the environment is predominantly Windows (enables WMI Discovery natively). Linux MID Server for Linux-heavy environments. Use Windows as the default for mixed environments. |  | WMI discovery of Windows servers and workstations requires the MID Server to be on a Windows host with domain access. A Linux MID Server can still discover Windows targets via WMI but requires additional credential configuration.
2 | How many MID Servers are needed? | One MID Server per network segment that is not reachable from a single point. Minimum one for the corporate LAN. Add a second for redundancy if the environment has >500 managed devices. |  | A single MID Server is sufficient for most mid-market environments. Redundancy is a Phase 2 consideration unless the customer has a high-availability requirement.
3 | Where should the MID Server be placed on the network? | On the corporate LAN with visibility to all in-scope subnets. The MID Server must be able to reach target devices on WMI (port 135/445), SSH (port 22), and SNMP (port 161) as applicable. |  | A MID Server that cannot reach target subnets produces no Discovery data. Validate network reachability before the MID Server is installed — not after.
4 | What are the minimum VM sizing requirements? | Minimum: 4 vCPU, 8 GB RAM, 100 GB disk. Recommended for >500 devices: 8 vCPU, 16 GB RAM, 200 GB disk. Run on a dedicated VM — do not co-locate with other workloads. |  | Under-resourced MID Servers are the most common cause of slow or incomplete Discovery runs. The MID Server processes probe results locally before sending to ServiceNow.

## Dependencies
02 — MID Server Configuration — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | VM provisioned per sizing requirements | Required | Customer Infrastructure Lead | Sprint 1 Wk 1 | MID Server software cannot be installed until the VM is ready.
2 | ServiceNow instance URL and MID Server credentials | Required | ECS Architect | Sprint 1 Wk 1 | Required to register the MID Server with the instance.
3 | Network firewall rules allowing MID Server traffic to in-scope subnets | Required | Customer Network Lead | Sprint 1 Wk 1 | Without firewall rules, Discovery probes cannot reach target devices.
4 | Outbound HTTPS (443) from MID Server to ServiceNow instance URL | Required | Customer Network Lead | Sprint 1 Wk 1 | MID Server communicates results to ServiceNow via HTTPS.

## Configuration Data
02 — MID Server Configuration — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. MID Server Specification
MID Server hostname | [Customer to complete]
Operating system | [Windows Server 2019/2022 recommended]
vCPU | [4 minimum / 8 recommended]
RAM (GB) | [8 minimum / 16 recommended]
Disk (GB) | [100 minimum / 200 recommended]
Network location | [Corporate LAN segment with visibility to in-scope subnets]
MID Server service account | [Customer to complete — domain service account] | Requires local admin on MID Server host. Domain admin not required.
Redundant MID Server planned? | [Yes / No / Phase 2]
2. Validation Checklist
MID Server status in ServiceNow | Up (green) | Check Discovery > MID Servers.
Test probe to server subnet — responds | Pass | Run test Discovery against one known server IP.
Test probe to workstation subnet — responds | Pass | Run after server subnet is validated.
Outbound HTTPS to instance confirmed | Pass | MID Server logs show no connection errors.

## R&R
02 — MID Server Configuration — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Provision MID Server VM | C | R/A | Customer Infrastructure Lead provisions the VM.
Install and register MID Server software | R/A | C | ECS Architect installs; customer provides access.
Configure firewall rules for Discovery traffic | C | R/A | Customer Network Lead configures firewall.
Validate MID Server and run test probe | R/A | C | ECS Architect validates; customer IT Ops confirms.

## Consultant Guide
02 — MID Server Configuration — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
MID Server is the critical path item
The MID Server must be deployed and validated before any Discovery configuration begins. If the MID Server is delayed, Sprint 2 Discovery is delayed. Escalate immediately if VM provisioning is not started by Sprint 1 Week 1. This is the most common Sprint 2 delay and it is always caused by late VM provisioning.
Service account permissions
The MID Server service account needs local administrator rights on the MID Server host to install and run as a Windows service. It does NOT need domain admin rights. Many customers confuse these — clarify early to avoid a security team rejection of a 'domain admin request'.

## Adoption vs Re-engineering
02 — MID Server Configuration — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to use an existing server rather than provisioning a new VM | Provision a dedicated VM. Do not co-locate the MID Server with production workloads. | Co-located MID Servers compete for CPU and memory during Discovery runs, causing both Discovery and the host workload to perform poorly. A dedicated VM is the OOTB recommendation and is required for supportability. | 'The MID Server has CPU and memory spikes during Discovery runs. If it is sharing a host with your SQL Server, both services will be impacted during those spikes. A dedicated VM costs almost nothing in a virtualised environment and eliminates the risk.' | Never co-locate. If resource constraints are severe, reduce MID Server sizing rather than co-locating.

## ServiceNow Mapping
02 — MID Server Configuration — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. MID Server Management
MID Server record | ecc_agent | Registered MID Servers appear here.
MID Server status | Discovery > MID Servers | Must show 'Up' before Discovery schedules run.
MID Server logs | ECC Queue > Output (filter by MID Server) | Review for connection errors after installation.