## Instructions
04 — Search Configuration
Employee Center Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Employee Center unified search configuration: which content types are indexed, search result ranking, and the 'No results' experience. EC search is the primary way most employees find what they need — it must search across catalog items, KB articles, and EC topics simultaneously.
Who fills this out | ECS SA configures; customer ITSM PO validates search results for the top 10 expected queries.
Sprint window | Sprint 5 Week 2
Estimated effort | 2 hours
Related workbooks | 02 Topic Taxonomy · Knowledge Pack — Search Optimization
Success criteria
• | EC search indexes: catalog items, KB articles, EC topics.
• | Top 10 expected search queries return relevant results.
• | No results experience includes a 'Submit a request' fallback.
• | Search analytics reporting is configured.

## Process Decisions
04 — Search Configuration — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What content types should EC search return? | OOTB EC search returns: catalog items (sc_cat_item), knowledge articles (kb_knowledge), and EC topics (sn_hr_sp_topic). All three are indexed by default. Do not restrict search to a single content type. |  | Restricting EC search to catalog items only means users who search for a knowledge article get no results and call the helpdesk. The three-content-type search is the OOTB design and handles the full user journey.
2 | What should the 'No results found' experience show? | OOTB: 'No results found' page includes a prominent 'Submit a request' button that opens the General Requests catalog item. Configure this before go-live — it converts search failures into catalog submissions rather than helpdesk calls. |  | Every search that returns no results is a user who is about to call the helpdesk. The OOTB no-results fallback to 'Submit a request' captures that intent in the catalog instead.

## Dependencies
04 — Search Configuration — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | EC topics configured (Workbook 02) | Required | ECS SA | Sprint 5 Wk 1
2 | KB articles published (Knowledge Pack) | Required | Customer KMs | Sprint 5 Wk 2 | Search returns no KB results until articles are published.

## Configuration Data
04 — Search Configuration — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Search Source Configuration
Catalog items indexed | Yes — OOTB sc_cat_item search source
Knowledge articles indexed | Yes — OOTB kb_knowledge search source
EC topics indexed | Yes — OOTB sn_hr_sp_topic search source
Search result ranking | OOTB: catalog items rank above KB for transactional queries; KB ranks above catalog for informational queries | No configuration needed — OOTB ranking algorithm.
No-results fallback | OOTB 'No results' page with Submit a Request CTA | Configure CTA to open General Requests catalog item.
2. Search Validation Queries (top 10)
Query 1 | [Customer: most common helpdesk request type] | Expected result: catalog item
Query 2 | [Customer: second most common request]
Query 3 | [Customer: common password/access issue] | Expected result: KB article or catalog item
Queries 4–10 | [Customer ITSM PO to provide remaining 7 queries] | Validate all 10 before go-live.

## R&R
04 — Search Configuration — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure EC search sources | R/A | I | ECS SA.
Configure no-results fallback | R/A | I | ECS SA.
Provide top 10 test search queries | I | R/A | Customer ITSM PO.
Validate search results for all 10 queries | R/A | C | ECS SA tests; customer confirms results are correct.
Configure search analytics reporting | R/A | I | ECS SA.

## Consultant Guide
04 — Search Configuration — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Post-launch search analytics
Configure OOTB EC search analytics before go-live. The first 30 days of search analytics are the most valuable dataset in the engagement: what users search for, what results they click, and where they give up. This data drives: (1) synonym additions to the KB search, (2) new catalog item prioritisation, and (3) VA topic additions. Review search analytics at the Sprint 6 planning session.

## Adoption vs Re-engineering
04 — Search Configuration — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to exclude KB articles from EC search so users only see catalog items | Keep all three content types in EC search. | Excluding KB from EC search forces users who could self-serve with a knowledge article to submit a catalog request instead — increasing fulfillment workload for no benefit. | 'If a user searches for how to reset their password and we only show catalog items, they submit a request. If we also show the KB article, they self-serve in 2 minutes and the helpdesk doesn't get the ticket. Every KB article that surfaces in search is a potential deflection.' | Never restrict EC search to a single content type.

## ServiceNow Mapping
04 — Search Configuration — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Search Configuration
EC Search Source | sp_search_source | Configured per content type in Service Portal > Search Sources.
Search Analytics | Employee Center > Administration > Search Analytics | OOTB analytics for EC searches — what users searched, what they clicked.