## Instructions
04 — Initial Inventory
HAM Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Seed inventory the customer wants in ServiceNow at MVP. Every row becomes one alm_hardware record. The goal is real, accountable data — not exhaustive coverage. A small, accurate inventory is more valuable than a large, stale one.
Who fills this out | Customer-side: IT Operations / Stockroom Lead, with the HAM Process Owner reviewing reconciliation rules. ECS-side: Solution Architect validates references and runs the import.
When it's due | Process Decisions Week 1 of Sprint 0; Data tab populated by end of Sprint 0, Week 2. Depends on workbooks 01 (Stockrooms), 03 (Models), and 05 (Lifecycle States).
How long it takes | Approximately 4–8 hours of data entry per 500 assets, plus 2 hours of reconciliation discussion.
Where the data comes from | Existing CMDB exports, procurement spreadsheets, Discovery output (if available), SCCM/Intune exports, current ITAM tool exports (Snipe-IT, ManageEngine, etc.).
How to use this workbook | Decide reconciliation policy in Process Decisions before populating Data. The biggest cost of HAM Foundations is bad seed data — make decisions about authoritative sources before importing one row.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
Dependencies | Other Packs and source data that must be in place before this workbook can be imported.
Configuration Data | Final OOTB-aligned configuration parameters used by ECS to configure ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership for each activity.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant.
Adoption vs Re-engineering | Pushback scenarios when the customer asks for legacy patterns; OOTB defense language.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.

## Process Decisions
Initial Inventory — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Authoritative source for serial numbers — manufacturer, SCCM, or manual entry? | SCCM/Intune for endpoints when available; manufacturer scan for new receipts; manual only for legacy gear with no Discovery. |  | Drives Realization Pack reconciliation rules.
2 | Asset tag generation — reuse existing tags or regenerate? | Reuse existing physical asset tags. Regeneration breaks the tag-to-device link in audit trail. |  | Critical: never regenerate tags.
3 | Devices in user hands but not yet tagged — what to do? | Generate tags via Number Maintenance and provide print sheets. Customer's IT Ops physically tags during next-touch (refresh, return, repair).
4 | Devices found in Discovery but not in the seed inventory — handle automatically? | Hold for manual reconciliation in Sprint 1. Auto-create deferred to Realization Pack workbook 07 Audits & Reconciliation.
5 | Inventory completeness target at MVP? | 80% of assets currently in user hands plus 100% of receiving stockroom. 100% coverage is a Realization goal. |  | Real, accountable 80% > inflated, stale 100%.
6 | Devices loaned out / on customer sites — track? | Yes, with stockroom = In-Transit-<region>. assigned_to = the loanee user.
7 | Decommissioned but not yet disposed — track? | Yes, state = Retired, stockroom = Pending Disposal. Drives disposal pipeline metrics.
8 | Personal-device registers (BYOD) — include? | No. BYOD has separate compliance scope; not part of corporate HAM.
9 | Acquired_date — required or optional? | Required for warranty tracking. If unknown for legacy assets, set to first-seen date with notes.
10 | Cost / book value — track at Foundations? | Optional. Required for Realization Pack workbook 06 Disposal & Retirement.
11 | Bulk-import format — Excel only, or CSV from existing tool? | CSV from existing tool preferred. ECS provides CSV-to-workbook conversion for one-time migration.
12 | Duplicate handling — by serial, asset_tag, or both? | Serial primary, asset_tag secondary. Both unique.
13 | Devices retired pre-ServiceNow — load historic records? | Defer unless audit requires. If yes, load with state = Retired and acquired_date = best-known.
14 | Reconciliation with Foundation Data Pack Users — strict or permissive? | Strict: every assigned_to_user_id must resolve. Unresolved rows held for fix.

## Dependencies
Initial Inventory — Dependencies
Other Packs and source data that must be in place before this workbook can be imported.
# | Dependency | Status | Owner | Due | Notes
1 | Workbook 01 Stockrooms imported | In Progress | ECS
2 | Workbook 02 Asset Classes finalized | In Progress | Customer
3 | Workbook 03 Asset Models imported | In Progress | ECS
4 | Workbook 05 Lifecycle States configured | Not Started | ECS
5 | Foundation Data Pack — Users imported | Complete | ECS
6 | Existing inventory export delivered to ECS | Not Started | Customer
7 | Reconciliation policy signed off | Not Started | Customer
8 | SCCM/Intune connector live (if endpoints to be reconciled) | Not Started | ECS

## Configuration Data
Initial Inventory — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are example placeholders to confirm in workshop.
Field / Setting | Value | Notes
1. Coverage Targets
Target row count at MVP | ~850 | Across 3 classes; ~80% of in-user assets
Coverage measurement | Reconciled count / known fleet count | Reported in Sprint 1 demo
2. Required Fields per Row
Always required | asset_tag, serial_number, class_name, model_display_name, state | Data Policy on alm_hardware
Required when state = In stock | stockroom_name | Data Policy
Required when state = In use | assigned_to_user_id | Data Policy
Required when state = Retired | stockroom_name = Pending Disposal | Data Policy
3. Reconciliation
Authoritative serial source | SCCM/Intune for endpoints; manual for non-Discovery
Duplicate detection | Coalesce on serial_number | OOTB import set behavior
Unresolved reference handling | Hold for fix — no auto-create
4. Import Strategy
Method | Import Set + Transform Map → alm_hardware
Volume threshold | Batch sizes ≤ 5,000 rows | Larger batches scheduled overnight

## R&R
Initial Inventory — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Reconciliation policy decisions | R | A | ECS facilitates; Customer's HAM Process Owner signs off.
Existing inventory export delivery | I | R | Customer's IT Operations.
Data quality assessment | R | C | ECS profiles delivered data.
Cross-reference validation (users, stockrooms, models) | R | I | ECS runs validation script.
Unresolved-reference reconciliation | C | R | Customer fixes source data.
Asset-tag printing & physical labeling | I | R | Customer's IT Ops; ECS provides tag templates.
Production import | R | A | ECS executes; Customer signs off on count.
Sprint 1 demo: receive → assign → return → retire | R | C | ECS demos; Customer validates.
Post-import drift management | C | R | Customer's HAM Process Owner.

## Consultant Guide
Initial Inventory — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Not for customer distribution.
OOTB alm_hardware Foundations
alm_hardware is the OOTB asset table for all hardware. Each row references model (cmdb_model), stockroom (alm_stockroom), and assigned_to (sys_user). install_status drives lifecycle. CI relationships via cmdb_ci_computer / cmdb_ci_display / cmdb_ci_mobile_device class extensions.
Implementation Sequence
• Profile delivered inventory: row counts per class, % with serial, % with assigned_to, % with stockroom — flag low-quality columns for customer fix.
• Validate references: every model_display_name resolves to cmdb_model; every stockroom_name resolves to alm_stockroom; every assigned_to_user_id resolves to sys_user.
• Run dedup: coalesce on serial_number; flag manufacturer-duplicate rows for customer review.
• Apply state-based Data Policy: hold rows that violate (e.g., 'In use' with no assigned_to).
• Import in batches; validate target row counts after each batch.
• Build initial reconciliation report: ServiceNow vs SCCM vs Intune deltas.
• Smoke test: pick 10 random assets and trace tag → serial → user → stockroom.
• Demo at Sprint 1 review: receive → assign → return → retire on a real asset, end-to-end OOTB.
Common Pitfalls to Avoid
• Importing 'because we have the data' rather than 'because we can vouch for the data' — the validation script catches references but cannot validate accuracy.
• Auto-creating users / stockrooms / models on import — every auto-create is a future drift problem.
• Mixing seed inventory with Discovery feeds in the same import — keep them separate to attribute issues correctly.
• Skipping the Sprint 1 demo on a real asset — the demo proves the OOTB workflow works. If you can't demo it, the inventory isn't usable.
• Treating 100% coverage as the goal — 80% real coverage with a working process beats 100% inflated coverage.

## Adoption vs Re-engineering
Initial Inventory — Adoption vs Re-engineering
When the customer says "but our old tool did X." Use these to defend OOTB before agreeing to customize.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"Bulk-load every device anyone has ever owned, including 5 years of historic." | Active inventory only at MVP. Historic loaded only if audit mandates. | Historic data inflates row counts and degrades search. Sprint 1 demo metrics get noisy. Reconciliation reports become dominated by retired assets. | "What historic reports do you run? If it's audit traces, those are query-time joins on archived data, not active inventory rows. If it's nostalgic, defer." | Mandatory regulated retention (FDA, DoD, certain financial).
"Auto-create users in ServiceNow when seed inventory has unmatched assigned_to." | Hold unmatched rows for customer fix. Users come from Foundation Data Pack 01. | Auto-create silently masks data-quality problems. Every auto-created user becomes a future Active Directory reconciliation failure. | "Foundation Data Pack 01 Users is the source of truth. If a user is missing there, they should be missing here too — and that's the signal to add them at the source." | Never. This is process discipline.
"Just import what we have — we'll fix the data quality later." | Profile first, fix references, then import. | Bad seed data poisons every downstream report and reconciliation. 'Fix later' becomes 'fix never' once the system is live and the team is busy. | "Sprint 1 demo gets the credibility we need to do Realization. If we demo on dirty data, the business sees dirty data. Two days of cleanup before import buys six months of trust." | Never.
"Custom u_legacy_id field to keep our old asset IDs visible alongside the new asset_tag." | Optional. If included, u_legacy_id is an opaque identifier — never used for new processes. | Legacy IDs are a transition aid, not a long-term tracking field. They become permanent if exposed in OOTB UI. | "Add u_legacy_id as a hidden field for audit-trail purposes. Don't expose it on the asset form — agents use asset_tag." | Audit retention requires legacy ID continuity for 7+ years.
"Track every PSU, dock, hub, and cable that goes with the laptop." | Bundles tracked as Consumables (alm_consumable), not individual hardware. Realization Pack workbook 02. | Per-cable hardware records create 5–10× the rows with no ITAM signal. Bundles are stockroom-tracked at receipt and issue. | "Consumables handle the cable + dock + PSU bundle. Individual cable tracking is rarely worth the effort. Realization workbook 02 sets up the consumable pattern." | High-value docks ($300+) issued as a serialized accessory.

## ServiceNow Mapping
Initial Inventory — ServiceNow Mapping
Internal reference — target tables, OOTB features used, and import behavior.
Primary table(s) | alm_hardware (with class extensions: cmdb_ci_computer, cmdb_ci_display, cmdb_ci_mobile_device)
Field mapping
Workbook column | ServiceNow field | Notes
asset_tag | asset_tag | Unique. Auto-generated for new; reused for existing.
serial_number | serial_number | Coalesce key. Unique.
class_name | model_category (via model) | Reference resolved through cmdb_model.
model_display_name | model | Reference to cmdb_model.
stockroom_name | stockroom | Reference to alm_stockroom.
assigned_to_user_id | assigned_to | Reference to sys_user.
state | install_status | Choice list defined in workbook 05.
acquired_date | acquired | ISO date.
warranty_end | warranty_expiration | ISO date.
notes | u_notes | Free text.
Validation & import notes
• Coalesce on serial_number; missing serial flagged for review.
• Validation runs before transform: reference resolution, state-based required fields, asset_tag format.
• Batch size 5,000 max for synchronous import; larger batches scheduled overnight.
• Smoke test mandatory: 10 random rows traced end-to-end after each import.