## Instructions
04 — Intune Service Graph Connector
Integration Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | This workbook captures the requirements, dependencies, configuration data, and roles & responsibilities for integrating Microsoft Intune with ServiceNow via the Service Graph Connector (SGC) for Intune. Intune covers cloud-managed devices (mobile devices, modern Windows endpoints under Intune management) — complementing SCCM coverage for traditional Windows clients and providing visibility into mobile and BYOD scenarios.
Who fills this out | Customer-side: Intune administrator, plus the device management lead. ECS-side: the Solution Architect on your engagement.
When it's due | By the end of Sprint 0, Week 2 for connection details; the full Intune SGC build typically completes in Sprint 1.
How long it takes | Approximately 4–6 hours over Sprints 0 and 1, including app registration creation, MID server validation, and initial test imports.
Where the data comes from | Intune administrator for tenant details, app registration, and Microsoft Graph API access; existing ServiceNow CMDB content (if porting); CSDM 5.0 Reference Model.
How to use this workbook | Same flow as the SCCM workbook (03). Intune integration is conceptually similar but uses Microsoft Graph API instead of SQL JDBC, so the dependencies and credentials differ.
Tabs in this workbook
Requirements | What the integration must do — device classes, scope, schedule.
Dependencies | Prerequisites: app registration, Graph API permissions, MID server.
Configuration Data | Tenant ID, app registration, sync schedules, scope filters.
R&R | RACI matrix — ECS vs Customer ownership.
Developer Notes | Reference for the ECS Solution Architect / Senior Developer.
Port from Legacy | How to migrate your existing Intune integration.
ServiceNow Mapping | Internal reference — target tables and SGC architecture.
Common pitfalls
• | App registration without admin consent for required Graph API permissions — silent failure on sync.
• | Client secret expiration not tracked — sync silently breaks when secret rotates.
• | Importing every Intune device class (including stale BYOD enrollments) — better to scope by device platform and management state.
• | Conflict with SCCM SGC for co-managed devices — devices managed by both SCCM and Intune may appear twice unless IRE precedence is configured.
• | Sync schedule too aggressive — Microsoft Graph API has rate limits; runaway syncs can throttle the entire Graph API tenant.
Frequently Asked Questions
Q: | Do we need both SCCM SGC and Intune SGC?
A: | Often yes. SCCM = traditional Windows client management; Intune = cloud-managed Windows, macOS, iOS, Android. Co-managed devices appear in both — IRE rules determine precedence.
Q: | How do we handle BYOD devices?
A: | Intune-managed BYOD devices appear in the import. Decide in Requirements tab whether to include them, exclude them, or import with a different CI class.
Q: | What about Apple devices managed via Apple Business Manager?
A: | Intune SGC covers them when they're enrolled in Intune. ABM-only enrollment without Intune is out of scope (no Microsoft Graph visibility).
Q: | How long does the initial Intune sync take?
A: | Depends on device count. 5K devices = roughly 15–30 min on first import; throttled by Graph API rate limits.
Who to ask | Your engagement's ECS Solution Architect.

## Requirements
Intune SGC — Integration Requirements
Customer fills the Answer column. Use the Notes column for context, exceptions, or deferred questions.
# | Requirement Question | Answer | Notes
1 | Approximately how many Intune-managed devices? | 5,200 devices: 3,800 Windows, 900 iOS, 400 macOS, 100 Android
2 | Which device platforms are in scope? (Windows, macOS, iOS, Android) | All four
3 | Which Intune device categories are out of scope? | BYOD personal devices; lab devices; retired devices not yet purged
4 | Should co-managed devices (managed by both SCCM and Intune) be tracked separately or merged? | Merged — Intune is authoritative for mobile attributes; SCCM is authoritative for hardware inventory
5 | What is the desired sync frequency for devices? | Every 12 hours
6 | Should installed apps be imported (mobile app inventory)? | Yes — for SAM visibility
7 | Are there specific Intune compliance policies that should map to ServiceNow? | Yes — compliance status (Compliant/Non-compliant/Grace) maps to u_ fields
8 | How should Intune-managed devices that lose enrollment appear? | Set inactive immediately; do not delete
9 | Are there any Intune custom attributes or extension attributes to import? | Yes — extensionAttribute1 (ownership), extensionAttribute2 (assignment_type)
10 | Compliance constraints on device data (PII, MDM-restricted attributes)? | Standard PII handling; geolocation NOT to be imported

## Dependencies
Intune SGC — Dependencies & Prerequisites
Every item must be confirmed before integration build can begin. Customer-owned items in green; ECS-owned items in blue.
# | Dependency | Status | Owner | Due | Notes
1 | App registration created in Entra ID for ServiceNow Intune SGC | Not Started | Customer
2 | Required Microsoft Graph permissions granted with admin consent | Not Started | Customer
3 | App registration client secret created and rotation date documented | Not Started | Customer
4 | Client secret vaulted in ServiceNow Credential store | Not Started | ECS
5 | Tenant ID, client ID, secret reference documented in Configuration Data tab | Not Started | Customer
6 | MID server with internet access to graph.microsoft.com (port 443) | Complete | ECS
7 | Service Graph Connector for Intune installed (from Store) | Not Started | ECS
8 | CSDM 5.0 reference model loaded into ServiceNow | Complete | ECS
9 | Sample query against Microsoft Graph API verified | Not Started | ECS
10 | Co-management approach decided (if SCCM SGC also in scope) | In Progress | Customer

## Configuration Data
Intune SGC — Configuration Data
Customer fills the Value column. The yellow-shaded examples illustrate the expected format.
Field | Value | Notes
1. Microsoft Graph Connection
Entra ID tenant ID | 12345678-1234-1234-1234-123456789012 | From Entra ID > Properties
App registration client ID | abcdef12-3456-7890-abcd-ef1234567890 | Created in App registrations
App registration client secret reference | [ECS will populate] | Vaulted in ServiceNow Credential store
Required Graph API permissions (Application) | DeviceManagementManagedDevices.Read.All, DeviceManagementApps.Read.All, DeviceManagementConfiguration.Read.All | Admin consent required
Client secret rotation date | 2027-05-01 | Track for renewal
2. MID Server
MID server | midserver-prod-01.yourorg.com | Same MID can serve multiple integrations
Internet egress to graph.microsoft.com confirmed | Yes
3. Service Graph Connector for Intune
SGC application version | 2.5 (latest from ServiceNow Store)
Sync schedule — Devices | Every 12 hours
Sync schedule — Apps | Daily at 04:00 ET
Initial backfill timing | Off-hours; expect 30–60 min for ~5K devices
4. Scope and Filters
Device platforms in scope | Windows, macOS, iOS, Android
Device categories EXCLUDED | BYOD-Personal; Lab; Retired
Compliance attributes to import | complianceState, lastSyncDateTime, isEncrypted, jailBroken
Custom attributes to import | extensionAttribute1 (ownership), extensionAttribute2 (assignment_type)
5. Co-Management (if SCCM SGC in scope)
Co-management precedence | Intune authoritative for mobile attributes; SCCM authoritative for hardware inventory | Drives IRE rule design
Conflict resolution approach | Auto-merge using IRE; flag conflicts for review
6. Orphan Handling
Stale device threshold (days) | 60 | Longer than SCCM since mobile devices may be off-grid for extended periods
Auto-delete orphaned devices? | No | Inactive flag only; manual review for deletion

## R&R
Intune SGC — Roles & Responsibilities
RACI-style: R = Responsible (does the work), A = Accountable (signs off), C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
App registration creation in Entra ID | C | R | Customer's IAM team owns; ECS specifies required permissions.
Granting Microsoft Graph permissions with admin consent | C | R | Requires admin approval — Customer's identity admin executes.
Client secret creation and vaulting | R | R | Customer creates secret in app reg; ECS vaults in ServiceNow.
Client secret rotation tracking | I | R | Customer tracks IdP-side rotation; ECS provides SOP for ServiceNow update.
Service Graph Connector for Intune installation | R | I | ECS-managed.
CSDM model alignment for Intune-discovered classes | R | C | ECS designs OOTB-aligned mapping.
Initial test sync against sub-prod CMDB | R | C | ECS executes; Customer validates samples.
Co-management precedence design (if SCCM also in scope) | R | C | ECS designs IRE rules; Customer confirms business intent.
Production sync activation | R | A | ECS executes; Customer signs off.
Long-term ownership of Intune SGC operations | I | R | Customer's CMDB / endpoint team owns post-Hypercare.

## Developer Notes
Intune SGC — Developer Notes
Internal reference for the ECS Solution Architect / Senior Developer building the integration. Not customer-facing.
OOTB-First Approach
Use the Service Graph Connector for Intune (from ServiceNow Store). Microsoft Graph API queries are handled OOTB; the connector manages pagination, throttling, and error handling. Custom Microsoft Graph queries via Script Includes should be avoided — they break with Graph API versioning and add maintenance burden.
Implementation Pattern
• Customer creates App Registration in Entra ID with the required Graph application permissions.
• Customer grants admin consent for the permissions.
• Install SGC for Intune from ServiceNow Store.
• Configure Connection alias with tenant ID, client ID, vaulted client secret.
• Validate connection via 'Test Connection'.
• Run 'Initial Setup' — auto-discovers device classes and standard mappings.
• Adjust class mappings to align with CSDM 5.0.
• Configure scheduled imports per requirements (devices, apps).
• If co-management with SCCM is in scope, configure IRE precedence rules per device class to determine authoritative source per attribute.
• Run initial backfill in sub-prod; validate sample of records.
• Configure stale device policy.
Common Pitfalls to Avoid
• Custom Graph API queries via Script Include — bypasses SGC pagination and throttling, leads to rate-limit errors.
• Not granting admin consent on permissions — silent failure on sync.
• Configuring sync frequency too aggressive — Graph API rate limits will throttle the entire tenant; respect documented limits.
• Not configuring IRE precedence with SCCM SGC — co-managed devices appear duplicated or attributes flip-flop.
• Importing extensionAttributes that aren't actually populated — creates noise; verify population before import.
• Hard-coding client secret in connection record instead of using credential vault — broken practice and security risk.
Validation Checklist
• Connection test passes from MID server to graph.microsoft.com.
• Initial test import populates expected number of devices (within 5% of Intune count).
• Sample devices match Intune portal data: device name, OS, model, last sync, compliance state.
• Mobile app inventory populates expected counts.
• Co-managed devices show single CI record with attributes from authoritative source per IRE rules.
• Subsequent incremental syncs complete in under 30 minutes.
• Stale device policy correctly flags devices not seen in 60 days.
References
• ServiceNow Docs: Service Graph Connector for Intune
• Microsoft Docs: Microsoft Graph permissions reference
• ECS Practice Library: Intune SGC Pattern Library (internal)

## Port from Legacy
Intune SGC — Port from Legacy Instance
Used when porting an existing integration from your domain-separated instance to the new OOTB-aligned instance.
Porting Approach
Legacy Intune integrations are typically less customized than SCCM (Intune is newer; many enterprises don't yet have a deeply-customized integration). Where they exist, they often consist of custom Microsoft Graph queries via Script Include, custom transform maps to legacy CI classes, and Business Rules that fire on imported devices. The porting approach is to abandon the custom Graph integration and rebuild using the Intune SGC; review custom u_ fields and Business Rules against business need.
Step-by-Step Porting Process
1. Inventory legacy Intune-related integration: data sources, import sets, transform maps, scheduled jobs, custom Graph queries.
2. List custom CI extensions to OOTB classes (custom u_ fields on cmdb_ci_computer or cmdb_ci_mobile_device).
3. List custom Business Rules on imported records.
4. List custom Script Includes for Graph API access.
5. Categorize each item against the OOTB SGC pattern.
6. Document each disposition.
7. Build the new instance using OOTB Intune SGC. Do NOT port the legacy custom Graph integration.
8. Custom u_ fields with documented business need carry forward in the new instance.
9. Custom Business Rules are reviewed individually — most can be replaced by OOTB IRE rules.
Legacy Configuration Inventory
Customer fills this in by exporting from the legacy instance and categorizing each item.
Configuration Item / Component | Disposition | Notes / Rationale
Legacy custom Graph script 'IntuneGraphSync' Script Include | Rebuild OOTB | Replaced by OOTB SGC for Intune.
Legacy data source 'Intune Devices' | Retire | OOTB SGC handles this.
Legacy transform map 'Intune → cmdb_ci_mobile_device' | Retire | OOTB SGC transform replaces.
Custom u_field 'u_intune_compliance_state' on cmdb_ci_computer | Port As-Is | Actively used; OOTB SGC populates.
Custom u_field 'u_byod_owner' on cmdb_ci_mobile_device | Port with Modifications | Sourced from extensionAttribute1 in new design.
Custom Business Rule 'Set device retired on Intune unenrollment' | Port with Modifications | Logic preserved but reimplemented as OOTB Discovery rule.
Custom Business Rule 'Auto-tag BYOD devices' | Retire | Now handled by Intune categories + OOTB SGC.
Custom IRE precedence between SCCM and legacy Intune | Rebuild OOTB | Reconfigure with new SCCM SGC + Intune SGC architecture.
Disposition Legend
Port As-Is | Configuration aligns with OOTB; can be transferred directly with minor adjustments for the new instance.
Port with Modifications | Configuration is mostly OOTB-aligned but needs adjustments to fit CSDM 5.0 or current best practices.
Rebuild OOTB | Configuration is custom or workaround; will be rebuilt against the OOTB pattern in the new instance.
Retire | Configuration is no longer needed; will not be carried forward.
PCR Required | Configuration is genuinely needed but goes outside OOTB envelope; requires Project Change Request.
Defer to Phase 2 | Not in Phase 1 scope; documented in backlog for later phase.

## ServiceNow Mapping
ServiceNow Import Mapping (for ECS Solution Architect reference)
Imports to: cmdb_ci_computer (Windows, macOS), cmdb_ci_mobile_device (iOS, Android), cmdb_sam_sw_install (mobile apps). Configuration: Service Graph Connector for Intune application (from ServiceNow Store). Connection uses Microsoft Graph API via the IntegrationHub Microsoft connector framework. Credentials in sys_credential. IRE precedence rules in cmdb_metadata coordinate co-management with SCCM SGC.