## Instructions
03 -- Dashboard Design & Layout
Performance Analytics Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Document the widget layout, audience, and refresh settings for each OOTB PA dashboard activated at go-live.
Who fills this out | ECS Consultant configures OOTB layouts. Dashboard owners review and approve during UAT.
Sprint window | Sprint 6 -- dashboards configured and approved by Week 12
Estimated effort | 4-5 hours including widget configuration and owner UAT
Related workbooks | 01 PA Scope · 02 Indicator Library
Success criteria
• | All three OOTB dashboards configured with correct widgets.
• | Each dashboard owner has approved the layout.
• | Dashboards accessible to correct roles (Viewer for owners).
• | Sharing settings confirmed (individual vs. group access).

## Process Decisions
03 -- Dashboard Design & Layout — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should dashboards be shared with specific users or roles? | Share with roles (IT Director role, Service Desk Manager role). Do not share to all users. |  | Role-based sharing ensures dashboards reach the right audience as the organization grows. User-level sharing requires manual updates when people change roles.
2 | Should executive dashboard include a traffic light summary? | Yes -- OOTB PA supports a KPI summary widget with green/yellow/red status. Include it as the first widget on the executive dashboard. |  | Traffic light summary gives the IT Director a 5-second health check without reading all charts. It is the highest-value widget on the executive dashboard.
3 | Should dashboards be set as homepage for dashboard owners? | Recommend setting the relevant PA dashboard as homepage for each named owner. |  | Homepage setting ensures the dashboard is the first thing owners see on login -- maximizing the chance they review it daily.

## Dependencies
03 -- Dashboard Design & Layout — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | OOTB indicators active (WB2) | Required | ECS | Sprint 6 Wk 1 | Dashboard widgets require active indicators.
2 | Dashboard owners named (WB1) | Required | Customer | Sprint 6 Wk 1 | Cannot configure sharing without named owners.
3 | PA Viewer roles granted | Required | ECS | Sprint 6 Wk 1 | Owners need PA Viewer role to access dashboards.

## Configuration Data
03 -- Dashboard Design & Layout — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. ITSM Executive Overview -- Widget Layout
Widget 1: SLA Compliance Traffic Light | KPI summary -- green/yellow/red for SLA compliance | Position: top left, full width. OOTB pa_kpi_summary widget
Widget 2: Incident Volume Trend (30 days) | Line chart -- daily incident volume | Position: left column. OOTB pa_chart widget
Widget 3: Open Incidents by Priority | Bar chart -- P1/P2/P3/P4 open count | Position: right column. OOTB pa_chart widget
Widget 4: MTTR Trend (30 days) | Line chart -- average resolution time daily | Position: bottom left. OOTB pa_chart widget
Widget 5: SLA Compliance % (30 days) | Line chart -- daily SLA compliance % | Position: bottom right. OOTB pa_chart widget
2. Incident Management Dashboard -- Widget Layout
Widget 1: Open Backlog Scorecard | Single number -- current open incidents | OOTB pa_scorecard widget
Widget 2: Incidents by Assignment Group | Bar chart -- volume and backlog by group | OOTB pa_breakdown widget
Widget 3: First Call Resolution Rate | Gauge -- FCR % vs. 70% target | OOTB pa_gauge widget
Widget 4: Reassignment Rate Trend | Line chart -- average reassignments per incident | OOTB pa_chart widget
Widget 5: MTTR by Category | Bar chart -- resolution time by incident category | OOTB pa_breakdown widget
3. Service Desk Performance -- Widget Layout
Widget 1: Agent Workload Distribution | Bar chart -- open incidents per agent | OOTB pa_breakdown widget
Widget 2: Incidents Resolved Today | Single number scorecard | OOTB pa_scorecard widget
Widget 3: FCR Rate by Agent | Table -- FCR % per agent for current week | OOTB pa_breakdown widget
Widget 4: Volume vs. Capacity Trend | Line chart -- daily volume vs. team average handle capacity | OOTB pa_chart widget
4. Access & Sharing
ITSM Executive Overview -- shared to | IT Director role (itil_admin or custom IT Director role) | Customer to confirm role name
Incident Management -- shared to | IT Manager role | Customer to confirm role name
Service Desk Performance -- shared to | Service Desk Manager role | Customer to confirm role name
Set as homepage | Recommend for all three named owners | Customer owners confirm preference

## R&R
03 -- Dashboard Design & Layout — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure OOTB widget layout for each dashboard | R/A | I | ECS Consultant.
Configure sharing and role assignments | R/A | Provide role names | ECS configures; Customer confirms roles.
Dashboard owner UAT | R (facilitate) | A (approve) | ECS facilitates; each owner approves their dashboard.
Set homepage for dashboard owners | R/A | Confirm preference | ECS sets with owner consent.

## Consultant Guide
03 -- Dashboard Design & Layout — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Layout simplicity rule
Each OOTB dashboard should have 4-6 widgets maximum. More widgets = cognitive overload = dashboard is ignored. The rule is: every widget must answer a question the owner asks at least weekly. If they cannot name the question, remove the widget.
UAT with owners
Sit with each dashboard owner for 30 minutes. Walk through their dashboard and ask: 'What question does each widget answer?' If they struggle, simplify. Dashboards that owners understand are dashboards they use. Dashboards that impress but confuse are dashboards that get abandoned.
Traffic light widget
The traffic light (KPI summary) widget is the most impactful single widget on the executive dashboard. It converts a complex dashboard into a 3-second health check. Always lead with it. The IT Director will see it on homepage load and know immediately if ITSM is healthy.

## Adoption vs Re-engineering
03 -- Dashboard Design & Layout — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Add 15 widgets to the executive dashboard to show everything | 4-6 widgets maximum; curate relentlessly. | 15 widgets on a single dashboard produces scroll fatigue and information overload. IT Directors stop reviewing overpacked dashboards within 2 weeks. | We curate these dashboards based on one principle: what does the IT Director look at first thing Monday morning? That is the dashboard. Everything else is available in OOTB Reports for drill-down. Five focused widgets that answer five important questions will be used every day. Fifteen widgets that try to show everything will be ignored by week 3. | Never -- widget discipline is a governance principle, not a constraint.

## ServiceNow Mapping
03 -- Dashboard Design & Layout — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Dashboard Widgets
pa_dashboard | Dashboard container record | pa_dashboard
pa_widget | Individual widget on a dashboard -- chart, scorecard, KPI summary | pa_widget
pa_chart_widget | Chart widget -- line, bar, gauge types | pa_chart_widget
pa_scorecard_widget | Single-number scorecard widget | pa_scorecard_widget