## Instructions
01 -- PI Scope & Readiness Decisions
Predictive Intelligence Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Confirm which OOTB Predictive Intelligence models to activate, verify training data volume requirements, and establish the sprint sequence for model training and go-live.
Who fills this out | ECS Architect leads. Customer IT Manager and Service Desk Lead provide data volume confirmation.
Sprint window | Sprint 4 -- decisions complete by end of Week 8
Estimated effort | 2-3 hours with Customer IT Manager
Related workbooks | 02 Category Classification · 03 Similar Incident · 04 Assignment Intelligence · AP-12 Discovery · AP-CAT Service Catalog
Success criteria
• | PI models in scope confirmed (category, similar incident, assignment).
• | Training data volume verified (1,000+ incidents minimum for classification).
• | Existing category/subcategory structure confirmed stable before PI activation.
• | Customer named PI Admin for ongoing model management.
• | Model retraining cadence agreed (weekly OOTB default).

## Process Decisions
01 -- PI Scope & Readiness Decisions — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which PI models should be activated at go-live? | All three OOTB models: Category Classification, Similar Incident, and Assignment Intelligence. |  | All three ship OOTB with Now Platform. They share the same training pipeline. Activating all three in Sprint 4 maximizes AI realization value. Defer 'Predictive Fields' (additional custom fields) to Phase 2.
2 | How much historical incident data is required? | Minimum 1,000 closed incidents with category and assignment group populated. Target 5,000+ for reliable accuracy. |  | ServiceNow's ML engine requires sufficient training examples per class. Below 1,000 records, accuracy is too low for production use. Customer must confirm data volume before Sprint 4 model training begins.
3 | Should PI be activated before or after catalog normalization? | After catalog normalization (AP-CAT). Category and subcategory values must be stable before PI trains on them. |  | PI Category Classification trains on the current category taxonomy. If categories change after training, the model predictions become unreliable. Finalize the category structure first.
4 | How often should models retrain? | Weekly retraining (OOTB default schedule). Do not increase to daily -- excessive retraining adds compute load without accuracy improvement. |  | Weekly captures new incidents at an appropriate pace. Models stabilize after 4-6 weeks of weekly retraining cycles.
5 | Should PI suggestions be auto-applied or agent-reviewed? | Agent-reviewed at go-live. Auto-apply is Phase 2 after accuracy exceeds 80% for 30 consecutive days. |  | OOTB supports both modes. Starting with suggestions (not auto-apply) builds agent trust and surfaces accuracy issues safely.

## Dependencies
01 -- PI Scope & Readiness Decisions — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | 1,000+ closed incidents with populated category and assignment | Required | Customer | Before Sprint 4 training | PI model cannot be trained without sufficient historical data.
2 | Stable category/subcategory taxonomy (AP-CAT) | Required | ECS | Sprint 3 close | Categories must not change after PI model training begins.
3 | Assignment groups fully populated in ServiceNow | Required | Customer | Sprint 2 close | Assignment Intelligence needs populated group records to predict correctly.
4 | Now Platform licensed for PI (Intelligent Experiences) | Required | Customer | Before Sprint 4 | PI is licensed separately. Customer must confirm entitlement.

## Configuration Data
01 -- PI Scope & Readiness Decisions — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. PI Model Activation
Category Classification model | Activate -- Sprint 4 Week 1 | Predicts incident category and subcategory from short description
Similar Incident model | Activate -- Sprint 4 Week 1 | Surfaces related past incidents to reduce resolution time
Assignment Intelligence model | Activate -- Sprint 4 Week 2 | Predicts assignment group from category and short description
Predictive Fields (additional) | Defer to Phase 2 | Custom field prediction requires additional configuration scope
2. Training Data Thresholds
Minimum incidents for training | 1,000 closed incidents | Below this threshold PI accuracy is unreliable
Target incidents for high accuracy | 5,000+ closed incidents | Customer to confirm count before Sprint 4 kickoff
Minimum examples per category | 50 incidents per category/subcategory | Categories with fewer examples will have low prediction confidence
Retraining schedule | Weekly (OOTB default -- every Sunday at midnight) | Do not change retraining frequency in 18-week scope
3. Suggestion Mode
Initial mode at go-live | Suggest only -- agent must confirm before applying | Build agent trust before enabling auto-apply
Auto-apply threshold | 80% model accuracy for 30 consecutive days | Customer PI Admin and ECS review before enabling
Confidence threshold for display | 0.70 (OOTB default) | Suggestions below 0.70 confidence are suppressed from agent view

## R&R
01 -- PI Scope & Readiness Decisions — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Confirm PI license entitlement | I | R/A | Customer IT Director.
Confirm historical incident data volume | I | R/A | Customer Service Desk Lead.
Activate PI models in ServiceNow | R/A | I | ECS Architect.
Monitor model accuracy post-activation | R | A | ECS monitors first 4 weeks; Customer PI Admin takes over.
Approve auto-apply threshold (Phase 2) | R (advise) | A (decide) | Customer IT Director decides with ECS recommendation.

## Consultant Guide
01 -- PI Scope & Readiness Decisions — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Data quality gate
Before activating PI, run a data quality check: query incidents for null category, null assignment_group, and null short_description. If more than 20% of training records have null categories, PI accuracy will be poor. Work with the customer to backfill or exclude dirty records from the training set.
Category stability rule
PI Category Classification is extremely sensitive to taxonomy changes. If the customer changes categories after training, the model will predict old categories that no longer exist. Enforce a category freeze before Sprint 4 training. Document any planned future category changes as Phase 2.
Agent trust-building
The biggest risk to PI adoption is agents ignoring suggestions because the first few are wrong. Coach the Service Desk Lead to frame PI as a 'second opinion, not an order.' After 4 weeks, pull the suggestion acceptance rate from PI Analytics. If below 40%, schedule an accuracy review.
Confidence threshold calibration
If agents report too many irrelevant suggestions, raise the confidence threshold to 0.80 in PI Solution settings. If agents report that PI is too silent (few suggestions), lower to 0.65. Do not go below 0.60 -- below this threshold suggestions are essentially random.

## Adoption vs Re-engineering
01 -- PI Scope & Readiness Decisions — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want PI to auto-assign tickets without agent review | Suggest mode at go-live; auto-apply after accuracy validated. | Auto-apply without validated accuracy creates mis-routed tickets that damage help desk trust in the AI platform. | Auto-assignment is the goal -- we just need to earn it. Starting with suggestions lets agents correct wrong predictions, which improves the model faster. Once accuracy holds above 80% for a month, we enable auto-apply and the agents get the full benefit without the routing risk. | After 30 consecutive days at 80%+ accuracy.
Train PI on our custom fields, not just category | OOTB category, subcategory, and assignment group at go-live. Custom fields in Phase 2. | Custom field prediction requires creating additional PI Solutions -- each adds configuration scope. OOTB fields cover the highest-value predictions. | Custom field prediction is absolutely on the roadmap -- it is a Phase 2 item once the baseline models are proven. Adding custom fields to the training set before the baseline is stable would make it harder to diagnose accuracy issues. | Phase 2 -- after baseline models exceed 80% acceptance rate.

## ServiceNow Mapping
01 -- PI Scope & Readiness Decisions — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. PI Core Tables
ml_solution | PI Solution record -- one per active model (category, similar, assignment) | ml_solution
ml_capability | Capability record linking PI solution to a table (incident) | ml_capability
ml_input_output | Defines input fields (short_description) and output fields (category) for each model | ml_input_output
2. Agent Experience
Incident form PI widget | OOTB widget on Incident form showing PI suggestions inline | incident (form layout)
PI Analytics dashboard | OOTB -- model accuracy, acceptance rate, suggestion volume | ml_analytics