## Instructions
02 — Catalog Item Inventory & Triage
Service Catalog Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Creates a complete inventory of all catalog items from the legacy system or current state, and applies a Keep / Simplify / Retire triage decision to each. The triage output defines the Sprint 4 build scope and prevents the catalog from launching with legacy clutter that reduces self-service adoption.
Who fills this out | Customer-side: ITSM Process Owner leads the triage, with input from fulfillment team leads for each category. ECS SA facilitates and applies the OOTB-first lens. Target: complete the triage in one 2-hour workshop plus customer review time.
Sprint window | Sprint 3 Week 2 — Sprint 4 Week 1
Estimated effort | 2–4 hours workshop + 1–2 hours customer review. Scale with item count.
Related workbooks | 01 Category Rationalization · 03 Item Template Standards · 04 Fulfillment Workflow Decisions
Success criteria
• | Every legacy catalog item has a Keep / Simplify / Retire decision.
• | Items marked 'Keep' or 'Simplify' are mapped to the new category structure from Workbook 01.
• | The Sprint 4 build list (Keep + Simplify items) contains no more than 15 items.
• | Items marked 'Retire' have a recorded rationale for the project record.
• | Every item in the build list has an identified fulfillment owner group.

## Process Decisions
02 — Catalog Item Inventory & Triage — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | How many catalog items should we launch with at go-live? | 10–15 items for the Sprint 4 MVP. Target the highest-volume requests (top 10 by incident/request volume in the last 12 months) plus any items with regulatory or compliance significance. |  | Customers who try to launch 50+ catalog items in a single sprint typically deliver half of them with poor variable design and broken fulfillment workflows. 10–15 well-built items drive more self-service adoption than 50 partially-built items.
2 | What is the triage criterion for 'Retire'? | Retire an item if: (a) it has had fewer than 5 requests in the last 12 months, (b) it duplicates another item, (c) it represents a process that should be an incident rather than a request, or (d) the fulfillment process no longer exists. |  | Legacy catalogs typically contain 20–30% items that have never been used or are duplicates. Retiring them reduces maintenance overhead and makes the catalog more browsable.
3 | What does 'Simplify' mean in the triage context? | Simplify means: rebuild the item using the OOTB item template (Workbook 03) with a reduced variable set (5 variables or fewer at MVP), standardised fulfillment workflow, and OOTB approval logic. Do not carry over legacy custom variables or complex logic. |  | Legacy catalog items often have 15–20 variables that were added ad-hoc over years. Most are never read by the fulfillment team. Simplify forces the question: which variables actually change what we do?
4 | How should we handle items that require integrations to third-party systems (e.g., AD, SCCM)? | Flag these as 'Sprint 6 items' in the triage. Build the basic catalog item structure in Sprint 4; add the integration trigger in Sprint 6 after the Integration Accelerator Pack is complete. |  | Building integration-dependent catalog items before integrations are validated creates rework. The catalog item structure is independent of the integration — build the form first, add the automation later.
5 | What do we do with catalog items that are really just incident types? | Retire the catalog item. Create an Incident category/subcategory for the equivalent Incident type. Catalog requests are for predictable, fulfillable requests with defined completion criteria. Incident types are for unknown or urgent issues. |  | Confusion between incidents and requests is the most common catalog design anti-pattern. A 'report a broken printer' catalog item is an incident, not a request. The catalog should contain requests — things a user predictably needs IT to provide.

## Dependencies
02 — Catalog Item Inventory & Triage — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Category Rationalization (Workbook 01) approved | Required | Customer ITSM Owner | Sprint 3 Wk 2 | Items cannot be triaged to new categories until the category structure is confirmed.
2 | Legacy catalog item list (with request volume data if available) | Required | Customer ITSM Owner | Sprint 3 Wk 2 | Volume data is the primary triage criterion for Keep vs Retire decisions.
3 | Fulfillment team leads available for triage workshop | Required | Customer IT Ops | Sprint 3 Wk 2 | Fulfillment owners know which items are actually used and which are obsolete.
4 | Request volume report (last 12 months) from legacy system | Recommended | Customer ITSM Owner | Sprint 3 Wk 2 | Objective usage data prevents subjective 'we might need it' arguments for keeping low-value items.

## Configuration Data
02 — Catalog Item Inventory & Triage — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Triage Decision Fields (one row per legacy catalog item)
Legacy Item Name | [Customer to complete] | Name as it appears in the current system.
Legacy Category | [Customer to complete] | Category in the current system.
Request Volume (last 12 months) | [Customer to complete] | Number of requests submitted. Use 0 if unknown.
Triage Decision | [Keep / Simplify / Retire] | Keep = build as-is with OOTB template. Simplify = rebuild with reduced variables. Retire = decommission.
New Category (from Workbook 01) | [Customer to complete if Keep/Simplify] | Map to the new category structure.
Fulfillment Group | [Customer to complete if Keep/Simplify] | The group that fulfills this item.
Retire Rationale (if Retire) | [Customer to complete] | Record why this item is being retired for the project record.
Sprint Target | [Sprint 4 / Sprint 6 / Phase 2] | Sprint 4 = MVP build. Sprint 6 = integration-dependent items. Phase 2 = deferred.
Notes / Special Requirements | [Customer to complete] | Flag items with integration dependencies, approvals, or regulatory requirements.

## R&R
02 — Catalog Item Inventory & Triage — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Provide legacy catalog item list with volume data | I | R/A | Customer ITSM Owner prepares the source list.
Facilitate triage workshop | R/A | C | ECS SA facilitates; customer makes the Keep/Simplify/Retire decisions.
Apply OOTB-first lens to Simplify decisions | R/A | C | ECS SA advises on what simplification means for each item; customer approves.
Confirm fulfillment group for each Keep/Simplify item | I | R/A | Customer fulfillment team leads confirm ownership.
Document Retire rationale | R/A | C | ECS SA records rationale; customer confirms.
Approve final Sprint 4 build list | I | R/A | Customer ITSM Process Owner approves before Sprint 4 configuration begins.

## Consultant Guide
02 — Catalog Item Inventory & Triage — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Triage workshop facilitation
The triage workshop works best as a fast-paced decision session. Project the legacy item list, go row by row, and ask three questions for each: (1) How many times was this requested in the last year? (2) If we didn't have this item, what would the user do instead? (3) Who fulfills it and do they still exist? These three questions resolve 80% of triage decisions in under 2 minutes per item. Reserve the full discussion time for borderline items.
The 15-item MVP discipline
The hardest conversation is holding the Sprint 4 scope to 15 items when the customer has 80 legacy items. The framing: 'We're not retiring these items permanently — we're deferring them to Sprint 6 or Phase 2. The 15 highest-value items go live in Sprint 4 with clean design and working fulfillment. The next 15 go live in Sprint 6, better because we learned from the first build. Items 30+ go into Phase 2 with full design time.' This makes the 15-item limit feel like a quality decision, not a cut.
Incidents masquerading as catalog items
Every legacy catalog typically contains 10–20% items that are really incident types: 'My email isn't working', 'I can't access a shared drive', 'My computer is slow'. These should be retired as catalog items and replaced with Incident categories. The test: if the fulfillment team's job is to investigate what's wrong rather than provide a known deliverable, it's an Incident, not a Request.

## Adoption vs Re-engineering
02 — Catalog Item Inventory & Triage — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We need to launch all 80 legacy catalog items on day one | Launch 10–15 MVP items in Sprint 4. Deliver the next set in Sprint 6. Phase 2 covers the remainder. | 80 catalog items built in one sprint produces 80 items with inconsistent variable design, untested fulfillment workflows, and no adoption measurement. 15 well-built items produce measurable self-service adoption that justifies the Phase 2 build. | 'We're not cutting items — we're sequencing them. The 15 items we build in Sprint 4 will be built correctly, with tested fulfillment and clean forms. Then we measure adoption and use that data to prioritise the next 15. You'll end up with a better catalog faster than if we try to do everything at once.' | Never launch all legacy items without triage. If the customer has a hard business requirement (e.g., regulatory) for specific items, those move to the Sprint 4 list regardless of volume.

## ServiceNow Mapping
02 — Catalog Item Inventory & Triage — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Catalog Item Tables
sc_cat_item | Catalog Item | Main catalog item table. One record per item.
item_option_new | Catalog Item Variable | Variables (form fields) on a catalog item.
sc_request | Service Request | Parent record created when a user submits a catalog request.
sc_req_item | Requested Item (RITM) | One RITM per catalog item in a request. Fulfillment tracks at RITM level.
2. Key Item Fields
name | Display name — what the user sees
category | Reference to sc_category | Set from the new category structure (Workbook 01).
fulfillment_group | Default assignment group for fulfillment
delivery_time | Expected fulfillment duration (days) | Used in SLA calculation if SLA is applied to RITM.
active | true = visible to users | Set false for items in triage/review.