## Instructions
04 — VA Analytics & Adoption Measurement
Virtual Agent Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Define KPIs, OOTB dashboards, and review cadence for measuring Virtual Agent containment and adoption post-go-live.
Who fills this out | ECS Consultant configures OOTB dashboards in Sprint 6. Customer VA Admin owns ongoing reporting after go-live.
Sprint window | Sprint 6 — KPI baseline set at go-live; 30/60/90-day targets defined here
Estimated effort | 2 hours for dashboard activation and KPI baseline setup
Related workbooks | 01 VA Scope & Channel Decisions · 02 Topic Design & NLU Intent Library · 05 Go-Live Readiness
Success criteria
• | OOTB VA Analytics dashboard accessible to Customer VA Admin at go-live.
• | Containment rate baseline established on Day 1.
• | 30/60/90-day KPI targets agreed with Customer PM.
• | Weekly unhandled intent review cadence established.
• | 30-day review meeting scheduled before go-live.

## Process Decisions
04 — VA Analytics & Adoption Measurement — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What is the primary KPI for Virtual Agent success? | Containment rate — percentage of sessions resolved without live-agent handoff. |  | OOTB VA Analytics tracks containment natively. It is the single most meaningful measure of VA effectiveness.
2 | What are realistic containment targets? | 15% at 30 days; 30% at 90 days. |  | 15% is realistic for a 6-topic MVP. 30% at 90 days is achievable with utterance tuning and 2-3 Phase 2 topics added. Overpromising creates stakeholder risk.
3 | How often should VA analytics be reviewed? | Weekly for first 90 days (Customer VA Admin); 30/60/90-day reviews with ECS. |  | Weekly cadence catches NLU quality issues before they compound. ECS reviews at 30/60/90 days to assess Phase 2 topic candidates.
4 | Should custom Performance Analytics indicators be built? | No — use OOTB VA Analytics for the entire 18-week scope. |  | OOTB VA Analytics provides containment, handoff rate, session volume, and unhandled intents. Custom PA indicators add configuration scope not warranted in Sprint 6.
5 | What triggers a Phase 2 topic build? | A single unhandled intent concept exceeding 20 sessions per week for 2 consecutive weeks. |  | Data-driven threshold. Prevents guessing about what topics to add next.

## Dependencies
04 — VA Analytics & Adoption Measurement — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Now Assist VA Analytics entitlement | Required | Customer | Before Sprint 6 | Confirm Now Assist Analytics module is included in license before go-live.
2 | Go-live date confirmed | Required | Customer PM | Sprint 6 Wk 1 | KPI clock starts on Day 1 of production launch. Baseline date must be recorded.
3 | Customer VA Admin identified and trained | Required | Customer | Sprint 6 | Admin must know how to pull OOTB analytics reports before handover.

## Configuration Data
04 — VA Analytics & Adoption Measurement — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. KPI Targets
Primary KPI | Containment rate (% sessions resolved without handoff) | OOTB VA Analytics tracks natively
Secondary KPI | Average session duration (minutes) | High duration = low NLU confidence — investigate if >5 min avg
Tertiary KPI | Unhandled intent volume — top 5 weekly | Phase 2 topic backlog source
Target — 30 days | 15% containment | Based on 6-topic MVP go-live set with 10-20 utterances
Target — 60 days | 22% containment | With utterance tuning post-30-day review
Target — 90 days | 30% containment | With utterance tuning + 2-3 Phase 2 topics
2. Review Cadence
Weekly review (Customer) | VA Admin pulls OOTB top-5 unhandled intents report every Monday | Customer VA Admin owns — no ECS involvement in weekly pull
30-day review | ECS + Customer PM + VA Admin — containment vs. 15% target; Phase 2 topic candidates | ECS schedules before Sprint 6 close
60-day review | Customer PM + VA Admin — adjust utterances; confirm Phase 2 topic builds started | Customer-led; ECS advisory only
90-day review | ECS + Customer PM — Phase 2 assessment; stabilization sign-off | Marks end of ECS hypercare obligations
High-handoff alert | >70% handoff rate in any week triggers ECS review call | ECS + Customer VA Admin troubleshoot NLU coverage
3. Dashboard Access
OOTB dashboard location | Now Assist > Virtual Agent Analytics | No custom PA indicators — OOTB only for 18-week scope
Access role required | sn_va_analyst (OOTB) | Customer VA Admin must have this role before go-live

## R&R
04 — VA Analytics & Adoption Measurement — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Activate VA Analytics dashboard | R/A | Verify access | ECS activates; Customer VA Admin confirms visibility.
Record go-live baseline date | R | A | ECS records; Customer PM confirms.
Pull weekly unhandled intent report | N/A | R/A | Customer VA Admin owns weekly pull.
30-day containment review | R | A | ECS presents analysis; Customer PM decides Phase 2 scope.
Phase 2 topic prioritization | I (advise) | R/A (decide) | Customer decides with ECS input from unhandled intent data.
Ongoing monthly reporting (post-90 days) | N/A | R/A | Customer VA Admin owns post-stabilization.

## Consultant Guide
04 — VA Analytics & Adoption Measurement — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Why 15% at 30 days is right
A 6-topic VA with 10-20 utterances each will not cover the full vocabulary of a user base at launch. 15% is a credible, achievable target. Setting it at 30% or higher on day 1 creates stakeholder risk when the inevitable dip in week 2 (as novelty fades) occurs. Under-promise, over-deliver.
Utterance tuning lever
The fastest way to improve containment after go-live is to add utterances from the weekly unhandled intent report. Coach the Customer VA Admin to identify the top 3 unhandled phrasing variants each week and add them as utterances to the relevant topic. This alone can move containment 5-10 points between 30 and 90 days.
Phase 2 topic trigger discipline
The 20-sessions/2-weeks threshold prevents the customer from adding topics based on gut feel or a single complaint. Data-driven topic expansion is the OOTB pattern. When a threshold is crossed, add it to the Phase 2 backlog -- not necessarily to the current sprint.
Redirect PA requests
Customers with existing PA deployments will ask for VA PA indicators. Redirect to OOTB VA Analytics for the 90-day stabilization period. PA indicator configuration adds a sprint of work. The OOTB dashboard is sufficient to prove or disprove containment at the scale of an 18-week engagement.

## Adoption vs Re-engineering
04 — VA Analytics & Adoption Measurement — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
The 30% target is too low -- we expect 60% by month 3 | 15% at 30 days; 30% at 90 days -- industry-aligned for a 6-topic OOTB deployment. | Containment scales with topic count and utterance quality. A 6-topic set cannot reliably contain 60% of diverse IT requests at 90 days. | A 30% containment rate means 30% of employees resolve their issue without calling the help desk -- that is hundreds of saved tickets per month for a 1,000-person organization. The OOTB pattern is to land at 30% and grow to 50%+ over 6-12 months as the topic library expands. We deliver the foundation; Phase 2 delivers the scale. | When topic library exceeds 15 and utterance coverage is validated across all topics.
We need a custom PA scorecard for VA | OOTB VA Analytics covers all 18-week reporting needs. | Custom PA indicators add sprint scope and are not needed until baseline is established at 90 days. | The OOTB VA Analytics dashboard shows everything you need to manage VA health: containment rate, handoff rate, top topics, and unhandled intents. Once you have 90 days of baseline data, we can design a PA scorecard in Phase 2 grounded in real patterns rather than assumptions. | Phase 2 -- after 90-day stabilization baseline established.

## ServiceNow Mapping
04 — VA Analytics & Adoption Measurement — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. VA Analytics
VA Analytics dashboard | OOTB Now Assist module -- containment, handoff, session volume, top topics, unhandled intents | sn_va_analytics
Conversation log | Raw session data -- queryable for custom reporting post-go-live | va_conversation_log
VA Analyst role | sn_va_analyst -- grants access to VA Analytics dashboard | sys_user_role
2. Phase 2 Reference
Performance Analytics indicators (Phase 2) | Custom KPI indicators for executive scorecard -- out of scope for 18-week | pa_indicator, pa_scorecard