## Project Plan
ECS FEDERAL · CONNECTION — SERVICENOW OOTB REIMPLEMENTATION · 18-WEEK PROJECT PLAN (PHASE 1)
CN-PP-01 · Connection · ECS Team + Customer · Set Project Start Date (B3) to the Sprint 0 Monday — all dates recalculate
Project Start Date: | 2025-09-01 | ← Change this date; all task dates recalculate automatically
LEGEND: Phase Header (dark navy) ¦ Task Row (white/alt) ¦ ✦ Milestone (gold) ¦ Recurring Governance (teal) ¦ Predecessors = Task IDs in column A
ID | WBS | Phase | Sprint | Task Name | Duration (Days) | Start Date | Finish Date | Predecessors | ECS Primary | ECS Support | Customer Primary | Customer Support | Status | % Complete | Notes / Deliverables
1 | 0 | Stage 1 — Initiate & Plan | Sprint 0 | SPRINT 0 — ENGAGEMENT SETUP | 10 | 2025-09-01 | 2025-09-12 |  | EM | SA, PC | Sponsor, CustPM |  | Not Started | 0% | Weeks 1–2. All setup activities to ensure team and environment are ready for Sprint 1.
2 | 0.1 | Stage 1 — Initiate & Plan | Sprint 0 | Internal ECS kickoff — SOW review & consultant assignment | 1 | 2025-09-01 | 2025-09-01 |  | EM | PM |  |  | Not Started | 0% | Review SOW scope, confirm consultant roles, load sprint tooling and templates.
3 | 0.2 | Stage 1 — Initiate & Plan | Sprint 0 | Contract & SOW finalization (customer signature) | 1 | 2025-09-01 | 2025-09-01 |  | EM |  | Sponsor | CustPM | Not Started | 0% | Confirm signed SOW before Sprint 1 commitment.
4 | 0.3 | Stage 1 — Initiate & Plan | Sprint 0 | Customer kickoff meeting | 1 | 2025-09-02 | 2025-09-02 | 2,3 | EM, SA | PC | Sponsor, CustPM | TechLead | Not Started | 0% | Introductions, engagement overview, 18-week journey walk-through, Q&A.
5 | 0.4 | Stage 1 — Initiate & Plan | Sprint 0 | Environment provisioning — dev / test / prod instances | 3 | 2025-09-02 | 2025-09-04 | 4 | SA, TC |  | TechLead |  | Not Started | 0% | ServiceNow instance request, MID server setup, network access.
6 | 0.5 | Stage 1 — Initiate & Plan | Sprint 0 | Access & credentials setup (admin, consultant, test accounts) | 2 | 2025-09-02 | 2025-09-03 | 4 | TC | SA | TechLead |  | Not Started | 0% | ECS consultant accounts, customer admin accounts, SSO config baseline.
7 | 0.6 | Stage 1 — Initiate & Plan | Sprint 0 | Governance & decision rights workshop | 1 | 2025-09-03 | 2025-09-03 | 4 | EM, PC |  | Sponsor, CustPM | TechLead | Not Started | 0% | Establish customization council, RACI, escalation path, decision log.
8 | 0.7 | Stage 1 — Initiate & Plan | Sprint 0 | Customization Council charter signed | 1 | 2025-09-04 | 2025-09-04 | 7 | EM |  | Sponsor |  | Not Started | 0% | Council charter defines quorum, meeting cadence, and veto rights for any scope deviation.
9 | 0.8 | Stage 1 — Initiate & Plan | Sprint 0 | Communication plan & cadence established | 1 | 2025-09-03 | 2025-09-03 | 4 | EM |  | CustPM |  | Not Started | 0% | Weekly status report schedule, bi-weekly sponsor sync, sprint demo invites.
10 | 0.9 | Stage 1 — Initiate & Plan | Sprint 0 | Risk register initialized | 1 | 2025-09-04 | 2025-09-04 | 4 | EM, PC |  | CustPM |  | Not Started | 0% | Populate with known risks: data readiness, SME availability, environment delays.
11 | 0.10 | Stage 1 — Initiate & Plan | Sprint 0 | Foundation Data Pack distributed to customer | 1 | 2025-09-05 | 2025-09-05 | 4 | PC |  | CustPM | SME-ITSM | Not Started | 0% | AP-01 workbooks: users, locations, departments, groups, assignment rules, SLAs, schedules.
12 | 0.11 | Stage 1 — Initiate & Plan | Sprint 0 | Stakeholder mapping completed | 1 | 2025-09-05 | 2025-09-05 | 4 | EM |  | CustPM | Sponsor | Not Started | 0% | Identify all SMEs, decision owners, and change champions per process area.
13 | 0.12 | Stage 1 — Initiate & Plan | Sprint 0 | Sprint 0 readiness validation (ECS checklist) | 1 | 2025-09-12 | 2025-09-12 | 5,6,7,8,9,10,11,12 | EM | SA | CustPM |  | Not Started | 0% | Confirm: env provisioned, access live, governance signed, data pack distributed, risks logged.
14 | 0.M | Stage 1 — Initiate & Plan | Sprint 0 | ✦ MILESTONE: Sprint 0 Complete — Ready to Build | — | 2025-09-12 | 2025-09-12 | 13 |  |  |  |  | Not Started | 0%
15 | 1 | Stage 1 — Initiate & Plan | Sprint 1 | SPRINT 1 — PLATFORM FOUNDATION & ITSM DESIGN | 10 | 2025-09-15 | 2025-09-26 |  | SA, PC | EM | CustPM, TechLead | SME-ITSM | Not Started | 0% | Weeks 3–4. Platform stand-up, CSDM, and ITSM design workshops.
16 | 1.1 | Stage 1 — Initiate & Plan | Sprint 1 | Sprint 1 planning session | 1 | 2025-09-15 | 2025-09-15 | 14 | EM, SA | PC, TC | CustPM |  | Not Started | 0% | Story review, sprint backlog confirmation, acceptance criteria.
17 | 1.2 | Stage 1 — Initiate & Plan | Sprint 1 | Platform architecture stand-up & baseline configuration | 3 | 2025-09-15 | 2025-09-17 | 16,5 | SA, TC |  | TechLead |  | Not Started | 0% | CMDB scope settings, update sets, source control, MID server validation.
18 | 1.3 | Stage 1 — Initiate & Plan | Sprint 1 | CSDM definition workshop | 2 | 2025-09-15 | 2025-09-16 | 16 | SA, PC |  | CustPM, TechLead | SME-ITSM | Not Started | 0% | Map customer services, apps, and CIs to CSDM layers. Define service taxonomy.
19 | 1.4 | Stage 1 — Initiate & Plan | Sprint 1 | CSDM validation against ServiceNow data model | 2 | 2025-09-17 | 2025-09-18 | 18 | SA | TC | TechLead |  | Not Started | 0% | Validate service-CI relationships; confirm Business Service and Technical Service scope.
20 | 1.5 | Stage 1 — Initiate & Plan | Sprint 1 | ITSM design workshop — Incident Management | 1 | 2025-09-15 | 2025-09-15 | 16 | PC | SA | SME-ITSM | CustPM | Not Started | 0% | State model, categorization, priority matrix, routing logic, SLA tiers.
21 | 1.6 | Stage 1 — Initiate & Plan | Sprint 1 | ITSM design workshop — Problem Management | 1 | 2025-09-16 | 2025-09-16 | 20 | PC | SA | SME-ITSM |  | Not Started | 0% | Problem identification triggers, investigation workflow, known error base.
22 | 1.7 | Stage 1 — Initiate & Plan | Sprint 1 | ITSM design workshop — Request Management | 1 | 2025-09-17 | 2025-09-17 | 21 | PC | SA | SME-ITSM | SME-Catalog | Not Started | 0% | Request types, fulfillment model, approval tiers, SLA targets.
23 | 1.8 | Stage 1 — Initiate & Plan | Sprint 1 | Foundation Data Pack review — users, groups, locations | 2 | 2025-09-18 | 2025-09-19 | 11 | PC | TC | SME-ITSM | TechLead | Not Started | 0% | Review customer-returned workbooks; identify gaps before Sprint 3 config.
24 | 1.9 | Stage 1 — Initiate & Plan | Sprint 1 | Assignment rules & SLA design review | 1 | 2025-09-19 | 2025-09-19 | 23 | PC | SA | SME-ITSM |  | Not Started | 0% | Confirm assignment group structure, SLA definitions, and escalation schedules.
25 | 1.10 | Stage 1 — Initiate & Plan | Sprint 1 | Sprint 1 demo | 1 | 2025-09-25 | 2025-09-25 | 17,19,24 | SA, PC | EM | Sponsor, CustPM | TechLead, SME-ITSM | Not Started | 0% | Demo: platform baseline, CSDM service map, design decision recap.
26 | 1.11 | Stage 1 — Initiate & Plan | Sprint 1 | Sprint 1 retro | 1 | 2025-09-26 | 2025-09-26 | 25 | EM | SA, PC | CustPM |  | Not Started | 0% | Velocity, blockers, action items. Update risk register.
27 | 1.M | Stage 1 — Initiate & Plan | Sprint 1 | ✦ MILESTONE: Sprint 1 Complete | — | 2025-09-26 | 2025-09-26 | 26 |  |  |  |  | Not Started | 0%
28 | 2 | Stage 1 — Initiate & Plan | Sprint 2 | SPRINT 2 — DISCOVERY & CMDB FOUNDATION | 10 | 2025-09-29 | 2025-10-10 |  | SA, TC | PC | TechLead | SME-ITSM | Not Started | 0% | Weeks 5–6. Discovery tooling, Service Graph Connectors, CMDB normalization, catalog scope.
29 | 2.1 | Stage 1 — Initiate & Plan | Sprint 2 | Sprint 2 planning session | 1 | 2025-09-29 | 2025-09-29 | 27 | EM, SA | PC, TC | CustPM |  | Not Started | 0%
30 | 2.2 | Stage 1 — Initiate & Plan | Sprint 2 | Discovery tool installation & network scan configuration | 3 | 2025-09-29 | 2025-10-01 | 29 | TC | SA | TechLead |  | Not Started | 0% | Discovery schedules, credentials, network range scoping.
31 | 2.3 | Stage 1 — Initiate & Plan | Sprint 2 | Service Graph Connectors — SCCM / Intune porting | 4 | 2025-09-29 | 2025-10-02 | 29 | TC | SA | TechLead |  | Not Started | 0% | Port connectors from prior system; validate CI population in CMDB.
32 | 2.4 | Stage 1 — Initiate & Plan | Sprint 2 | CMDB normalization — scope & approach workshop | 1 | 2025-09-29 | 2025-09-29 | 29 | SA, PC |  | TechLead | CustPM | Not Started | 0% | Agree CI classes in scope, normalization rules, rogue CI cleanup approach.
33 | 2.5 | Stage 1 — Initiate & Plan | Sprint 2 | CI class selection workshop | 1 | 2025-09-30 | 2025-09-30 | 32,19 | SA | PC | TechLead | SME-ITSM | Not Started | 0% | Select Server, Network, Application CI classes; confirm relationship types.
34 | 2.6 | Stage 1 — Initiate & Plan | Sprint 2 | Initial CMDB data load & relationship validation | 3 | 2025-10-01 | 2025-10-03 | 33 | TC | SA | TechLead |  | Not Started | 0% | Load SCCM/Intune data; validate CI counts, duplicates, relationship integrity.
35 | 2.7 | Stage 1 — Initiate & Plan | Sprint 2 | Service catalog — category structure design workshop | 1 | 2025-09-29 | 2025-09-29 | 29 | PC | SA | SME-Catalog | CustPM | Not Started | 0% | Rationalize legacy categories; target ≤15 top-level categories OOTB.
36 | 2.8 | Stage 1 — Initiate & Plan | Sprint 2 | Service catalog — item inventory & prioritization | 2 | 2025-09-30 | 2025-10-01 | 35 | PC |  | SME-Catalog |  | Not Started | 0% | Inventory existing items; prioritize 13–15 for Sprint 4/6 build.
37 | 2.9 | Stage 1 — Initiate & Plan | Sprint 2 | Sprint 2 demo | 1 | 2025-10-09 | 2025-10-09 | 30,31,34,36 | SA, TC | EM | Sponsor, CustPM | TechLead | Not Started | 0% | Demo: Discovery scan, CMDB CIs, Service Graph connector results, catalog scope.
38 | 2.10 | Stage 1 — Initiate & Plan | Sprint 2 | Sprint 2 retro | 1 | 2025-10-10 | 2025-10-10 | 37 | EM | SA, PC | CustPM |  | Not Started | 0%
39 | 2.M | Stage 1 — Initiate & Plan | Sprint 2 | ✦ MILESTONE: Sprint 2 Complete — Foundation Data in System | — | 2025-10-10 | 2025-10-10 | 38 |  |  |  |  | Not Started | 0%
40 | 3 | Stage 2 — Execute | Sprint 3 | SPRINT 3 — ITSM CORE BUILD | 10 | 2025-10-13 | 2025-10-24 |  | PC, TC | SA | SME-ITSM | TechLead | Not Started | 0% | Weeks 7–8. Configure Incident, Major Incident, Problem, Request, SLAs, assignments, approvals.
41 | 3.1 | Stage 2 — Execute | Sprint 3 | Sprint 3 planning session | 1 | 2025-10-13 | 2025-10-13 | 39 | EM, SA | PC, TC | CustPM |  | Not Started | 0%
42 | 3.2 | Stage 2 — Execute | Sprint 3 | Incident Management — OOTB configuration | 3 | 2025-10-13 | 2025-10-15 | 41,20 | PC, TC | SA | SME-ITSM |  | Not Started | 0% | State model, categories, assignment rules, VIP handling, OOTB form layout.
43 | 3.3 | Stage 2 — Execute | Sprint 3 | Major Incident Management configuration | 2 | 2025-10-16 | 2025-10-17 | 42 | PC, TC |  | SME-ITSM |  | Not Started | 0% | P1/P2 bridge triggers, comms templates, bridge workspace, MIM role.
44 | 3.4 | Stage 2 — Execute | Sprint 3 | Problem Management configuration | 2 | 2025-10-13 | 2025-10-14 | 41,21 | PC, TC |  | SME-ITSM |  | Not Started | 0% | Problem creation triggers, investigation/RCA workflow, known error publishing.
45 | 3.5 | Stage 2 — Execute | Sprint 3 | Request Management configuration (RITM + catalog flow) | 2 | 2025-10-13 | 2025-10-14 | 41,22 | PC, TC |  | SME-ITSM | SME-Catalog | Not Started | 0% | RITM state model, task assignment, approval workflow, SLA.
46 | 3.6 | Stage 2 — Execute | Sprint 3 | SLA configuration & testing | 2 | 2025-10-15 | 2025-10-16 | 42,24 | PC, TC |  | SME-ITSM |  | Not Started | 0% | P1–P4 SLA definitions, schedule attachments, breach notifications, pause conditions.
47 | 3.7 | Stage 2 — Execute | Sprint 3 | Assignment rules configuration | 2 | 2025-10-15 | 2025-10-16 | 42,24 | PC, TC |  | SME-ITSM | TechLead | Not Started | 0% | OOTB assignment rules, group rotation, overflow rules.
48 | 3.8 | Stage 2 — Execute | Sprint 3 | Approval workflow configuration | 2 | 2025-10-17 | 2025-10-20 | 45 | PC, TC |  | SME-ITSM |  | Not Started | 0% | Approval groups, delegate rules, auto-approval thresholds, OOTB approval engine.
49 | 3.9 | Stage 2 — Execute | Sprint 3 | Notifications configuration | 1 | 2025-10-21 | 2025-10-21 | 42,44,45 | TC | PC | SME-ITSM |  | Not Started | 0% | OOTB notification templates for Incident, Problem, Request state changes.
50 | 3.10 | Stage 2 — Execute | Sprint 3 | Sprint 3 demo — ITSM Core | 1 | 2025-10-23 | 2025-10-23 | 43,44,45,46,47,48,49 | PC, TC | EM | Sponsor, CustPM | SME-ITSM | Not Started | 0% | Live demo of Incident lifecycle, Problem investigation, Request fulfillment.
51 | 3.11 | Stage 2 — Execute | Sprint 3 | Sprint 3 retro | 1 | 2025-10-24 | 2025-10-24 | 50 | EM | PC | CustPM |  | Not Started | 0%
52 | 3.M | Stage 2 — Execute | Sprint 3 | ✦ MILESTONE: Sprint 3 Complete — ITSM Core Configured | — | 2025-10-24 | 2025-10-24 | 51 |  |  |  |  | Not Started | 0%
53 | 4 | Stage 2 — Execute | Sprint 4 | SPRINT 4 — CHANGE / CAB & SERVICE CATALOG BUILD | 10 | 2025-10-27 | 2025-11-07 |  | PC, TC | SA | SME-ITSM, SME-Catalog | CustPM | Not Started | 0% | Weeks 9–10. Change/CAB OOTB build, catalog items batch 1 & 2, Employee Center baseline.
54 | 4.1 | Stage 2 — Execute | Sprint 4 | Sprint 4 planning session | 1 | 2025-10-27 | 2025-10-27 | 52 | EM, SA | PC, TC | CustPM |  | Not Started | 0%
55 | 4.2 | Stage 2 — Execute | Sprint 4 | Change Management — OOTB configuration | 3 | 2025-10-27 | 2025-10-29 | 54 | PC, TC | SA | SME-ITSM |  | Not Started | 0% | Normal/Standard/Emergency change types, CAB schedule, risk assessment, OOTB state model.
56 | 4.3 | Stage 2 — Execute | Sprint 4 | CAB Workbench setup & CAB process design | 2 | 2025-10-30 | 2025-10-31 | 55 | PC | TC | SME-ITSM | Sponsor | Not Started | 0% | CAB meeting workspace, agenda automation, change calendar, approval flow.
57 | 4.4 | Stage 2 — Execute | Sprint 4 | Service catalog — item build batch 1 (items 1–5) | 3 | 2025-10-27 | 2025-10-29 | 54,36 | PC, TC |  | SME-Catalog |  | Not Started | 0% | Build highest-priority 5 catalog items with OOTB variables, workflows, and approvals.
58 | 4.5 | Stage 2 — Execute | Sprint 4 | Service catalog — item build batch 2 (items 6–10) | 3 | 2025-10-30 | 2025-11-03 | 57 | PC, TC |  | SME-Catalog |  | Not Started | 0%
59 | 4.6 | Stage 2 — Execute | Sprint 4 | Fulfillment workflow configuration | 2 | 2025-10-31 | 2025-11-03 | 57 | TC | PC | SME-Catalog |  | Not Started | 0% | Flow designer workflows for catalog items; task assignment and SLA.
60 | 4.7 | Stage 2 — Execute | Sprint 4 | Employee Center portal — baseline setup | 3 | 2025-10-29 | 2025-10-31 | 54 | TC | PC | SME-HR | TechLead | Not Started | 0% | Portal branding baseline, taxonomy, IT & HR topic pages, announcement widget.
61 | 4.8 | Stage 2 — Execute | Sprint 4 | Sprint 4 demo — Change, Catalog, Employee Center | 1 | 2025-11-06 | 2025-11-06 | 56,58,59,60 | PC, TC | EM | Sponsor, CustPM | SME-ITSM, SME-Catalog | Not Started | 0%
62 | 4.9 | Stage 2 — Execute | Sprint 4 | Sprint 4 retro | 1 | 2025-11-07 | 2025-11-07 | 61 | EM | PC | CustPM |  | Not Started | 0%
63 | 4.M | Stage 2 — Execute | Sprint 4 | ✦ MILESTONE: Sprint 4 Complete — Core Build Done | — | 2025-11-07 | 2025-11-07 | 62 |  |  |  |  | Not Started | 0%
64 | 5 | Stage 2 — Execute | Sprint 5 | SPRINT 5 — EMPLOYEE EXPERIENCE & PLATFORM ANALYTICS | 10 | 2025-11-10 | 2025-11-21 |  | PC, TC | SA | SME-HR, CustPM | TechLead | Not Started | 0% | Weeks 11–12. Employee Center, Knowledge, Virtual Agent, Predictive Intelligence, PA.
65 | 5.1 | Stage 2 — Execute | Sprint 5 | Sprint 5 planning session | 1 | 2025-11-10 | 2025-11-10 | 63 | EM, SA | PC, TC | CustPM |  | Not Started | 0%
66 | 5.2 | Stage 2 — Execute | Sprint 5 | Employee Center — branding, navigation & content finalization | 3 | 2025-11-10 | 2025-11-12 | 65,60 | TC | PC | SME-HR | TechLead | Not Started | 0% | Custom branding, mega-menu, topic taxonomy, HR catalog integration.
67 | 5.3 | Stage 2 — Execute | Sprint 5 | Knowledge Management — article structure & curation | 2 | 2025-11-10 | 2025-11-11 | 65 | PC | TC | SME-ITSM, SME-HR |  | Not Started | 0% | KB category structure, article templates, publishing workflow, search optimization.
68 | 5.4 | Stage 2 — Execute | Sprint 5 | Virtual Agent — topic design workshop | 1 | 2025-11-10 | 2025-11-10 | 65 | PC | SA | SME-ITSM, SME-HR | CustPM | Not Started | 0% | Prioritize top 5–8 topics; define intent, conversation flows, fallback handling.
69 | 5.5 | Stage 2 — Execute | Sprint 5 | Virtual Agent — priority topic build & testing | 3 | 2025-11-11 | 2025-11-13 | 68,67 | TC | PC | SME-ITSM |  | Not Started | 0% | Build topics in NLU Workbench; test with sample utterances; embed in Employee Center.
70 | 5.6 | Stage 2 — Execute | Sprint 5 | Predictive Intelligence — data readiness validation | 2 | 2025-11-13 | 2025-11-14 | 65 | SA, TC |  | TechLead |  | Not Started | 0% | Validate incident/request history volume and quality for ML training readiness.
71 | 5.7 | Stage 2 — Execute | Sprint 5 | Platform Analytics — dashboard & KPI design workshop | 1 | 2025-11-10 | 2025-11-10 | 65 | PC | SA | CustPM, Sponsor | SME-ITSM | Not Started | 0% | Define KPIs per process area; map to PA data sources; agree dashboard layouts.
72 | 5.8 | Stage 2 — Execute | Sprint 5 | Platform Analytics — KPI and dashboard configuration | 3 | 2025-11-11 | 2025-11-13 | 71 | TC | PC | CustPM |  | Not Started | 0% | Build PA indicators, breakdowns, and dashboards in ServiceNow.
73 | 5.9 | Stage 2 — Execute | Sprint 5 | Sprint 5 demo — Employee Experience & Analytics | 1 | 2025-11-20 | 2025-11-20 | 66,69,70,72 | PC, TC | EM | Sponsor, CustPM | SME-HR, SME-ITSM | Not Started | 0% | Demo: Employee Center, Virtual Agent conversation, PA dashboard.
74 | 5.10 | Stage 2 — Execute | Sprint 5 | Sprint 5 retro | 1 | 2025-11-21 | 2025-11-21 | 73 | EM | PC | CustPM |  | Not Started | 0%
75 | 5.M | Stage 2 — Execute | Sprint 5 | ✦ MILESTONE: Sprint 5 Complete | — | 2025-11-21 | 2025-11-21 | 74 |  |  |  |  | Not Started | 0%
76 | 6 | Stage 3 — Deliver | Sprint 6 | SPRINT 6 — HAM, CATALOG COMPLETION & STABILIZATION | 10 | 2025-11-24 | 2025-12-05 |  | SA, TC | PC | SME-Asset, TechLead | CustPM | Not Started | 0% | Weeks 13–14. HAM Foundations/Realization, remaining catalog items, integration testing, stabilization.
77 | 6.1 | Stage 3 — Deliver | Sprint 6 | Sprint 6 planning session | 1 | 2025-11-24 | 2025-11-24 | 75 | EM, SA | PC, TC | CustPM |  | Not Started | 0%
78 | 6.2 | Stage 3 — Deliver | Sprint 6 | HAM Foundations — stockrooms, asset classes & models | 3 | 2025-11-24 | 2025-11-26 | 77 | SA, TC |  | SME-Asset | TechLead | Not Started | 0% | Configure stockrooms, asset classes, models per AP-04 (HAM Foundations pack).
79 | 6.3 | Stage 3 — Deliver | Sprint 6 | HAM Realization — lifecycle states & IMAC workflow config | 3 | 2025-11-27 | 2025-12-01 | 78 | TC | SA | SME-Asset |  | Not Started | 0% | Receive, assign, transfer, return, retire workflows. Procurement intake. Per AP-05.
80 | 6.4 | Stage 3 — Deliver | Sprint 6 | Service catalog — remaining items build (items 11–15) | 4 | 2025-11-24 | 2025-11-27 | 77,58 | PC, TC |  | SME-Catalog |  | Not Started | 0% | Complete catalog to 13–15 total OOTB items; final testing and approvals.
81 | 6.5 | Stage 3 — Deliver | Sprint 6 | Integration testing — all integrations (AD, SSO, SCCM, Intune) | 4 | 2025-11-24 | 2025-11-27 | 77,31,34 | TC | SA | TechLead |  | Not Started | 0% | End-to-end integration validation; user sync, SSO login, CMDB data flow.
82 | 6.6 | Stage 3 — Deliver | Sprint 6 | Environment stabilization & performance testing | 3 | 2025-11-28 | 2025-12-02 | 79,80,81 | SA, TC |  | TechLead |  | Not Started | 0% | Full regression sweep; performance test under expected load; fix blocking issues.
83 | 6.7 | Stage 3 — Deliver | Sprint 6 | Sprint 6 demo — HAM, Catalog, Stabilization | 1 | 2025-12-04 | 2025-12-04 | 79,80,82 | SA, TC | EM | Sponsor, CustPM | SME-Asset | Not Started | 0% | Demo full HAM lifecycle, completed catalog, performance metrics.
84 | 6.8 | Stage 3 — Deliver | Sprint 6 | Sprint 6 retro | 1 | 2025-12-05 | 2025-12-05 | 83 | EM | SA, PC | CustPM |  | Not Started | 0%
85 | 6.M | Stage 3 — Deliver | Sprint 6 | ✦ MILESTONE: Sprint 6 Complete — Build Phase Done | — | 2025-12-05 | 2025-12-05 | 84 |  |  |  |  | Not Started | 0%
86 | 7 | Stage 3 — Deliver | Sprint 7 | SPRINT 7 — USER ACCEPTANCE TESTING | 10 | 2025-12-08 | 2025-12-19 |  | PC, EM | SA, TC | CustPM | SME-ITSM, SME-Catalog, SME-HR, SME-Asset, End-Users | Not Started | 0% | Weeks 15–16. Customer-led testing across all process areas.
87 | 7.1 | Stage 3 — Deliver | Sprint 7 | UAT test scenarios distributed to customer | 1 | 2025-12-08 | 2025-12-08 | 85 | PC |  | CustPM |  | Not Started | 0% | Distribute CLT-UAT-02 scenario packs per process area.
88 | 7.2 | Stage 3 — Deliver | Sprint 7 | UAT kickoff & tester orientation | 1 | 2025-12-08 | 2025-12-08 | 85 | EM, PC |  | CustPM | SME-ITSM, SME-Catalog, SME-HR, SME-Asset | Not Started | 0% | Walkthrough of UAT process, defect logging via CLT-UAT-03, escalation path.
89 | 7.3 | Stage 3 — Deliver | Sprint 7 | UAT execution — ITSM (Incident, Problem, Change, Request) | 3 | 2025-12-09 | 2025-12-11 | 87,88 | PC | TC | SME-ITSM | End-Users | Not Started | 0% | Customer executes test scenarios; ECS monitors and assists without leading.
90 | 7.4 | Stage 3 — Deliver | Sprint 7 | UAT execution — Service Catalog & Employee Center | 3 | 2025-12-09 | 2025-12-11 | 87,88 | PC | TC | SME-Catalog, SME-HR | End-Users | Not Started | 0%
91 | 7.5 | Stage 3 — Deliver | Sprint 7 | UAT execution — Virtual Agent & Knowledge | 3 | 2025-12-09 | 2025-12-11 | 87,88 | PC | TC | SME-HR, SME-ITSM | End-Users | Not Started | 0%
92 | 7.6 | Stage 3 — Deliver | Sprint 7 | UAT execution — HAM lifecycle | 2 | 2025-12-10 | 2025-12-11 | 87,88 | SA | TC | SME-Asset |  | Not Started | 0%
93 | 7.7 | Stage 3 — Deliver | Sprint 7 | UAT defect triage & remediation | 3 | 2025-12-12 | 2025-12-16 | 89,90,91,92 | PC, TC | SA | CustPM | SME-ITSM | Not Started | 0% | Triage defects: fix blocking issues; log non-blocking as post-go-live backlog.
94 | 7.8 | Stage 3 — Deliver | Sprint 7 | UAT sign-off (customer) | 1 | 2025-12-19 | 2025-12-19 | 93 | EM |  | Sponsor, CustPM |  | Not Started | 0% | Formal sign-off on UAT completion. Required before go-live authorization.
95 | 7.M | Stage 3 — Deliver | Sprint 7 | ✦ MILESTONE: UAT Sign-Off Received | — | 2025-12-19 | 2025-12-19 | 94 |  |  |  |  | Not Started | 0%
96 | 8 | Stage 3 — Deliver | Sprint 7 | SPRINT 7 — GO-LIVE PREPARATION & EXECUTION | 3 | 2025-12-22 | 2025-12-24 |  | EM, SA | TC, PC | Sponsor, CustPM | TechLead | Not Started | 0% | End of Week 16 / start of Week 17. Final go/no-go and production cutover.
97 | 8.1 | Stage 3 — Deliver | Sprint 7 | Go-live checklist completion & readiness review | 1 | 2025-12-22 | 2025-12-22 | 95 | EM, SA | PC | Sponsor, CustPM | TechLead | Not Started | 0% | CLT-CO-01 go-live checklist reviewed and signed. Confirm helpdesk readiness.
98 | 8.2 | Stage 3 — Deliver | Sprint 7 | Go-live execution — production cutover | 1 | 2025-12-23 | 2025-12-23 | 97 | SA, TC | EM | TechLead | Sponsor | Not Started | 0% | Promote update sets to prod, validate, flip DNS/SSO to prod, comms broadcast.
99 | 8.M | Stage 3 — Deliver | Sprint 7 | ✦ MILESTONE: GO-LIVE | — | 2025-12-23 | 2025-12-23 | 98 |  |  |  |  | Not Started | 0%
100 | 9 | Stage 4 — Close | Sprint 8 | SPRINT 8 — HYPERCARE | 8 | 2025-12-24 | 2026-01-02 |  | EM, PC | SA, TC | CustPM | SME-ITSM, TechLead | Not Started | 0% | Weeks 17–18. Production support, knowledge transfer, and operational handoff.
101 | 9.1 | Stage 4 — Close | Sprint 8 | Daily stand-ups & production issue triage | 6 | 2025-12-24 | 2025-12-31 | 99 | EM, PC | TC | CustPM |  | Not Started | 0% | 30-min daily stand-up; ECS on standby for P1/P2 escalations during hypercare window.
102 | 9.2 | Stage 4 — Close | Sprint 8 | Knowledge transfer sessions — process area owners | 4 | 2025-12-24 | 2025-12-29 | 99 | PC, SA |  | SME-ITSM, SME-Catalog, SME-HR, SME-Asset | TechLead | Not Started | 0% | Structured handoff sessions: admin procedures, OOTB config rationale, run-book.
103 | 9.3 | Stage 4 — Close | Sprint 8 | Operational handoff documentation | 4 | 2025-12-25 | 2025-12-30 | 99 | PC | SA | CustPM | TechLead | Not Started | 0% | CLT-CO-03, CLT-CO-04, CLT-CO-06: expectations, handoff pack, SOPs delivered.
104 | 9.4 | Stage 4 — Close | Sprint 8 | Post-go-live ownership matrix finalized | 1 | 2025-12-31 | 2025-12-31 | 103 | EM |  | Sponsor, CustPM |  | Not Started | 0% | CLT-CO-05: per-process owner, escalation path, support tier. Customer-signed.
105 | 9.5 | Stage 4 — Close | Sprint 8 | Engagement closeout & lessons learned | 1 | 2026-01-01 | 2026-01-01 | 101,102,104 | EM | PM | Sponsor | CustPM | Not Started | 0% | INT-LL-01 completed. Closeout deck. Final invoice trigger. Retro with ECS PM.
106 | 9.6 | Stage 4 — Close | Sprint 8 | Continuous improvement roadmap delivered | 1 | 2026-01-01 | 2026-01-01 | 104 | PC, SA |  | Sponsor, CustPM |  | Not Started | 0% | CLT-CO-07: post-engagement backlog of deferred items, follow-on engagement framing.
107 | 9.M | Stage 4 — Close | Sprint 8 | ✦ MILESTONE: Engagement Complete | — | 2026-01-02 | 2026-01-02 | 105,106 |  |  |  |  | Not Started | 0%
108 | G.1 | Governance | All Sprints | Weekly status report (ECS EM → Customer PM) | 1 | 2025-09-10 | 2025-09-10 | 9 | EM |  | CustPM |  | Not Started | 0% | RECURRING weekly throughout engagement. SH-SG-03 template.
109 | G.2 | Governance | All Sprints | Bi-weekly sponsor sync (EM + Sponsor) | 1 | 2025-09-12 | 2025-09-12 | 4 | EM |  | Sponsor | CustPM | Not Started | 0% | RECURRING bi-weekly. INT-TBV-04 agenda template. Health RAG status reviewed.
110 | G.3 | Governance | Monthly | Customization Council review (monthly) | 1 | 2025-09-19 | 2025-09-19 | 8 | EM, SA | PC | Sponsor, CustPM |  | Not Started | 0% | RECURRING monthly. Any OOTB deviation requests reviewed and triaged.
Formulas:
Finish Date = WORKDAY([Start Date],9)
Finish Date = [Start Date]

## Resource Buildup
Role | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
Leadership (Tim/Shawn | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 180
EM | 20 | 20 | 20 | 20 | 20 | 20 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 20 | 20 | 20 | 16 | 16 | 324
BPC/BA | 20 | 20 | 20 | 24 | 20 | 24 | 20 | 24 | 20 | 24 | 20 | 20 | 20 | 20 | 20 | 16 | 8 | 8 | 348
SA | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 8 | 336
TL/Dev |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 8 | 316
Dev |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  | 240
1744
200
[19 empty] | 348800 | All hours
[19 empty] | 36000 | Leadership cost
[19 empty] | 312800 | Cost without leadership

## MS Project Import
MS PROJECT IMPORT SHEET — Save this sheet as CSV (comma-delimited) or use File > Import in MS Project. Map columns by header name. Set Start Date on 'Project Plan' sheet tab first.
ID | Outline Level | Name | Duration | Start | Finish | Predecessors | Resource Names | Notes
1 | 1 | SPRINT 0 — ENGAGEMENT SETUP | 10 days | 2025-09-01 | 2025-09-12 |  | EM; SA, PC; Sponsor, CustPM | Weeks 1–2. All setup activities to ensure team and environment are ready for Sprint 1.
2 | 2 | Internal ECS kickoff — SOW review & consultant assignment | 1 days | 2025-09-01 | 2025-09-01 |  | EM; PM | Review SOW scope, confirm consultant roles, load sprint tooling and templates.
3 | 2 | Contract & SOW finalization (customer signature) | 1 days | 2025-09-01 | 2025-09-01 |  | EM; Sponsor; CustPM | Confirm signed SOW before Sprint 1 commitment.
4 | 2 | Customer kickoff meeting | 1 days | 2025-09-02 | 2025-09-02 | 2,3 | EM, SA; PC; Sponsor, CustPM; TechLead | Introductions, engagement overview, 18-week journey walk-through, Q&A.
5 | 2 | Environment provisioning — dev / test / prod instances | 3 days | 2025-09-02 | 2025-09-04 | 4 | SA, TC; TechLead | ServiceNow instance request, MID server setup, network access.
6 | 2 | Access & credentials setup (admin, consultant, test accounts) | 2 days | 2025-09-02 | 2025-09-03 | 4 | TC; SA; TechLead | ECS consultant accounts, customer admin accounts, SSO config baseline.
7 | 2 | Governance & decision rights workshop | 1 days | 2025-09-03 | 2025-09-03 | 4 | EM, PC; Sponsor, CustPM; TechLead | Establish customization council, RACI, escalation path, decision log.
8 | 2 | Customization Council charter signed | 1 days | 2025-09-04 | 2025-09-04 | 7 | EM; Sponsor | Council charter defines quorum, meeting cadence, and veto rights for any scope deviation.
9 | 2 | Communication plan & cadence established | 1 days | 2025-09-03 | 2025-09-03 | 4 | EM; CustPM | Weekly status report schedule, bi-weekly sponsor sync, sprint demo invites.
10 | 2 | Risk register initialized | 1 days | 2025-09-04 | 2025-09-04 | 4 | EM, PC; CustPM | Populate with known risks: data readiness, SME availability, environment delays.
11 | 2 | Foundation Data Pack distributed to customer | 1 days | 2025-09-05 | 2025-09-05 | 4 | PC; CustPM; SME-ITSM | AP-01 workbooks: users, locations, departments, groups, assignment rules, SLAs, schedules.
12 | 2 | Stakeholder mapping completed | 1 days | 2025-09-05 | 2025-09-05 | 4 | EM; CustPM; Sponsor | Identify all SMEs, decision owners, and change champions per process area.
13 | 2 | Sprint 0 readiness validation (ECS checklist) | 1 days | 2025-09-12 | 2025-09-12 | 5,6,7,8,9,10,11,12 | EM; SA; CustPM | Confirm: env provisioned, access live, governance signed, data pack distributed, risks logged.
14 | 0 | ✦ MILESTONE: Sprint 0 Complete — Ready to Build | 0 days | 2025-09-12 | 2025-09-12 | 13
15 | 1 | SPRINT 1 — PLATFORM FOUNDATION & ITSM DESIGN | 10 days | 2025-09-15 | 2025-09-26 |  | SA, PC; EM; CustPM, TechLead; SME-ITSM | Weeks 3–4. Platform stand-up, CSDM, and ITSM design workshops.
16 | 2 | Sprint 1 planning session | 1 days | 2025-09-15 | 2025-09-15 | 14 | EM, SA; PC, TC; CustPM | Story review, sprint backlog confirmation, acceptance criteria.
17 | 2 | Platform architecture stand-up & baseline configuration | 3 days | 2025-09-15 | 2025-09-17 | 16,5 | SA, TC; TechLead | CMDB scope settings, update sets, source control, MID server validation.
18 | 2 | CSDM definition workshop | 2 days | 2025-09-15 | 2025-09-16 | 16 | SA, PC; CustPM, TechLead; SME-ITSM | Map customer services, apps, and CIs to CSDM layers. Define service taxonomy.
19 | 2 | CSDM validation against ServiceNow data model | 2 days | 2025-09-17 | 2025-09-18 | 18 | SA; TC; TechLead | Validate service-CI relationships; confirm Business Service and Technical Service scope.
20 | 2 | ITSM design workshop — Incident Management | 1 days | 2025-09-15 | 2025-09-15 | 16 | PC; SA; SME-ITSM; CustPM | State model, categorization, priority matrix, routing logic, SLA tiers.
21 | 2 | ITSM design workshop — Problem Management | 1 days | 2025-09-16 | 2025-09-16 | 20 | PC; SA; SME-ITSM | Problem identification triggers, investigation workflow, known error base.
22 | 2 | ITSM design workshop — Request Management | 1 days | 2025-09-17 | 2025-09-17 | 21 | PC; SA; SME-ITSM; SME-Catalog | Request types, fulfillment model, approval tiers, SLA targets.
23 | 2 | Foundation Data Pack review — users, groups, locations | 2 days | 2025-09-18 | 2025-09-19 | 11 | PC; TC; SME-ITSM; TechLead | Review customer-returned workbooks; identify gaps before Sprint 3 config.
24 | 2 | Assignment rules & SLA design review | 1 days | 2025-09-19 | 2025-09-19 | 23 | PC; SA; SME-ITSM | Confirm assignment group structure, SLA definitions, and escalation schedules.
25 | 2 | Sprint 1 demo | 1 days | 2025-09-25 | 2025-09-25 | 17,19,24 | SA, PC; EM; Sponsor, CustPM; TechLead, SME-ITSM | Demo: platform baseline, CSDM service map, design decision recap.
26 | 2 | Sprint 1 retro | 1 days | 2025-09-26 | 2025-09-26 | 25 | EM; SA, PC; CustPM | Velocity, blockers, action items. Update risk register.
27 | 0 | ✦ MILESTONE: Sprint 1 Complete | 0 days | 2025-09-26 | 2025-09-26 | 26
28 | 1 | SPRINT 2 — DISCOVERY & CMDB FOUNDATION | 10 days | 2025-09-29 | 2025-10-10 |  | SA, TC; PC; TechLead; SME-ITSM | Weeks 5–6. Discovery tooling, Service Graph Connectors, CMDB normalization, catalog scope.
29 | 2 | Sprint 2 planning session | 1 days | 2025-09-29 | 2025-09-29 | 27 | EM, SA; PC, TC; CustPM
30 | 2 | Discovery tool installation & network scan configuration | 3 days | 2025-09-29 | 2025-10-01 | 29 | TC; SA; TechLead | Discovery schedules, credentials, network range scoping.
31 | 2 | Service Graph Connectors — SCCM / Intune porting | 4 days | 2025-09-29 | 2025-10-02 | 29 | TC; SA; TechLead | Port connectors from prior system; validate CI population in CMDB.
32 | 2 | CMDB normalization — scope & approach workshop | 1 days | 2025-09-29 | 2025-09-29 | 29 | SA, PC; TechLead; CustPM | Agree CI classes in scope, normalization rules, rogue CI cleanup approach.
33 | 2 | CI class selection workshop | 1 days | 2025-09-30 | 2025-09-30 | 32,19 | SA; PC; TechLead; SME-ITSM | Select Server, Network, Application CI classes; confirm relationship types.
34 | 2 | Initial CMDB data load & relationship validation | 3 days | 2025-10-01 | 2025-10-03 | 33 | TC; SA; TechLead | Load SCCM/Intune data; validate CI counts, duplicates, relationship integrity.
35 | 2 | Service catalog — category structure design workshop | 1 days | 2025-09-29 | 2025-09-29 | 29 | PC; SA; SME-Catalog; CustPM | Rationalize legacy categories; target ≤15 top-level categories OOTB.
36 | 2 | Service catalog — item inventory & prioritization | 2 days | 2025-09-30 | 2025-10-01 | 35 | PC; SME-Catalog | Inventory existing items; prioritize 13–15 for Sprint 4/6 build.
37 | 2 | Sprint 2 demo | 1 days | 2025-10-09 | 2025-10-09 | 30,31,34,36 | SA, TC; EM; Sponsor, CustPM; TechLead | Demo: Discovery scan, CMDB CIs, Service Graph connector results, catalog scope.
38 | 2 | Sprint 2 retro | 1 days | 2025-10-10 | 2025-10-10 | 37 | EM; SA, PC; CustPM
39 | 0 | ✦ MILESTONE: Sprint 2 Complete — Foundation Data in System | 0 days | 2025-10-10 | 2025-10-10 | 38
40 | 1 | SPRINT 3 — ITSM CORE BUILD | 10 days | 2025-10-13 | 2025-10-24 |  | PC, TC; SA; SME-ITSM; TechLead | Weeks 7–8. Configure Incident, Major Incident, Problem, Request, SLAs, assignments, approvals.
41 | 2 | Sprint 3 planning session | 1 days | 2025-10-13 | 2025-10-13 | 39 | EM, SA; PC, TC; CustPM
42 | 2 | Incident Management — OOTB configuration | 3 days | 2025-10-13 | 2025-10-15 | 41,20 | PC, TC; SA; SME-ITSM | State model, categories, assignment rules, VIP handling, OOTB form layout.
43 | 2 | Major Incident Management configuration | 2 days | 2025-10-16 | 2025-10-17 | 42 | PC, TC; SME-ITSM | P1/P2 bridge triggers, comms templates, bridge workspace, MIM role.
44 | 2 | Problem Management configuration | 2 days | 2025-10-13 | 2025-10-14 | 41,21 | PC, TC; SME-ITSM | Problem creation triggers, investigation/RCA workflow, known error publishing.
45 | 2 | Request Management configuration (RITM + catalog flow) | 2 days | 2025-10-13 | 2025-10-14 | 41,22 | PC, TC; SME-ITSM; SME-Catalog | RITM state model, task assignment, approval workflow, SLA.
46 | 2 | SLA configuration & testing | 2 days | 2025-10-15 | 2025-10-16 | 42,24 | PC, TC; SME-ITSM | P1–P4 SLA definitions, schedule attachments, breach notifications, pause conditions.
47 | 2 | Assignment rules configuration | 2 days | 2025-10-15 | 2025-10-16 | 42,24 | PC, TC; SME-ITSM; TechLead | OOTB assignment rules, group rotation, overflow rules.
48 | 2 | Approval workflow configuration | 2 days | 2025-10-17 | 2025-10-20 | 45 | PC, TC; SME-ITSM | Approval groups, delegate rules, auto-approval thresholds, OOTB approval engine.
49 | 2 | Notifications configuration | 1 days | 2025-10-21 | 2025-10-21 | 42,44,45 | TC; PC; SME-ITSM | OOTB notification templates for Incident, Problem, Request state changes.
50 | 2 | Sprint 3 demo — ITSM Core | 1 days | 2025-10-23 | 2025-10-23 | 43,44,45,46,47,48,49 | PC, TC; EM; Sponsor, CustPM; SME-ITSM | Live demo of Incident lifecycle, Problem investigation, Request fulfillment.
51 | 2 | Sprint 3 retro | 1 days | 2025-10-24 | 2025-10-24 | 50 | EM; PC; CustPM
52 | 0 | ✦ MILESTONE: Sprint 3 Complete — ITSM Core Configured | 0 days | 2025-10-24 | 2025-10-24 | 51
53 | 1 | SPRINT 4 — CHANGE / CAB & SERVICE CATALOG BUILD | 10 days | 2025-10-27 | 2025-11-07 |  | PC, TC; SA; SME-ITSM, SME-Catalog; CustPM | Weeks 9–10. Change/CAB OOTB build, catalog items batch 1 & 2, Employee Center baseline.
54 | 2 | Sprint 4 planning session | 1 days | 2025-10-27 | 2025-10-27 | 52 | EM, SA; PC, TC; CustPM
55 | 2 | Change Management — OOTB configuration | 3 days | 2025-10-27 | 2025-10-29 | 54 | PC, TC; SA; SME-ITSM | Normal/Standard/Emergency change types, CAB schedule, risk assessment, OOTB state model.
56 | 2 | CAB Workbench setup & CAB process design | 2 days | 2025-10-30 | 2025-10-31 | 55 | PC; TC; SME-ITSM; Sponsor | CAB meeting workspace, agenda automation, change calendar, approval flow.
57 | 2 | Service catalog — item build batch 1 (items 1–5) | 3 days | 2025-10-27 | 2025-10-29 | 54,36 | PC, TC; SME-Catalog | Build highest-priority 5 catalog items with OOTB variables, workflows, and approvals.
58 | 2 | Service catalog — item build batch 2 (items 6–10) | 3 days | 2025-10-30 | 2025-11-03 | 57 | PC, TC; SME-Catalog
59 | 2 | Fulfillment workflow configuration | 2 days | 2025-10-31 | 2025-11-03 | 57 | TC; PC; SME-Catalog | Flow designer workflows for catalog items; task assignment and SLA.
60 | 2 | Employee Center portal — baseline setup | 3 days | 2025-10-29 | 2025-10-31 | 54 | TC; PC; SME-HR; TechLead | Portal branding baseline, taxonomy, IT & HR topic pages, announcement widget.
61 | 2 | Sprint 4 demo — Change, Catalog, Employee Center | 1 days | 2025-11-06 | 2025-11-06 | 56,58,59,60 | PC, TC; EM; Sponsor, CustPM; SME-ITSM, SME-Catalog
62 | 2 | Sprint 4 retro | 1 days | 2025-11-07 | 2025-11-07 | 61 | EM; PC; CustPM
63 | 0 | ✦ MILESTONE: Sprint 4 Complete — Core Build Done | 0 days | 2025-11-07 | 2025-11-07 | 62
64 | 1 | SPRINT 5 — EMPLOYEE EXPERIENCE & PLATFORM ANALYTICS | 10 days | 2025-11-10 | 2025-11-21 |  | PC, TC; SA; SME-HR, CustPM; TechLead | Weeks 11–12. Employee Center, Knowledge, Virtual Agent, Predictive Intelligence, PA.
65 | 2 | Sprint 5 planning session | 1 days | 2025-11-10 | 2025-11-10 | 63 | EM, SA; PC, TC; CustPM
66 | 2 | Employee Center — branding, navigation & content finalization | 3 days | 2025-11-10 | 2025-11-12 | 65,60 | TC; PC; SME-HR; TechLead | Custom branding, mega-menu, topic taxonomy, HR catalog integration.
67 | 2 | Knowledge Management — article structure & curation | 2 days | 2025-11-10 | 2025-11-11 | 65 | PC; TC; SME-ITSM, SME-HR | KB category structure, article templates, publishing workflow, search optimization.
68 | 2 | Virtual Agent — topic design workshop | 1 days | 2025-11-10 | 2025-11-10 | 65 | PC; SA; SME-ITSM, SME-HR; CustPM | Prioritize top 5–8 topics; define intent, conversation flows, fallback handling.
69 | 2 | Virtual Agent — priority topic build & testing | 3 days | 2025-11-11 | 2025-11-13 | 68,67 | TC; PC; SME-ITSM | Build topics in NLU Workbench; test with sample utterances; embed in Employee Center.
70 | 2 | Predictive Intelligence — data readiness validation | 2 days | 2025-11-13 | 2025-11-14 | 65 | SA, TC; TechLead | Validate incident/request history volume and quality for ML training readiness.
71 | 2 | Platform Analytics — dashboard & KPI design workshop | 1 days | 2025-11-10 | 2025-11-10 | 65 | PC; SA; CustPM, Sponsor; SME-ITSM | Define KPIs per process area; map to PA data sources; agree dashboard layouts.
72 | 2 | Platform Analytics — KPI and dashboard configuration | 3 days | 2025-11-11 | 2025-11-13 | 71 | TC; PC; CustPM | Build PA indicators, breakdowns, and dashboards in ServiceNow.
73 | 2 | Sprint 5 demo — Employee Experience & Analytics | 1 days | 2025-11-20 | 2025-11-20 | 66,69,70,72 | PC, TC; EM; Sponsor, CustPM; SME-HR, SME-ITSM | Demo: Employee Center, Virtual Agent conversation, PA dashboard.
74 | 2 | Sprint 5 retro | 1 days | 2025-11-21 | 2025-11-21 | 73 | EM; PC; CustPM
75 | 0 | ✦ MILESTONE: Sprint 5 Complete | 0 days | 2025-11-21 | 2025-11-21 | 74
76 | 1 | SPRINT 6 — HAM, CATALOG COMPLETION & STABILIZATION | 10 days | 2025-11-24 | 2025-12-05 |  | SA, TC; PC; SME-Asset, TechLead; CustPM | Weeks 13–14. HAM Foundations/Realization, remaining catalog items, integration testing, stabilization.
77 | 2 | Sprint 6 planning session | 1 days | 2025-11-24 | 2025-11-24 | 75 | EM, SA; PC, TC; CustPM
78 | 2 | HAM Foundations — stockrooms, asset classes & models | 3 days | 2025-11-24 | 2025-11-26 | 77 | SA, TC; SME-Asset; TechLead | Configure stockrooms, asset classes, models per AP-04 (HAM Foundations pack).
79 | 2 | HAM Realization — lifecycle states & IMAC workflow config | 3 days | 2025-11-27 | 2025-12-01 | 78 | TC; SA; SME-Asset | Receive, assign, transfer, return, retire workflows. Procurement intake. Per AP-05.
80 | 2 | Service catalog — remaining items build (items 11–15) | 4 days | 2025-11-24 | 2025-11-27 | 77,58 | PC, TC; SME-Catalog | Complete catalog to 13–15 total OOTB items; final testing and approvals.
81 | 2 | Integration testing — all integrations (AD, SSO, SCCM, Intune) | 4 days | 2025-11-24 | 2025-11-27 | 77,31,34 | TC; SA; TechLead | End-to-end integration validation; user sync, SSO login, CMDB data flow.
82 | 2 | Environment stabilization & performance testing | 3 days | 2025-11-28 | 2025-12-02 | 79,80,81 | SA, TC; TechLead | Full regression sweep; performance test under expected load; fix blocking issues.
83 | 2 | Sprint 6 demo — HAM, Catalog, Stabilization | 1 days | 2025-12-04 | 2025-12-04 | 79,80,82 | SA, TC; EM; Sponsor, CustPM; SME-Asset | Demo full HAM lifecycle, completed catalog, performance metrics.
84 | 2 | Sprint 6 retro | 1 days | 2025-12-05 | 2025-12-05 | 83 | EM; SA, PC; CustPM
85 | 0 | ✦ MILESTONE: Sprint 6 Complete — Build Phase Done | 0 days | 2025-12-05 | 2025-12-05 | 84
86 | 1 | SPRINT 7 — USER ACCEPTANCE TESTING | 10 days | 2025-12-08 | 2025-12-19 |  | PC, EM; SA, TC; CustPM; SME-ITSM, SME-Catalog, SME-HR, SME-Asset, End-Users | Weeks 15–16. Customer-led testing across all process areas.
87 | 2 | UAT test scenarios distributed to customer | 1 days | 2025-12-08 | 2025-12-08 | 85 | PC; CustPM | Distribute CLT-UAT-02 scenario packs per process area.
88 | 2 | UAT kickoff & tester orientation | 1 days | 2025-12-08 | 2025-12-08 | 85 | EM, PC; CustPM; SME-ITSM, SME-Catalog, SME-HR, SME-Asset | Walkthrough of UAT process, defect logging via CLT-UAT-03, escalation path.
89 | 2 | UAT execution — ITSM (Incident, Problem, Change, Request) | 3 days | 2025-12-09 | 2025-12-11 | 87,88 | PC; TC; SME-ITSM; End-Users | Customer executes test scenarios; ECS monitors and assists without leading.
90 | 2 | UAT execution — Service Catalog & Employee Center | 3 days | 2025-12-09 | 2025-12-11 | 87,88 | PC; TC; SME-Catalog, SME-HR; End-Users
91 | 2 | UAT execution — Virtual Agent & Knowledge | 3 days | 2025-12-09 | 2025-12-11 | 87,88 | PC; TC; SME-HR, SME-ITSM; End-Users
92 | 2 | UAT execution — HAM lifecycle | 2 days | 2025-12-10 | 2025-12-11 | 87,88 | SA; TC; SME-Asset
93 | 2 | UAT defect triage & remediation | 3 days | 2025-12-12 | 2025-12-16 | 89,90,91,92 | PC, TC; SA; CustPM; SME-ITSM | Triage defects: fix blocking issues; log non-blocking as post-go-live backlog.
94 | 2 | UAT sign-off (customer) | 1 days | 2025-12-19 | 2025-12-19 | 93 | EM; Sponsor, CustPM | Formal sign-off on UAT completion. Required before go-live authorization.
95 | 0 | ✦ MILESTONE: UAT Sign-Off Received | 0 days | 2025-12-19 | 2025-12-19 | 94
96 | 1 | SPRINT 7 — GO-LIVE PREPARATION & EXECUTION | 3 days | 2025-12-22 | 2025-12-24 |  | EM, SA; TC, PC; Sponsor, CustPM; TechLead | End of Week 16 / start of Week 17. Final go/no-go and production cutover.
97 | 2 | Go-live checklist completion & readiness review | 1 days | 2025-12-22 | 2025-12-22 | 95 | EM, SA; PC; Sponsor, CustPM; TechLead | CLT-CO-01 go-live checklist reviewed and signed. Confirm helpdesk readiness.
98 | 2 | Go-live execution — production cutover | 1 days | 2025-12-23 | 2025-12-23 | 97 | SA, TC; EM; TechLead; Sponsor | Promote update sets to prod, validate, flip DNS/SSO to prod, comms broadcast.
99 | 0 | ✦ MILESTONE: GO-LIVE | 0 days | 2025-12-23 | 2025-12-23 | 98
100 | 1 | SPRINT 8 — HYPERCARE | 8 days | 2025-12-24 | 2026-01-02 |  | EM, PC; SA, TC; CustPM; SME-ITSM, TechLead | Weeks 17–18. Production support, knowledge transfer, and operational handoff.
101 | 2 | Daily stand-ups & production issue triage | 6 days | 2025-12-24 | 2025-12-31 | 99 | EM, PC; TC; CustPM | 30-min daily stand-up; ECS on standby for P1/P2 escalations during hypercare window.
102 | 2 | Knowledge transfer sessions — process area owners | 4 days | 2025-12-24 | 2025-12-29 | 99 | PC, SA; SME-ITSM, SME-Catalog, SME-HR, SME-Asset; TechLead | Structured handoff sessions: admin procedures, OOTB config rationale, run-book.
103 | 2 | Operational handoff documentation | 4 days | 2025-12-25 | 2025-12-30 | 99 | PC; SA; CustPM; TechLead | CLT-CO-03, CLT-CO-04, CLT-CO-06: expectations, handoff pack, SOPs delivered.
104 | 2 | Post-go-live ownership matrix finalized | 1 days | 2025-12-31 | 2025-12-31 | 103 | EM; Sponsor, CustPM | CLT-CO-05: per-process owner, escalation path, support tier. Customer-signed.
105 | 2 | Engagement closeout & lessons learned | 1 days | 2026-01-01 | 2026-01-01 | 101,102,104 | EM; PM; Sponsor; CustPM | INT-LL-01 completed. Closeout deck. Final invoice trigger. Retro with ECS PM.
106 | 2 | Continuous improvement roadmap delivered | 1 days | 2026-01-01 | 2026-01-01 | 104 | PC, SA; Sponsor, CustPM | CLT-CO-07: post-engagement backlog of deferred items, follow-on engagement framing.
107 | 0 | ✦ MILESTONE: Engagement Complete | 0 days | 2026-01-02 | 2026-01-02 | 105,106
108 | 2 | Weekly status report (ECS EM → Customer PM) | 1 days | 2025-09-10 | 2025-09-10 | 9 | EM; CustPM | RECURRING weekly throughout engagement. SH-SG-03 template.
109 | 2 | Bi-weekly sponsor sync (EM + Sponsor) | 1 days | 2025-09-12 | 2025-09-12 | 4 | EM; Sponsor; CustPM | RECURRING bi-weekly. INT-TBV-04 agenda template. Health RAG status reviewed.
110 | 2 | Customization Council review (monthly) | 1 days | 2025-09-19 | 2025-09-19 | 8 | EM, SA; PC; Sponsor, CustPM | RECURRING monthly. Any OOTB deviation requests reviewed and triaged.
Formulas:
Finish = WORKDAY([Start],9)

## SNow PPM Import
SNow PPM IMPORT SHEET — Fields map to ServiceNow Project Task table (pm_project_task). Import via: Project > Import Tasks > Excel/CSV. Dates pull from 'Project Plan' tab.
task_number | short_description | parent_task | phase | planned_start_date | planned_end_date | duration_days | state | assigned_to_role | description | predecessors
ECS-001 | SPRINT 0 — ENGAGEMENT SETUP |  | Sprint 0 | 2025-09-01 | 2025-09-12 | 10 | Open | EM; Sponsor, CustPM | Weeks 1–2. All setup activities to ensure team and environment are ready for Sprint 1.
ECS-002 | Internal ECS kickoff — SOW review & consultant assignment | ECS-001 | Sprint 0 | 2025-09-01 | 2025-09-01 | 1 | Open | EM | Review SOW scope, confirm consultant roles, load sprint tooling and templates.
ECS-003 | Contract & SOW finalization (customer signature) | ECS-001 | Sprint 0 | 2025-09-01 | 2025-09-01 | 1 | Open | EM; Sponsor | Confirm signed SOW before Sprint 1 commitment.
ECS-004 | Customer kickoff meeting | ECS-001 | Sprint 0 | 2025-09-02 | 2025-09-02 | 1 | Open | EM, SA; Sponsor, CustPM | Introductions, engagement overview, 18-week journey walk-through, Q&A. | 2,3
ECS-005 | Environment provisioning — dev / test / prod instances | ECS-001 | Sprint 0 | 2025-09-02 | 2025-09-04 | 3 | Open | SA, TC; TechLead | ServiceNow instance request, MID server setup, network access. | 4
ECS-006 | Access & credentials setup (admin, consultant, test accounts) | ECS-001 | Sprint 0 | 2025-09-02 | 2025-09-03 | 2 | Open | TC; TechLead | ECS consultant accounts, customer admin accounts, SSO config baseline. | 4
ECS-007 | Governance & decision rights workshop | ECS-001 | Sprint 0 | 2025-09-03 | 2025-09-03 | 1 | Open | EM, PC; Sponsor, CustPM | Establish customization council, RACI, escalation path, decision log. | 4
ECS-008 | Customization Council charter signed | ECS-001 | Sprint 0 | 2025-09-04 | 2025-09-04 | 1 | Open | EM; Sponsor | Council charter defines quorum, meeting cadence, and veto rights for any scope deviation. | 7
ECS-009 | Communication plan & cadence established | ECS-001 | Sprint 0 | 2025-09-03 | 2025-09-03 | 1 | Open | EM; CustPM | Weekly status report schedule, bi-weekly sponsor sync, sprint demo invites. | 4
ECS-010 | Risk register initialized | ECS-001 | Sprint 0 | 2025-09-04 | 2025-09-04 | 1 | Open | EM, PC; CustPM | Populate with known risks: data readiness, SME availability, environment delays. | 4
ECS-011 | Foundation Data Pack distributed to customer | ECS-001 | Sprint 0 | 2025-09-05 | 2025-09-05 | 1 | Open | PC; CustPM | AP-01 workbooks: users, locations, departments, groups, assignment rules, SLAs, schedules. | 4
ECS-012 | Stakeholder mapping completed | ECS-001 | Sprint 0 | 2025-09-05 | 2025-09-05 | 1 | Open | EM; CustPM | Identify all SMEs, decision owners, and change champions per process area. | 4
ECS-013 | Sprint 0 readiness validation (ECS checklist) | ECS-001 | Sprint 0 | 2025-09-12 | 2025-09-12 | 1 | Open | EM; CustPM | Confirm: env provisioned, access live, governance signed, data pack distributed, risks logged. | 5,6,7,8,9,10,11,12
ECS-014 | ✦ MILESTONE: Sprint 0 Complete — Ready to Build | ECS-001 | Sprint 0 | 2025-09-12 | 2025-09-12 | 0 | Open |  |  | 13
ECS-015 | SPRINT 1 — PLATFORM FOUNDATION & ITSM DESIGN |  | Month 1 | 2025-09-15 | 2025-09-26 | 10 | Open | SA, PC; CustPM, TechLead | Weeks 3–4. Platform stand-up, CSDM, and ITSM design workshops.
ECS-016 | Sprint 1 planning session | ECS-015 | Month 1 | 2025-09-15 | 2025-09-15 | 1 | Open | EM, SA; CustPM | Story review, sprint backlog confirmation, acceptance criteria. | 14
ECS-017 | Platform architecture stand-up & baseline configuration | ECS-015 | Month 1 | 2025-09-15 | 2025-09-17 | 3 | Open | SA, TC; TechLead | CMDB scope settings, update sets, source control, MID server validation. | 16,5
ECS-018 | CSDM definition workshop | ECS-015 | Month 1 | 2025-09-15 | 2025-09-16 | 2 | Open | SA, PC; CustPM, TechLead | Map customer services, apps, and CIs to CSDM layers. Define service taxonomy. | 16
ECS-019 | CSDM validation against ServiceNow data model | ECS-015 | Month 1 | 2025-09-17 | 2025-09-18 | 2 | Open | SA; TechLead | Validate service-CI relationships; confirm Business Service and Technical Service scope. | 18
ECS-020 | ITSM design workshop — Incident Management | ECS-015 | Month 1 | 2025-09-15 | 2025-09-15 | 1 | Open | PC; SME-ITSM | State model, categorization, priority matrix, routing logic, SLA tiers. | 16
ECS-021 | ITSM design workshop — Problem Management | ECS-015 | Month 1 | 2025-09-16 | 2025-09-16 | 1 | Open | PC; SME-ITSM | Problem identification triggers, investigation workflow, known error base. | 20
ECS-022 | ITSM design workshop — Request Management | ECS-015 | Month 1 | 2025-09-17 | 2025-09-17 | 1 | Open | PC; SME-ITSM | Request types, fulfillment model, approval tiers, SLA targets. | 21
ECS-023 | Foundation Data Pack review — users, groups, locations | ECS-015 | Month 1 | 2025-09-18 | 2025-09-19 | 2 | Open | PC; SME-ITSM | Review customer-returned workbooks; identify gaps before Sprint 3 config. | 11
ECS-024 | Assignment rules & SLA design review | ECS-015 | Month 1 | 2025-09-19 | 2025-09-19 | 1 | Open | PC; SME-ITSM | Confirm assignment group structure, SLA definitions, and escalation schedules. | 23
ECS-025 | Sprint 1 demo | ECS-015 | Month 1 | 2025-09-25 | 2025-09-25 | 1 | Open | SA, PC; Sponsor, CustPM | Demo: platform baseline, CSDM service map, design decision recap. | 17,19,24
ECS-026 | Sprint 1 retro | ECS-015 | Month 1 | 2025-09-26 | 2025-09-26 | 1 | Open | EM; CustPM | Velocity, blockers, action items. Update risk register. | 25
ECS-027 | ✦ MILESTONE: Sprint 1 Complete | ECS-015 | Month 1 | 2025-09-26 | 2025-09-26 | 0 | Open |  |  | 26
ECS-028 | SPRINT 2 — DISCOVERY & CMDB FOUNDATION |  | Month 1 | 2025-09-29 | 2025-10-10 | 10 | Open | SA, TC; TechLead | Weeks 5–6. Discovery tooling, Service Graph Connectors, CMDB normalization, catalog scope.
ECS-029 | Sprint 2 planning session | ECS-028 | Month 1 | 2025-09-29 | 2025-09-29 | 1 | Open | EM, SA; CustPM |  | 27
ECS-030 | Discovery tool installation & network scan configuration | ECS-028 | Month 1 | 2025-09-29 | 2025-10-01 | 3 | Open | TC; TechLead | Discovery schedules, credentials, network range scoping. | 29
ECS-031 | Service Graph Connectors — SCCM / Intune porting | ECS-028 | Month 1 | 2025-09-29 | 2025-10-02 | 4 | Open | TC; TechLead | Port connectors from prior system; validate CI population in CMDB. | 29
ECS-032 | CMDB normalization — scope & approach workshop | ECS-028 | Month 1 | 2025-09-29 | 2025-09-29 | 1 | Open | SA, PC; TechLead | Agree CI classes in scope, normalization rules, rogue CI cleanup approach. | 29
ECS-033 | CI class selection workshop | ECS-028 | Month 1 | 2025-09-30 | 2025-09-30 | 1 | Open | SA; TechLead | Select Server, Network, Application CI classes; confirm relationship types. | 32,19
ECS-034 | Initial CMDB data load & relationship validation | ECS-028 | Month 1 | 2025-10-01 | 2025-10-03 | 3 | Open | TC; TechLead | Load SCCM/Intune data; validate CI counts, duplicates, relationship integrity. | 33
ECS-035 | Service catalog — category structure design workshop | ECS-028 | Month 1 | 2025-09-29 | 2025-09-29 | 1 | Open | PC; SME-Catalog | Rationalize legacy categories; target ≤15 top-level categories OOTB. | 29
ECS-036 | Service catalog — item inventory & prioritization | ECS-028 | Month 1 | 2025-09-30 | 2025-10-01 | 2 | Open | PC; SME-Catalog | Inventory existing items; prioritize 13–15 for Sprint 4/6 build. | 35
ECS-037 | Sprint 2 demo | ECS-028 | Month 1 | 2025-10-09 | 2025-10-09 | 1 | Open | SA, TC; Sponsor, CustPM | Demo: Discovery scan, CMDB CIs, Service Graph connector results, catalog scope. | 30,31,34,36
ECS-038 | Sprint 2 retro | ECS-028 | Month 1 | 2025-10-10 | 2025-10-10 | 1 | Open | EM; CustPM |  | 37
ECS-039 | ✦ MILESTONE: Sprint 2 Complete — Foundation Data in System | ECS-028 | Month 1 | 2025-10-10 | 2025-10-10 | 0 | Open |  |  | 38
ECS-040 | SPRINT 3 — ITSM CORE BUILD |  | Month 2 | 2025-10-13 | 2025-10-24 | 10 | Open | PC, TC; SME-ITSM | Weeks 7–8. Configure Incident, Major Incident, Problem, Request, SLAs, assignments, approvals.
ECS-041 | Sprint 3 planning session | ECS-040 | Month 2 | 2025-10-13 | 2025-10-13 | 1 | Open | EM, SA; CustPM |  | 39
ECS-042 | Incident Management — OOTB configuration | ECS-040 | Month 2 | 2025-10-13 | 2025-10-15 | 3 | Open | PC, TC; SME-ITSM | State model, categories, assignment rules, VIP handling, OOTB form layout. | 41,20
ECS-043 | Major Incident Management configuration | ECS-040 | Month 2 | 2025-10-16 | 2025-10-17 | 2 | Open | PC, TC; SME-ITSM | P1/P2 bridge triggers, comms templates, bridge workspace, MIM role. | 42
ECS-044 | Problem Management configuration | ECS-040 | Month 2 | 2025-10-13 | 2025-10-14 | 2 | Open | PC, TC; SME-ITSM | Problem creation triggers, investigation/RCA workflow, known error publishing. | 41,21
ECS-045 | Request Management configuration (RITM + catalog flow) | ECS-040 | Month 2 | 2025-10-13 | 2025-10-14 | 2 | Open | PC, TC; SME-ITSM | RITM state model, task assignment, approval workflow, SLA. | 41,22
ECS-046 | SLA configuration & testing | ECS-040 | Month 2 | 2025-10-15 | 2025-10-16 | 2 | Open | PC, TC; SME-ITSM | P1–P4 SLA definitions, schedule attachments, breach notifications, pause conditions. | 42,24
ECS-047 | Assignment rules configuration | ECS-040 | Month 2 | 2025-10-15 | 2025-10-16 | 2 | Open | PC, TC; SME-ITSM | OOTB assignment rules, group rotation, overflow rules. | 42,24
ECS-048 | Approval workflow configuration | ECS-040 | Month 2 | 2025-10-17 | 2025-10-20 | 2 | Open | PC, TC; SME-ITSM | Approval groups, delegate rules, auto-approval thresholds, OOTB approval engine. | 45
ECS-049 | Notifications configuration | ECS-040 | Month 2 | 2025-10-21 | 2025-10-21 | 1 | Open | TC; SME-ITSM | OOTB notification templates for Incident, Problem, Request state changes. | 42,44,45
ECS-050 | Sprint 3 demo — ITSM Core | ECS-040 | Month 2 | 2025-10-23 | 2025-10-23 | 1 | Open | PC, TC; Sponsor, CustPM | Live demo of Incident lifecycle, Problem investigation, Request fulfillment. | 43,44,45,46,47,48,49
ECS-051 | Sprint 3 retro | ECS-040 | Month 2 | 2025-10-24 | 2025-10-24 | 1 | Open | EM; CustPM |  | 50
ECS-052 | ✦ MILESTONE: Sprint 3 Complete — ITSM Core Configured | ECS-040 | Month 2 | 2025-10-24 | 2025-10-24 | 0 | Open |  |  | 51
ECS-053 | SPRINT 4 — CHANGE / CAB & SERVICE CATALOG BUILD |  | Month 2 | 2025-10-27 | 2025-11-07 | 10 | Open | PC, TC; SME-ITSM, SME-Catalog | Weeks 9–10. Change/CAB OOTB build, catalog items batch 1 & 2, Employee Center baseline.
ECS-054 | Sprint 4 planning session | ECS-053 | Month 2 | 2025-10-27 | 2025-10-27 | 1 | Open | EM, SA; CustPM |  | 52
ECS-055 | Change Management — OOTB configuration | ECS-053 | Month 2 | 2025-10-27 | 2025-10-29 | 3 | Open | PC, TC; SME-ITSM | Normal/Standard/Emergency change types, CAB schedule, risk assessment, OOTB state model. | 54
ECS-056 | CAB Workbench setup & CAB process design | ECS-053 | Month 2 | 2025-10-30 | 2025-10-31 | 2 | Open | PC; SME-ITSM | CAB meeting workspace, agenda automation, change calendar, approval flow. | 55
ECS-057 | Service catalog — item build batch 1 (items 1–5) | ECS-053 | Month 2 | 2025-10-27 | 2025-10-29 | 3 | Open | PC, TC; SME-Catalog | Build highest-priority 5 catalog items with OOTB variables, workflows, and approvals. | 54,36
ECS-058 | Service catalog — item build batch 2 (items 6–10) | ECS-053 | Month 2 | 2025-10-30 | 2025-11-03 | 3 | Open | PC, TC; SME-Catalog |  | 57
ECS-059 | Fulfillment workflow configuration | ECS-053 | Month 2 | 2025-10-31 | 2025-11-03 | 2 | Open | TC; SME-Catalog | Flow designer workflows for catalog items; task assignment and SLA. | 57
ECS-060 | Employee Center portal — baseline setup | ECS-053 | Month 2 | 2025-10-29 | 2025-10-31 | 3 | Open | TC; SME-HR | Portal branding baseline, taxonomy, IT & HR topic pages, announcement widget. | 54
ECS-061 | Sprint 4 demo — Change, Catalog, Employee Center | ECS-053 | Month 2 | 2025-11-06 | 2025-11-06 | 1 | Open | PC, TC; Sponsor, CustPM |  | 56,58,59,60
ECS-062 | Sprint 4 retro | ECS-053 | Month 2 | 2025-11-07 | 2025-11-07 | 1 | Open | EM; CustPM |  | 61
ECS-063 | ✦ MILESTONE: Sprint 4 Complete — Core Build Done | ECS-053 | Month 2 | 2025-11-07 | 2025-11-07 | 0 | Open |  |  | 62
ECS-064 | SPRINT 5 — EMPLOYEE EXPERIENCE & PLATFORM ANALYTICS |  | Month 3 | 2025-11-10 | 2025-11-21 | 10 | Open | PC, TC; SME-HR, CustPM | Weeks 11–12. Employee Center, Knowledge, Virtual Agent, Predictive Intelligence, PA.
ECS-065 | Sprint 5 planning session | ECS-064 | Month 3 | 2025-11-10 | 2025-11-10 | 1 | Open | EM, SA; CustPM |  | 63
ECS-066 | Employee Center — branding, navigation & content finalization | ECS-064 | Month 3 | 2025-11-10 | 2025-11-12 | 3 | Open | TC; SME-HR | Custom branding, mega-menu, topic taxonomy, HR catalog integration. | 65,60
ECS-067 | Knowledge Management — article structure & curation | ECS-064 | Month 3 | 2025-11-10 | 2025-11-11 | 2 | Open | PC; SME-ITSM, SME-HR | KB category structure, article templates, publishing workflow, search optimization. | 65
ECS-068 | Virtual Agent — topic design workshop | ECS-064 | Month 3 | 2025-11-10 | 2025-11-10 | 1 | Open | PC; SME-ITSM, SME-HR | Prioritize top 5–8 topics; define intent, conversation flows, fallback handling. | 65
ECS-069 | Virtual Agent — priority topic build & testing | ECS-064 | Month 3 | 2025-11-11 | 2025-11-13 | 3 | Open | TC; SME-ITSM | Build topics in NLU Workbench; test with sample utterances; embed in Employee Center. | 68,67
ECS-070 | Predictive Intelligence — data readiness validation | ECS-064 | Month 3 | 2025-11-13 | 2025-11-14 | 2 | Open | SA, TC; TechLead | Validate incident/request history volume and quality for ML training readiness. | 65
ECS-071 | Platform Analytics — dashboard & KPI design workshop | ECS-064 | Month 3 | 2025-11-10 | 2025-11-10 | 1 | Open | PC; CustPM, Sponsor | Define KPIs per process area; map to PA data sources; agree dashboard layouts. | 65
ECS-072 | Platform Analytics — KPI and dashboard configuration | ECS-064 | Month 3 | 2025-11-11 | 2025-11-13 | 3 | Open | TC; CustPM | Build PA indicators, breakdowns, and dashboards in ServiceNow. | 71
ECS-073 | Sprint 5 demo — Employee Experience & Analytics | ECS-064 | Month 3 | 2025-11-20 | 2025-11-20 | 1 | Open | PC, TC; Sponsor, CustPM | Demo: Employee Center, Virtual Agent conversation, PA dashboard. | 66,69,70,72
ECS-074 | Sprint 5 retro | ECS-064 | Month 3 | 2025-11-21 | 2025-11-21 | 1 | Open | EM; CustPM |  | 73
ECS-075 | ✦ MILESTONE: Sprint 5 Complete | ECS-064 | Month 3 | 2025-11-21 | 2025-11-21 | 0 | Open |  |  | 74
ECS-076 | SPRINT 6 — HAM, CATALOG COMPLETION & STABILIZATION |  | Month 3 | 2025-11-24 | 2025-12-05 | 10 | Open | SA, TC; SME-Asset, TechLead | Weeks 13–14. HAM Foundations/Realization, remaining catalog items, integration testing, stabilization.
ECS-077 | Sprint 6 planning session | ECS-076 | Month 3 | 2025-11-24 | 2025-11-24 | 1 | Open | EM, SA; CustPM |  | 75
ECS-078 | HAM Foundations — stockrooms, asset classes & models | ECS-076 | Month 3 | 2025-11-24 | 2025-11-26 | 3 | Open | SA, TC; SME-Asset | Configure stockrooms, asset classes, models per AP-04 (HAM Foundations pack). | 77
ECS-079 | HAM Realization — lifecycle states & IMAC workflow config | ECS-076 | Month 3 | 2025-11-27 | 2025-12-01 | 3 | Open | TC; SME-Asset | Receive, assign, transfer, return, retire workflows. Procurement intake. Per AP-05. | 78
ECS-080 | Service catalog — remaining items build (items 11–15) | ECS-076 | Month 3 | 2025-11-24 | 2025-11-27 | 4 | Open | PC, TC; SME-Catalog | Complete catalog to 13–15 total OOTB items; final testing and approvals. | 77,58
ECS-081 | Integration testing — all integrations (AD, SSO, SCCM, Intune) | ECS-076 | Month 3 | 2025-11-24 | 2025-11-27 | 4 | Open | TC; TechLead | End-to-end integration validation; user sync, SSO login, CMDB data flow. | 77,31,34
ECS-082 | Environment stabilization & performance testing | ECS-076 | Month 3 | 2025-11-28 | 2025-12-02 | 3 | Open | SA, TC; TechLead | Full regression sweep; performance test under expected load; fix blocking issues. | 79,80,81
ECS-083 | Sprint 6 demo — HAM, Catalog, Stabilization | ECS-076 | Month 3 | 2025-12-04 | 2025-12-04 | 1 | Open | SA, TC; Sponsor, CustPM | Demo full HAM lifecycle, completed catalog, performance metrics. | 79,80,82
ECS-084 | Sprint 6 retro | ECS-076 | Month 3 | 2025-12-05 | 2025-12-05 | 1 | Open | EM; CustPM |  | 83
ECS-085 | ✦ MILESTONE: Sprint 6 Complete — Build Phase Done | ECS-076 | Month 3 | 2025-12-05 | 2025-12-05 | 0 | Open |  |  | 84
ECS-086 | SPRINT 7 — USER ACCEPTANCE TESTING |  | Stage 3 — Deliver | 2025-12-08 | 2025-12-19 | 10 | Open | PC, EM; CustPM | Weeks 15–16. Customer-led testing across all process areas.
ECS-087 | UAT test scenarios distributed to customer | ECS-086 | Stage 3 — Deliver | 2025-12-08 | 2025-12-08 | 1 | Open | PC; CustPM | Distribute CLT-UAT-02 scenario packs per process area. | 85
ECS-088 | UAT kickoff & tester orientation | ECS-086 | Stage 3 — Deliver | 2025-12-08 | 2025-12-08 | 1 | Open | EM, PC; CustPM | Walkthrough of UAT process, defect logging via CLT-UAT-03, escalation path. | 85
ECS-089 | UAT execution — ITSM (Incident, Problem, Change, Request) | ECS-086 | Stage 3 — Deliver | 2025-12-09 | 2025-12-11 | 3 | Open | PC; SME-ITSM | Customer executes test scenarios; ECS monitors and assists without leading. | 87,88
ECS-090 | UAT execution — Service Catalog & Employee Center | ECS-086 | Stage 3 — Deliver | 2025-12-09 | 2025-12-11 | 3 | Open | PC; SME-Catalog, SME-HR |  | 87,88
ECS-091 | UAT execution — Virtual Agent & Knowledge | ECS-086 | Stage 3 — Deliver | 2025-12-09 | 2025-12-11 | 3 | Open | PC; SME-HR, SME-ITSM |  | 87,88
ECS-092 | UAT execution — HAM lifecycle | ECS-086 | Stage 3 — Deliver | 2025-12-10 | 2025-12-11 | 2 | Open | SA; SME-Asset |  | 87,88
ECS-093 | UAT defect triage & remediation | ECS-086 | Stage 3 — Deliver | 2025-12-12 | 2025-12-16 | 3 | Open | PC, TC; CustPM | Triage defects: fix blocking issues; log non-blocking as post-go-live backlog. | 89,90,91,92
ECS-094 | UAT sign-off (customer) | ECS-086 | Stage 3 — Deliver | 2025-12-19 | 2025-12-19 | 1 | Open | EM; Sponsor, CustPM | Formal sign-off on UAT completion. Required before go-live authorization. | 93
ECS-095 | ✦ MILESTONE: UAT Sign-Off Received | ECS-086 | Stage 3 — Deliver | 2025-12-19 | 2025-12-19 | 0 | Open |  |  | 94
ECS-096 | SPRINT 7 — GO-LIVE PREPARATION & EXECUTION |  | Stage 3 — Deliver | 2025-12-22 | 2025-12-24 | 3 | Open | EM, SA; Sponsor, CustPM | End of Week 16 / start of Week 17. Final go/no-go and production cutover.
ECS-097 | Go-live checklist completion & readiness review | ECS-096 | Stage 3 — Deliver | 2025-12-22 | 2025-12-22 | 1 | Open | EM, SA; Sponsor, CustPM | CLT-CO-01 go-live checklist reviewed and signed. Confirm helpdesk readiness. | 95
ECS-098 | Go-live execution — production cutover | ECS-096 | Stage 3 — Deliver | 2025-12-23 | 2025-12-23 | 1 | Open | SA, TC; TechLead | Promote update sets to prod, validate, flip DNS/SSO to prod, comms broadcast. | 97
ECS-099 | ✦ MILESTONE: GO-LIVE | ECS-096 | Stage 3 — Deliver | 2025-12-23 | 2025-12-23 | 0 | Open |  |  | 98
ECS-100 | SPRINT 8 — HYPERCARE |  | Stage 4 — Close | 2025-12-24 | 2026-01-02 | 8 | Open | EM, PC; CustPM | Weeks 17–18. Production support, knowledge transfer, and operational handoff.
ECS-101 | Daily stand-ups & production issue triage | ECS-100 | Stage 4 — Close | 2025-12-24 | 2025-12-31 | 6 | Open | EM, PC; CustPM | 30-min daily stand-up; ECS on standby for P1/P2 escalations during hypercare window. | 99
ECS-102 | Knowledge transfer sessions — process area owners | ECS-100 | Stage 4 — Close | 2025-12-24 | 2025-12-29 | 4 | Open | PC, SA; SME-ITSM, SME-Catalog, SME-HR, SME-Asset | Structured handoff sessions: admin procedures, OOTB config rationale, run-book. | 99
ECS-103 | Operational handoff documentation | ECS-100 | Stage 4 — Close | 2025-12-25 | 2025-12-30 | 4 | Open | PC; CustPM | CLT-CO-03, CLT-CO-04, CLT-CO-06: expectations, handoff pack, SOPs delivered. | 99
ECS-104 | Post-go-live ownership matrix finalized | ECS-100 | Stage 4 — Close | 2025-12-31 | 2025-12-31 | 1 | Open | EM; Sponsor, CustPM | CLT-CO-05: per-process owner, escalation path, support tier. Customer-signed. | 103
ECS-105 | Engagement closeout & lessons learned | ECS-100 | Stage 4 — Close | 2026-01-01 | 2026-01-01 | 1 | Open | EM; Sponsor | INT-LL-01 completed. Closeout deck. Final invoice trigger. Retro with ECS PM. | 101,102,104
ECS-106 | Continuous improvement roadmap delivered | ECS-100 | Stage 4 — Close | 2026-01-01 | 2026-01-01 | 1 | Open | PC, SA; Sponsor, CustPM | CLT-CO-07: post-engagement backlog of deferred items, follow-on engagement framing. | 104
ECS-107 | ✦ MILESTONE: Engagement Complete | ECS-100 | Stage 4 — Close | 2026-01-02 | 2026-01-02 | 0 | Open |  |  | 105,106
ECS-108 | Weekly status report (ECS EM → Customer PM) |  | Governance | 2025-09-10 | 2025-09-10 | 1 | Open | EM; CustPM | RECURRING weekly throughout engagement. SH-SG-03 template. | 9
ECS-109 | Bi-weekly sponsor sync (EM + Sponsor) |  | Governance | 2025-09-12 | 2025-09-12 | 1 | Open | EM; Sponsor | RECURRING bi-weekly. INT-TBV-04 agenda template. Health RAG status reviewed. | 4
ECS-110 | Customization Council review (monthly) |  | Governance | 2025-09-19 | 2025-09-19 | 1 | Open | EM, SA; Sponsor, CustPM | RECURRING monthly. Any OOTB deviation requests reviewed and triaged. | 8
Formulas:
planned_end_date = WORKDAY([planned_start_date],9)

## Roles Reference
ECS FEDERAL — ENGAGEMENT ROLES REFERENCE
CODE | ROLE TITLE | TEAM | RESPONSIBILITIES | TYPICAL FTE COMMITMENT
EM | Engagement Manager | ECS | Overall engagement delivery, governance, escalation, sponsor relationship, risk management. | 100% during engagement
SA | Solution Architect | ECS | Platform architecture, CSDM, technical decisions, accelerator pack design, integration oversight. | 100% during engagement
PC | Process Consultant | ECS | Workshops facilitation, OOTB defense, discipline how-to guides, UAT support, training. | 100% during engagement
TC | Technical Consultant | ECS | ServiceNow configuration, scripting (minimal), data loads, integration builds. | 100% during engagement
PM | Practice Manager | ECS | Practice oversight, trust-but-verify reviews, escalation authority, lessons learned. | 20% throughout
Sponsor | Project Sponsor | Customer | Executive decisions, budget authority, customization council, go-live authorization. | 4–8 hrs/week
CustPM | Customer Project Manager | Customer | Day-to-day coordination, SME scheduling, status reporting to sponsor, action item tracking. | 50–100% during engagement
TechLead | Customer Technical Lead | Customer | Environment access, integration credentials, CI/CD pipeline, technical approvals. | 25–50% during engagement
SME-ITSM | ITSM Subject Matter Expert | Customer | Process decisions for Incident, Problem, Change, Request. Workshop participation. | 50% during relevant sprints
SME-Catalog | Catalog SME | Customer | Catalog item content, category decisions, fulfillment workflow approvals. | 50% during Sprints 2, 4, 6
SME-HR | HR / Employee Exp SME | Customer | Employee Center content, Virtual Agent topics, knowledge article content. | 50% during Sprint 5
SME-Asset | Asset Management SME | Customer | HAM scope, stockroom structure, lifecycle workflow decisions. | 50% during Sprint 6
End-Users | UAT Testers | Customer | Execute UAT test scenarios per process area. Log defects via ECS defect template. | 100% during UAT (Weeks 15–16)
RACI LEGEND
R | Responsible | Does the work. Assigned as ECS Primary or Customer Primary.
A | Accountable | Owns the outcome. One person per task.
C | Consulted | Provides input. Assigned as ECS Support or Customer Support.
I | Informed | Receives status updates. Tracked via Governance cadence.

## Instructions
HOW TO USE THIS PROJECT PLAN
STEP | INSTRUCTION | WHERE
1. Set Start Date | Go to the 'Project Plan' tab. In cell B3, enter your engagement start date (first Monday of Sprint 0). All 110 task dates recalculate automatically via WORKDAY formulas. | Project Plan · B3
2. Tailor the Plan | Adjust task names, durations, and dependencies to match your specific engagement scope. Add customer-specific tasks in the appropriate sprint section. Do not change column order — the MS Project import depends on it. | Project Plan
3. Import to MS Project | Go to the 'MS Project Import' tab. Save that sheet as CSV (UTF-8). Open MS Project > File > Import > CSV. Map: Name→Name, Duration→Duration, Start→Start, Finish→Finish, Predecessors→Predecessors, Resource Names→Resource Names. Select 'Create a new project'. Set working calendar to match your engagement. | MS Project Import tab
4. Import to ServiceNow PPM | Go to the 'SNow PPM Import' tab. Copy the data range (headers + rows). In ServiceNow: Modules > Project > Projects > [your project] > Task Import. Paste or upload the CSV. Map fields: short_description, planned_start_date, planned_end_date, assigned_to_role, description. The task_number field becomes the display number in SNow. | SNow PPM Import tab
5. Track Status | Update the 'Status' column (col N) and '% Complete' column (col O) on the Project Plan tab throughout the engagement. Status values: Not Started / In Progress / Complete / Blocked. | Project Plan · cols N, O
6. Governance | Rows 108–110 are recurring governance tasks (weekly status, bi-weekly sponsor sync, customization council). These are not in the MS Project/SNow import sheets — add them manually as recurring tasks in your project tool. | Project Plan · rows 108–110
7. Dependency Logic | The Predecessors column lists task IDs (column A). A comma-separated list means 'finish-to-start' for all listed tasks. When a predecessor task date shifts, update the start_day offset in the source data and re-run, or adjust dates manually in MS Project/SNow after import. | Project Plan · col I
8. Roles | See the 'Roles Reference' tab for full role definitions and RACI legend. ECS Primary = Responsible (does the work). Customer Primary = Accountable or key Consulted. Update role codes to match named individuals when running a live engagement. | Roles Reference tab