CLIENT DELIVERABLE - CUTOVER RUNBOOK

Connection ServiceNow

Go-Live Cutover Runbook

The sequenced, owned, reversible plan to move Connection to production - Week 16

ECS Federal - ServiceNow Practice

Audience: Connection Technical Lead & Platform Team; ECS Delivery

Companion to: Go-Live Readiness Checklist - Customer Dependency Tracker - Operational Handoff Pack

Document ID: DEL-CONN-CUT-01     ·     Version: 1.0 (template)     ·     Status: Template

ECS Federal - ServiceNow Practice - Confidential

# How to Use This Runbook

This runbook governs the production cutover at Go-Live (Week 16). It is sequenced, every step has an owner and a time, and it includes a rollback plan. Fill the [bracketed] specifics during cutover planning (Sprint 7). Do not start cutover until the Go-Live Readiness Checklist clears its blocking gates and the Sponsor authorizes.

Golden rule: no step proceeds without its predecessor validated. If validation fails and cannot be resolved in the window, invoke the Rollback Plan (Section 6).

# 1.  Cutover Overview

| Item | Detail |
| --- | --- |
| Cutover window | [Date / time], [duration] - low-traffic window agreed with Connection |
| Change freeze | Configuration freeze from [T-2 days]; only cutover changes permitted |
| Go/No-Go gate | Readiness Checklist blocking gates Met + Sponsor authorization |
| Cutover lead | ECS Solution Architect; Connection Technical Lead co-lead |
| Rollback decision | ECS EM + Connection Sponsor (see Section 6) |
| Comms owner | ECS Engagement Manager + Connection PM |

# 2.  Pre-Cutover Checklist (T-minus)

| When | Activity | Owner | Done |
| --- | --- | --- | --- |
| T-5 days | Go-Live Readiness Checklist blocking gates confirmed Met | EM | [ ] |
| T-2 days | Configuration freeze in effect; final update sets identified and ordered | SA | [ ] |
| T-2 days | Production clone/backup taken (rollback point) | Tech Lead | [ ] |
| T-1 day | Cutover comms sent to stakeholders and end users | EM + PM | [ ] |
| T-1 day | Cutover team confirmed and on standby with the schedule | SA | [ ] |
| T-0 | Final go/no-go held; Sponsor authorizes | EM + Sponsor | [ ] |

# 3.  Cutover Sequence

Execute in order. Each step records start/end time and a pass/fail validation before proceeding.

| # | Step | Owner | Validation |
| --- | --- | --- | --- |
| 1 | Final data sync/load (delta from sub-prod); confirm Foundation + CMDB data current | Tech Consultant | Record counts match; no load errors |
| 2 | Promote final update sets in order (dev -> test -> prod); resolve any preview conflicts | Solution Architect | All sets committed; no skipped records unresolved |
| 3 | Re-point integrations to production: AD/SSO, SCCM, Intune, email | Integration Engineer | Each integration test passes against prod |
| 4 | Cut over Vonage CTI: re-point OpenFrame/connector to the production Vonage tenant | CTI Engineer | Test inbound call -> Interaction -> Incident in prod |
| 5 | Run scheduled jobs / first Discovery + connector imports; verify CMDB populates | Tech Consultant | Sample CIs present; CMDB Health at baseline |
| 6 | Enable user access (SSO, roles via AD groups); confirm agent and EC access | Solution Architect | Sample users in each role can log in and work |
| 7 | Publish Employee Center; enable Virtual Agent and Knowledge | Process Consultant | EC live; VA responds; KB searchable |
| 8 | Final smoke tests (Section 5) | UAT Lead | All smoke tests pass |

# 4.  Validation & Smoke Tests

Run a fast subset of the UAT end-to-end suites against production to confirm the platform works before declaring go-live:

Incident: create via Employee Center and via phone (Vonage) - both reach an agent and resolve.

Request: order a catalog item, approve, and confirm fulfillment routing.

Change: raise a change tied to a CI; confirm risk scoring and CAB routing.

Self-service: Employee Center search, Virtual Agent, and knowledge return results.

Identity: SSO login and role-based access for a sample of each role.

Integrations: confirm AD/SSO, SCCM/Intune CI data, email, and CTI in production.

If any smoke test fails and cannot be resolved within the window, escalate to the rollback decision (Section 6).

# 5.  Rollback Plan

Rollback returns Connection to the prior state if cutover cannot complete successfully within the window.

## Rollback triggers

A blocking step fails validation and cannot be resolved within the cutover window.

A critical integration (SSO, CTI, or CMDB data) cannot be made functional in production.

A P1 issue with no workaround is found during smoke testing.

## Rollback decision and steps

Decision authority: ECS Engagement Manager + Connection Executive Sponsor.

1. Halt the cutover sequence; freeze further changes.

2. Restore from the production clone/backup taken at T-2 days (or revert promoted update sets).

3. Re-point integrations to their prior endpoints.

4. Confirm the prior state is functional; notify stakeholders of the rollback and the revised plan.

5. Hold a rapid retro; agree corrective actions and a new cutover date.

# 6.  Communications Plan

| Timing | Message | Audience | Owner |
| --- | --- | --- | --- |
| T-1 day | Cutover window, expected impact, where to get help | All users + stakeholders | EM + PM |
| Cutover start | Cutover has begun; system unavailable [if applicable] | Stakeholders | PM |
| Go-live confirmed | Platform is live; how to access; support channels | All users | EM + PM |
| If rollback | Rollback invoked; prior system remains; revised date | Stakeholders | EM + Sponsor |

# 7.  Go / No-Go Decision

The final go/no-go is held at T-0. GO requires: all Go-Live Readiness Checklist blocking gates Met, the pre-cutover checklist complete, and explicit authorization from the Connection Executive Sponsor and Product Owner. Any unmet blocking gate is a NO-GO unless the Sponsor accepts a documented risk with a mitigation.

# 8.  Post-Cutover & Hypercare Handoff

Confirm go-live in the status report and Executive Health Dashboard.

Open the Hypercare window: daily standups (Week 1), ECS L2+ escalation support.

Monitor platform health, scheduled jobs, and early-life incidents against the baseline.

Hand over per the Operational Handoff Pack at Hypercare exit.

Cutover is not 'done' at go-live - it is done when Hypercare exit criteria are met and steady-state ownership is accepted.