## Delivery Readiness Audit
CONNECTION - DELIVERY READINESS AUDIT (start to finish; ECS + customer lenses)
Audited against SOW v2.0 across the full lifecycle. Status: Have ¦ Partial ¦ Gap. Priority: P1 (close before/at the relevant phase) ¦ P2 ¦ P3. The biggest delivery risk is customer dependencies (SOW Sec 6).
# | Phase | Lens | Capability / Artifact | Status | What exists today | Gap / what's missing | Delivery risk if unaddressed | Recommendation | Priority
1 | Setup / Sprint 0 | Both | Team & client onboarding | Have | Onboarding guides, vision, role quick-ref, kickoff deck, checklist | - | - | Maintain | P3
2 | Setup / Sprint 0 | Both | Governance operating model | Have | Governance Charter, Delivery Guidelines, Triage/RAID | - | - | Maintain | P3
3 | Setup / Sprint 0 | ECS | Project plan & schedule | Have | 18-week plan (Sprints 0-8); resource buildup tab | Start date (B3) not set | Dates won't flow until set | Set start date at kickoff | P3
4 | Setup / Sprint 0 | Customer | Customer Responsibilities & Dependency Tracker (full engagement) | Have | Connection_Customer_Dependency_Tracker.xlsx (all SOW Sec 6 deps, owner/due/status/impact) | - | - | Maintain weekly; flag at-risk early | P1
5 | Setup / Sprint 0 | Both | RACI matrix | Partial | Role & Accountability Quick-Ref (RACI-style) | No formal per-deliverable/per-activity RACI | Ownership ambiguity on specific deliverables | Derive a deliverable-level RACI cut | P2
6 | Setup / Sprint 0 | Both | Communication plan | Partial | Cadence defined in setup story + guidelines | No standalone comms plan artifact | Minor - cadence is known | Optional one-pager | P3
7 | Build / Sprints 1-6 | Customer | Workshop pre-reads (per module) | Gap | 18 workshop decks + scope notes; library WP_01-17 exist | Connection-tailored client pre-reads not created | Cold workshops -> weak/slow decisions -> rework (facilitation model assumes pre-warmed decisions) | ADAPT from library WP_01-17 for in-scope modules | P2
8 | Build / Sprints 1-6 | ECS | Workshop decks & facilitation | Have | 18 client decks, scope notes, facilitation guide | - | - | Maintain | P3
9 | Build / Sprints 1-6 | Customer | Accelerator data packs | Have | 13 packs incl. Vonage; index README | - | - | Distribute on schedule | P3
10 | Build / Sprints 1-6 | ECS | Configuration backlog (stories) | Have | 141 config stories, SN Agile-ready, AC + DoD | - | - | Import to SN Agile | P2
11 | Build / Sprints 1-6 | ECS | Project delivery backlog (non-dev) | Have | 55 delivery stories across 9 work-streams | - | - | Import; track on dashboard | P3
12 | Build / Sprints 1-6 | ECS | Sprint plan & capacity model | Gap | Stories carry target sprints; resource buildup tab | No capacity-vs-load check (do ~196 stories fit team velocity over 6 sprints?) | Hidden overload -> mid-engagement slippage | BUILD - sprint-by-sprint capacity vs story-point load | P2
13 | Build / Sprints 1-6 | ECS | Definition of Ready | Gap | Definition of Done exists | No DoR (when a story may enter a sprint) | Half-baked stories enter sprints -> churn | Add a short DoR (1 page / tab) | P3
14 | Build / Sprints 1-6 | ECS | Sprint ceremonies (planning, retro) | Partial | Sprint Demo template exists | No planning agenda or retrospective template | Inconsistent ceremonies | Add planning + retro templates | P3
15 | Build / Sprints 1-6 | ECS | Per-module demo scripts | Gap | Sprint Demo shell; library INT-DS demo scripts exist | Connection demo scripts not created | Inconsistent demos; weak sign-off moments | ADAPT library demo scripts for in-scope modules | P3
16 | Build / Sprints 1-6 | Both | Decision register (running) | Partial | Triage Log (deviations) + sprint workbooks | No general open-decisions register beyond deviations | Decisions lost between workshops | Add a decisions log (or extend RAID) | P3
17 | Build / Sprints 1-6 | Both | Story/sprint acceptance & sign-off | Partial | DoD requires PO sign-off; SOW = 3-day acceptance window | No acceptance/sign-off log operationalizing the window | Acceptance drift -> PCR triggers missed | BUILD a lightweight acceptance/sign-off log | P2
18 | Build / Sprints 1-6 | ECS | Design documentation (per sprint) | Partial | Delivery story + library sprint workbooks | Connection sprint-workbook copies not yet created | Decisions not captured -> KT gaps | Copy sprint workbooks into Connection as decisions land | P3
19 | Testing | ECS | UAT end-to-end scripts + guidebook | Have | 18 E2E scripts, story traceability, guidebook, defect log | - | - | Assign testers at UAT | P2
20 | Testing | ECS | SIT / integration test scripts & test-data plan | Gap | SIT delivery story exists | No SIT script pack or test-data strategy | Integration defects surface late (AD/SSO, SCCM, Intune, CTI) | BUILD SIT scripts + a test-data plan | P2
21 | Go-Live / Cutover | ECS | Cutover Runbook | Have | Connection_Cutover_Runbook.docx (sequence, owners, validation, rollback, comms) | - | - | Finalize specifics in Sprint 7 | P1
22 | Go-Live / Cutover | Both | Go-Live Readiness Checklist (Connection) | Have | Connection_Go_Live_Readiness_Checklist.xlsx (gated go/no-go criteria) | - | - | Work it through Stage 3 | P1
23 | Go-Live / Cutover | Both | Go-Live readiness sign-off | Partial | Delivery story + DoD | No sign-off form | Authorization not formally captured | Add a sign-off form | P2
24 | Hypercare / Close | Both | Operational Handoff Pack | Gap | Library CLT-CO-03; delivery story | Ownership matrix, support model, escalation not built for Connection | Unclear steady-state ownership post-Hypercare | BUILD from library + RACI | P2
25 | Hypercare / Close | Both | Hypercare support model & exit report | Partial | Library CLT-CO-03/06; delivery story | Connection copies not created | Handover ambiguity | Copy + tailor near Go-Live | P3
26 | Hypercare / Close | ECS | KT Package (Admin + Train-the-Trainer) | Have | Admin Guide & KT, Train-the-Trainer Toolkit | - | - | Deliver at Go-Live | P3
27 | Hypercare / Close | Both | Lessons Learned & Closeout + 12-mo roadmap | Partial | Library + delivery stories | Connection copies not created | Close not documented | Produce at close | P3
28 | Governance / Scope | Both | PCR (Project Change Request) template | Gap | SOW Sec 9 PCR process referenced in guidelines | No PCR request form/template | Scope changes uncontrolled; SOW ties acceptance delays & customization #6 to PCR | BUILD a PCR form + log | P2
29 | Governance / Scope | ECS | Assumptions & Out-of-Scope register | Gap | SOW Sec 7-8 text | No tracker to manage assumptions/out-of-scope | Scope creep; assumptions unverified | Add a register (or tab in RAID) | P3
30 | Governance / Scope | ECS | Customization variance tracking | Partial | Triage/RAID has Triage Log + cap counter | Library INT-TBV-03 variance tracker (effort %) not copied | Variance % not tracked to capacity | Optional - add variance tab | P3
31 | Governance / Scope | Both | Status report, exec dashboard, deliverables matrix | Have | Weekly status, Exec Dashboard v2 (delivery metrics), SOW matrix | - | - | Run the cadence | P3
SUMMARY
Total items
Have
Partial
Gap
P1 (close first)
P2