## README - Import Guide
CONNECTION - PROJECT DELIVERY STORIES (the work most projects don't track)
Every non-development activity as a story: documentation, training, governance, testing, go-live, hypercare. Same rigor as config stories. Complements the 141-story config backlog -> together = the complete project backlog.
Why this exists
The gap | Most projects only story development. Documentation, training, governance, and PMO work get done but stay invisible to leadership - so burndown shows 'dev on track' while the rest of the team's effort is uncredited and unmanaged.
The fix | Story ALL the work, same rigor (acceptance criteria + Definition of Done). Leadership sees the whole project in real time and the team's performance shows in the numbers.
Pairs with | Connection_User_Stories_SN_Agile.xlsx (141 configuration stories). Import both -> one backlog, full picture.
How to import (ServiceNow Agile / rm_story)
1. Import EPICS first ('Epics' tab) into rm_epic (coalesce on Number).
2. Import 'Delivery Stories' into rm_story via Import Set + Transform Map.
3. Map columns to fields (same mapping as the config workbook; see that README).
4. Set State on import; refine points/owner in ServiceNow.

## Epics
CONNECTION - DELIVERY EPICS (work-streams)
One epic per work-stream. Import first -> rm_epic.
number | short_description | description | state
CONN-DEPIC-GOV | PMO & Governance (Delivery) | Project delivery work-stream: PMO & Governance. 8 stories spanning the engagement. | Draft
CONN-DEPIC-S0 | Engagement Setup (Delivery) | Project delivery work-stream: Engagement Setup. 8 stories spanning the engagement. | Draft
CONN-DEPIC-ONB | Onboarding & Enablement (Delivery) | Project delivery work-stream: Onboarding & Enablement. 2 stories spanning the engagement. | Draft
CONN-DEPIC-WS | Workshops (Delivery) | Project delivery work-stream: Workshops. 13 stories spanning the engagement. | Draft
CONN-DEPIC-DOC | Documentation (Delivery) | Project delivery work-stream: Documentation. 7 stories spanning the engagement. | Draft
CONN-DEPIC-KT | Training & Knowledge Transfer (Delivery) | Project delivery work-stream: Training & Knowledge Transfer. 3 stories spanning the engagement. | Draft
CONN-DEPIC-QA | Testing & Quality (Delivery) | Project delivery work-stream: Testing & Quality. 5 stories spanning the engagement. | Draft
CONN-DEPIC-GL | Go-Live & Cutover (Delivery) | Project delivery work-stream: Go-Live & Cutover. 4 stories spanning the engagement. | Draft
CONN-DEPIC-CO | Hypercare & Closeout (Delivery) | Project delivery work-stream: Hypercare & Closeout. 5 stories spanning the engagement. | Draft

## Delivery Stories
CONNECTION - PROJECT DELIVERY STORIES
Non-development work, storied with acceptance criteria + DoD + traceability to the SOW deliverable/artifact.
number | epic | work type | short_description | description | acceptance_criteria | definition_of_done | story_points | priority | sprint | owner (role) | traceability | state
CONN-GOV-001 | PMO & Governance | Delivery | Issue the weekly status report | As a Engagement Manager, I want a weekly status report issued to the Sponsor and PM, so that leadership sees progress, risks, and decisions every week. | AC1: Given the cadence, When each Friday arrives, Then a status report is issued with RAG by workstream, accomplishments, risks, and decisions needed. AC2: Given a Yellow/Red status, When reported, Then a Monday 1:1 and mitigation are triggered. AC3: Given the report, When produced, Then it uses the approved template and is stored in 02_Delivery. | See 'Definition of Done' tab | PM | 3 - Moderate | All sprints | Engagement Manager | Connection_Weekly_Status_Report_TEMPLATE.docx | Draft
CONN-GOV-002 | PMO & Governance | Delivery | Maintain the Executive Health Dashboard | As a Engagement Manager, I want the one-page exec health dashboard kept current, so that Sponsor and ECS leadership review health in real time. | AC1: Given the review cadence, When a steering/sponsor review occurs, Then the dashboard reflects current RAG, KPIs, and top risks/decisions. AC2: Given the 6 health vectors, When updated, Then each reflects the latest signal. AC3: Given the dashboard, When shared, Then it is client-safe and current. | See 'Definition of Done' tab | PM | 3 - Moderate | All sprints | Engagement Manager | Connection_Executive_Health_Dashboard.pptx | Draft
CONN-GOV-003 | PMO & Governance | Delivery | Operate the Governance Triage Log / RAID | As a Engagement Manager, I want the triage log and RAID kept current, so that every deviation and risk is transparent to both teams. | AC1: Given a deviation request, When raised, Then it is logged within 24 hours with disposition. AC2: Given the customization cap, When approached, Then the count and remaining-before-PCR are visible. AC3: Given RAID items, When reviewed weekly, Then material items surface in the status report. | See 'Definition of Done' tab | PM | 3 - Moderate | All sprints | Engagement Manager | Connection_Governance_Triage_and_RAID.xlsx | Draft
CONN-GOV-004 | PMO & Governance | Delivery | Run the Customization Council | As a Engagement Manager, I want the weekly Customization Council operated, so that OOTB discipline is enforced and deviations are governed. | AC1: Given pending requests, When the weekly slot arrives, Then the Council reviews each with an impact assessment and records the two-key decision. AC2: Given no requests, When the slot arrives, Then the meeting is canceled. AC3: Given a decision, When made, Then it is logged in the Triage Log within 24 hours. | See 'Definition of Done' tab | PM | 3 - Moderate | All sprints | Engagement Manager | Engagement Delivery Guidelines | Draft
CONN-GOV-005 | PMO & Governance | Delivery | Maintain the Baseline Risk Register | As a Engagement Manager, I want a current risk register maintained, so that risks are visible and actively managed. | AC1: Given Sprint 0, When set up, Then the register is initialized with known risks, owners, and mitigations. AC2: Given a new risk, When identified, Then it is added with severity and owner. AC3: Given the register, When reviewed, Then it informs the status report and dashboard. | See 'Definition of Done' tab | PM | 2 | Sprint 0 | Engagement Manager | Connection_Governance_Triage_and_RAID.xlsx (RAID) | Draft
CONN-GOV-006 | PMO & Governance | Delivery | Run bi-weekly Sponsor syncs | As a Engagement Manager, I want bi-weekly Sponsor syncs run with agenda and notes, so that the Sponsor stays aligned and sentiment is tracked. | AC1: Given the cadence, When each sync occurs, Then an agenda is shared and decisions/notes are captured. AC2: Given a concern, When raised, Then it is logged and actioned. AC3: Given sentiment, When assessed, Then it feeds the health dashboard. | See 'Definition of Done' tab | PM | 2 | All sprints | Engagement Manager | Sponsor Sync (trust-but-verify) | Draft
CONN-GOV-007 | PMO & Governance | Delivery | Run monthly Steering reviews | As a Engagement Manager, I want monthly steering reviews run with leadership, so that leadership reviews outcomes, KPIs, and roadmap. | AC1: Given the monthly cadence, When a review occurs, Then outcomes, KPIs, and the roadmap are presented. AC2: Given a decision, When made, Then it is recorded. AC3: Given the review, When complete, Then actions are tracked. | See 'Definition of Done' tab | PM | 2 | Monthly | Engagement Manager | Executive Health Dashboard | Draft
CONN-GOV-008 | PMO & Governance | Delivery | Report trust-but-verify health to practice management | As a Engagement Manager, I want weekly engagement-health metrics reported to ECS practice management, so that practice leadership supports early without micromanaging. | AC1: Given Friday COB, When metrics are sent, Then velocity, customization count, and dependency slips are reported with RAG. AC2: Given Yellow/Red, When reported, Then a Monday 1:1 plans the response. AC3: Given the report, When produced, Then it uses the trust-but-verify model. | See 'Definition of Done' tab | PM | 2 | All sprints | Engagement Manager | Engagement Delivery Guidelines | Draft
CONN-S0-001 | Engagement Setup | Delivery | Run the internal ECS kickoff and assign consultants | As a Engagement Manager, I want an internal ECS kickoff held and the team assigned, so that the delivery team is aligned and ready before customer kickoff. | AC1: Given the SOW, When the internal kickoff runs, Then scope is reviewed and roles/decision-rights are confirmed. AC2: Given the team, When assigned, Then each role and reading path is set (per onboarding). AC3: Given tooling, When loaded, Then backlog and templates are ready. | See 'Definition of Done' tab | PM | 2 | Sprint 0 | Engagement Manager | Connection_Team_Onboarding_and_Vision.docx | Draft
CONN-S0-002 | Engagement Setup | Delivery | Run the customer kickoff meeting | As a Engagement Manager, I want the joint customer kickoff delivered, so that Connection and ECS start aligned on goals, journey, and roles. | AC1: Given the kickoff deck, When delivered, Then the 18-week journey, scope, roles, and governance are walked through. AC2: Given stakeholders, When present, Then questions are addressed and next steps agreed. AC3: Given the meeting, When complete, Then notes and actions are recorded. | See 'Definition of Done' tab | PM | 2 | Sprint 0 | Engagement Manager | Connection_Kickoff_Deck.pptx | Draft
CONN-S0-003 | Engagement Setup | 2 - High | Run the governance & decision-rights workshop and sign the Council charter | As a Engagement Manager, I want the governance workshop run and the Customization Council charter signed, so that decision rights and the operating model are agreed before build. | AC1: Given the workshop, When run, Then decision rights, RACI, and escalation are agreed. AC2: Given the charter, When signed, Then the Council quorum, cadence, and two-key model are in effect. AC3: Given outputs, When recorded, Then they are stored and referenced. | See 'Definition of Done' tab | PM | 3 | Sprint 0 | Engagement Manager | Customer_Governance_Charter.docx | Draft
CONN-S0-004 | Engagement Setup | Delivery | Establish the communication plan and cadence | As a Engagement Manager, I want the communication plan and meeting cadence established, so that everyone knows when and how the engagement communicates. | AC1: Given Sprint 0, When set, Then weekly status, bi-weekly sponsor sync, and sprint demos are scheduled. AC2: Given the plan, When shared, Then audiences and channels are clear. AC3: Given cadence, When live, Then invites are issued. | See 'Definition of Done' tab | PM | 1 | Sprint 0 | Engagement Manager | Communication plan | Draft
CONN-S0-005 | Engagement Setup | Delivery | Distribute the Foundation Data Workbooks | As a Process Consultant, I want the accelerator-pack data workbooks distributed to Connection, so that customer data collection starts early to enable demos. | AC1: Given Sprint 0, When distributed, Then the Foundation and in-scope packs are handed to the right owners. AC2: Given the workbooks, When issued, Then due dates and instructions are clear. AC3: Given collection, When underway, Then progress is tracked in the onboarding checklist. | See 'Definition of Done' tab | PM | 2 | Sprint 0 | Process Consultant | 02_Delivery/Accelerator_Packs/ | Draft
CONN-S0-006 | Engagement Setup | Delivery | Confirm environments provisioned and access granted | As a Solution Architect, I want sub-prod/prod environments and ECS access confirmed, so that the team can build from Sprint 1. | AC1: Given provisioning, When complete, Then sub-prod and prod exist with ECS admin access. AC2: Given credentials, When set, Then they are vaulted and least-privilege. AC3: Given readiness, When validated, Then it is checked off in the readiness tracker. | See 'Definition of Done' tab | PM | 2 | Sprint 0 | Solution Architect | Onboarding Checklist | Draft
CONN-S0-007 | Engagement Setup | Delivery | Complete stakeholder and SME mapping | As a Engagement Manager, I want stakeholder and SME mapping completed, so that the right people are engaged per process area. | AC1: Given the org, When mapped, Then SMEs, decision owners, and change champions are named per area. AC2: Given gaps, When found, Then they are escalated to the Sponsor. AC3: Given the map, When complete, Then it informs workshop scheduling. | See 'Definition of Done' tab | PM | 1 | Sprint 0 | Engagement Manager | Stakeholder Mapping | Draft
CONN-S0-008 | Engagement Setup | Delivery | Pass the Sprint 0 readiness gate | As a Engagement Manager, I want the Sprint 0 readiness validation completed, so that build does not start until dependencies are met. | AC1: Given the readiness checklist, When validated, Then env, access, governance, data pack, and risks are confirmed. AC2: Given an unmet item, When found, Then a dependency-slip conversation occurs with the Sponsor. AC3: Given the gate, When passed, Then the Sprint 0 Complete milestone is set. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 0 | Engagement Manager | Connection_Onboarding_Checklist.xlsx | Draft
CONN-ONB-001 | Onboarding & Enablement | Delivery | Deliver the internal team onboarding package | As a Engagement Manager, I want the ECS team onboarded via the vision/guidelines/role materials, so that the team absorbs the approach by role and starts aligned. | AC1: Given the onboarding set, When delivered, Then each consultant has read their role path. AC2: Given the vision, When shared, Then the OOTB-first discipline and curate-don't-copy principle are understood. AC3: Given onboarding, When complete, Then the team can execute the delivery guidelines. | See 'Definition of Done' tab | Onboarding | 2 | Sprint 0 | Engagement Manager | 01_Onboarding/Internal_Team/ | Draft
CONN-ONB-002 | Onboarding & Enablement | Delivery | Deliver the client onboarding package | As a Process Consultant, I want Connection onboarded via the client guide and kickoff, so that the client knows what to expect and their accountabilities. | AC1: Given the client guide + deck, When delivered, Then roles, journey, governance, and checks are clear to Connection. AC2: Given the Sponsor/PM, When onboarded, Then their accountabilities are confirmed. AC3: Given onboarding, When complete, Then the client is ready for Sprint 0. | See 'Definition of Done' tab | Onboarding | 2 | Sprint 0 | Process Consultant | 01_Onboarding/Client_Facing/ | Draft
CONN-WS-001 | Workshops | Workshop | Facilitate and sign off the Platform Foundation workshop(s) | As a Process Consultant, I want the Platform Foundation workshop(s) facilitated to signed-off decisions, so that the Platform Foundation configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the Platform Foundation workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 1 | Process Consultant | Connection_Platform_Foundation_Workshop.pptx + Scope Notes | Draft
CONN-WS-002 | Workshops | Workshop | Facilitate and sign off the CSDM workshop(s) | As a Process Consultant, I want the CSDM workshop(s) facilitated to signed-off decisions, so that the CSDM configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the CSDM workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 1 | Process Consultant | Connection_CSDM_Workshop.pptx + Scope Notes | Draft
CONN-WS-003 | Workshops | Workshop | Facilitate and sign off the CMDB & Discovery workshop(s) | As a Process Consultant, I want the CMDB & Discovery workshop(s) facilitated to signed-off decisions, so that the CMDB & Discovery configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the CMDB & Discovery workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 2 | Process Consultant | Connection_CMDB_Workshop.pptx + Scope Notes | Draft
CONN-WS-004 | Workshops | Workshop | Facilitate and sign off the Incident, Problem & Major Incident workshop(s) | As a Process Consultant, I want the Incident, Problem & Major Incident workshop(s) facilitated to signed-off decisions, so that the Incident, Problem & Major Incident configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the Incident, Problem & Major Incident workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 3 | Process Consultant | Connection_Incident_Workshop.pptx + Scope Notes | Draft
CONN-WS-005 | Workshops | Workshop | Facilitate and sign off the Change workshop(s) | As a Process Consultant, I want the Change workshop(s) facilitated to signed-off decisions, so that the Change configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the Change workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 4 | Process Consultant | Connection_Change_Workshop.pptx + Scope Notes | Draft
CONN-WS-006 | Workshops | Workshop | Facilitate and sign off the Service Catalog workshop(s) | As a Process Consultant, I want the Service Catalog workshop(s) facilitated to signed-off decisions, so that the Service Catalog configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the Service Catalog workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 4 | Process Consultant | Connection_Service_Catalog_Workshop.pptx + Scope Notes | Draft
CONN-WS-007 | Workshops | Workshop | Facilitate and sign off the Integrations & Service Graph Connectors workshop(s) | As a Process Consultant, I want the Integrations & Service Graph Connectors workshop(s) facilitated to signed-off decisions, so that the Integrations & Service Graph Connectors configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the Integrations & Service Graph Connectors workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 3 | Process Consultant | Connection_Integrations_Workshop.pptx + Scope Notes | Draft
CONN-WS-008 | Workshops | Workshop | Facilitate and sign off the Vonage CTI & Interactions workshop(s) | As a Process Consultant, I want the Vonage CTI & Interactions workshop(s) facilitated to signed-off decisions, so that the Vonage CTI & Interactions configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the Vonage CTI & Interactions workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 4 | Process Consultant | Connection_Interactions_Vonage_CTI_Workshop.pptx + Scope Notes | Draft
CONN-WS-009 | Workshops | Workshop | Facilitate and sign off the Knowledge workshop(s) | As a Process Consultant, I want the Knowledge workshop(s) facilitated to signed-off decisions, so that the Knowledge configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the Knowledge workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 5 | Process Consultant | Connection_Knowledge_Workshop.pptx + Scope Notes | Draft
CONN-WS-010 | Workshops | Workshop | Facilitate and sign off the Employee Center & Virtual Agent workshop(s) | As a Process Consultant, I want the Employee Center & Virtual Agent workshop(s) facilitated to signed-off decisions, so that the Employee Center & Virtual Agent configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the Employee Center & Virtual Agent workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 5 | Process Consultant | Connection_Employee_Center_Workshop.pptx + Scope Notes | Draft
CONN-WS-011 | Workshops | Workshop | Facilitate and sign off the Predictive Intelligence workshop(s) | As a Process Consultant, I want the Predictive Intelligence workshop(s) facilitated to signed-off decisions, so that the Predictive Intelligence configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the Predictive Intelligence workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 5 | Process Consultant | Connection_Predictive_Intelligence_Workshop.pptx + Scope Notes | Draft
CONN-WS-012 | Workshops | Workshop | Facilitate and sign off the HAM workshop(s) | As a Process Consultant, I want the HAM workshop(s) facilitated to signed-off decisions, so that the HAM configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the HAM workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 6 | Process Consultant | Connection_HAM_Workshop.pptx + Scope Notes | Draft
CONN-WS-013 | Workshops | Workshop | Facilitate and sign off the Performance Analytics workshop(s) | As a Process Consultant, I want the Performance Analytics workshop(s) facilitated to signed-off decisions, so that the Performance Analytics configuration stories are unblocked with agreed decisions. | AC1: Given the pre-read and demo, When the Performance Analytics workshop runs, Then each in-scope decision is made in the room. AC2: Given a decision, When made, Then it is signed off by the named process owner and captured. AC3: Given a deviation, When raised, Then it is routed to the Triage Log; the workshop ends with signed-off stories (not a 'to think about' list). | See 'Definition of Done' tab | 2 | 2 - High | Sprint 6 | Process Consultant | Connection_Performance_Analytics_Workshop.pptx + Scope Notes | Draft
CONN-DOC-001 | Documentation | Documentation | Produce the Platform Architecture & CSDM Alignment Document | As a Solution Architect, I want the Month 1 architecture & CSDM alignment document produced and signed off, so that the data foundation is documented and accepted before Month 2 build. | AC1: Given the CSDM/CMDB workshop decisions, When drafted, Then the doc covers topology, CSDM alignment, CI classes/relationships, sources, and risk-scoring readiness. AC2: Given the draft, When reviewed, Then the Technical Lead and Sponsor sign off. AC3: Given the doc, When complete, Then it is built from the brand template and stored. | See 'Definition of Done' tab | 5 | 2 - High | Sprint 2 | Solution Architect | Connection_Platform_Architecture_and_CSDM_Alignment.docx | Draft
CONN-DOC-002 | Documentation | Documentation | Produce Sprint 1-2 Design Documentation | As a Solution Architect, I want the Sprint 1-2 design documentation produced (workbooks updated with decisions), so that Month 1 decisions are captured and traceable. | AC1: Given the Stage 1 workshops, When documented, Then the design workbooks reflect the agreed decisions. AC2: Given the docs, When reviewed, Then they are accepted by the Product Owner. AC3: Given the Triage Log, When current, Then deviations are reflected. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 2 | Solution Architect | 03_Shared/04_Sprint_Workbooks (Connection copies) | Draft
CONN-DOC-003 | Documentation | Documentation | Produce Sprint 3-4 Design Documentation | As a Process Consultant, I want the Sprint 3-4 design documentation produced, so that Month 2 decisions are captured and traceable. | AC1: Given the Stage 2 workshops, When documented, Then the design workbooks reflect the agreed decisions. AC2: Given the docs, When reviewed, Then they are accepted by the Product Owner. AC3: Given the Triage Log, When current, Then deviations are reflected. | See 'Definition of Done' tab | 3 | 3 - Moderate | Sprint 4 | Process Consultant | Sprint Workbooks | Draft
CONN-DOC-004 | Documentation | Documentation | Produce Month 3 Design Documentation | As a Process Consultant, I want the Month 3 design documentation produced, so that late-build decisions (EX, HAM, PA) are captured. | AC1: Given the Stage 2-3 workshops, When documented, Then EX/HAM/PA decisions are recorded. AC2: Given the docs, When reviewed, Then they are accepted. AC3: Given the set, When complete, Then it joins the KT Package. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Process Consultant | Sprint Workbooks | Draft
CONN-DOC-005 | Documentation | Documentation | Produce the Governance Charter Package | As a Engagement Manager, I want the governance charter package produced (decision rights, council charter, RACI), so that the operating model is documented and agreed. | AC1: Given Sprint 0, When produced, Then the charter, decision-rights, and RACI are delivered. AC2: Given the package, When reviewed, Then ECS and the Sponsor agree it. AC3: Given the docs, When complete, Then they are stored and referenced. | See 'Definition of Done' tab | 2 | 2 - High | Sprint 0 | Engagement Manager | Customer_Governance_Charter.docx + Role Quick-Ref | Draft
CONN-DOC-006 | Documentation | Documentation | Maintain the SOW Deliverables Matrix | As a Engagement Manager, I want the SOW deliverables matrix kept current, so that leadership tracks every committed deliverable and its status. | AC1: Given the 27 SOW deliverables, When tracked, Then each shows status (Ready/Adapt/Gap/Complete), owner, and sprint. AC2: Given a deliverable completion, When recorded, Then its status updates. AC3: Given the matrix, When reviewed, Then it reconciles to the project plan. | See 'Definition of Done' tab | 2 | 3 - Moderate | All sprints | Engagement Manager | Connection_SOW_Deliverables_Matrix.xlsx | Draft
CONN-DOC-007 | Documentation | Documentation | Produce and maintain the configuration story backlog | As a Solution Architect, I want the configuration user-story backlog maintained in SN Agile, so that development is tracked story-by-story with traceability. | AC1: Given the 141 stories, When imported, Then epics and stories exist in SN Agile with acceptance criteria and DoD. AC2: Given a sprint, When planned, Then stories are estimated and assigned. AC3: Given progress, When tracked, Then the backlog reflects state. | See 'Definition of Done' tab | 3 | 2 - High | All sprints | Solution Architect | Connection_User_Stories_SN_Agile.xlsx | Draft
CONN-QA-001 | Testing & Quality | Testing | Produce the UAT end-to-end test scripts | As a QA / UAT Lead, I want the end-to-end UAT scripts produced with story traceability, so that UAT is contained, managed, and tied back to the stories. | AC1: Given the stories, When authored, Then scripts are grouped into end-to-end suites with story-ID traceability. AC2: Given coverage, When checked, Then every story is covered E2E or flagged sprint-test-only. AC3: Given the scripts, When complete, Then they are ready for tester assignment. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 6 | QA / UAT Lead | Connection_UAT_End_to_End_Test_Scripts.xlsx | Draft
CONN-QA-002 | Testing & Quality | Testing | Produce the UAT Guidebook for end users | As a Process Consultant, I want the UAT guidebook produced for first-time testers, so that end users know how to test, log defects, and what good looks like. | AC1: Given the suites, When documented, Then the guidebook explains UAT, roles, how to run a script, and how to log a defect. AC2: Given a tester, When prepared, Then they can execute without prior experience. AC3: Given the guidebook, When delivered, Then it accompanies tester onboarding. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 6 | Process Consultant | Connection_UAT_Guidebook_for_End_Users.docx | Draft
CONN-QA-003 | Testing & Quality | Testing | Coordinate UAT execution | As a QA / UAT Lead, I want UAT execution coordinated across testers and suites, so that UAT completes with results recorded and defects logged. | AC1: Given assigned scripts, When UAT runs, Then testers record PASS/FAIL/BLOCKED/SKIP per script. AC2: Given a daily standup, When held, Then progress and blockers are tracked. AC3: Given completion, When reached, Then results roll up for go/no-go. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 7 | QA / UAT Lead | UAT Test Scripts | Draft
CONN-QA-004 | Testing & Quality | Testing | Triage and resolve UAT defects | As a Solution Architect, I want UAT defects triaged and resolved, so that P1/P2 defects are cleared (or planned) before go-live. | AC1: Given a logged defect, When triaged, Then severity and owner are set. AC2: Given a fix, When deployed, Then the tester re-tests and confirms. AC3: Given go-live, When approaching, Then no open P1/P2 defects remain without a plan. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 7 | Solution Architect | Connection_UAT_End_to_End_Test_Scripts.xlsx (Defect Log) | Draft
CONN-QA-005 | Testing & Quality | Testing | Execute System Integration Testing (SIT) | As a Technical Consultant, I want SIT executed across integrations end-to-end, so that integration touchpoints work before UAT/go-live. | AC1: Given the integrations, When SIT runs, Then AD/SSO, SCCM, Intune, email, and CTI are validated in sub-prod. AC2: Given a failure, When found, Then it is logged and fixed. AC3: Given SIT, When complete, Then results inform UAT readiness. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 6 | Technical Consultant | Integration packs | Draft
CONN-KT-001 | Training & Knowledge Transfer | Training | Deliver Admin Knowledge Transfer (4 sessions) | As a Solution Architect, I want the 4 admin KT sessions delivered, so that Connection's platform team can administer OOTB and stay upgrade-safe. | AC1: Given the KT plan, When delivered, Then 4 sessions cover admin, update sets, and OOTB governance. AC2: Given attendees, When trained, Then they can perform core admin tasks. AC3: Given the sessions, When complete, Then the Admin Guide is handed over. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 7 | Solution Architect | Connection_Administrator_Guide_and_KT.docx | Draft
CONN-KT-002 | Training & Knowledge Transfer | Training | Deliver Train-the-Trainer (2 per process area) | As a Process Consultant, I want two train-the-trainer sessions per in-scope process area delivered, so that Connection trainers can deliver end-user training. | AC1: Given the toolkit, When delivered, Then each area gets 2 sessions (demo + teach-back). AC2: Given trainers, When enabled, Then they can run end-user training. AC3: Given the sessions, When complete, Then the quick-reference outline is handed over. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 7 | Process Consultant | Connection_Train_the_Trainer_Toolkit.docx | Draft
CONN-KT-003 | Training & Knowledge Transfer | Training | Assemble the Knowledge Transfer Package | As a Solution Architect, I want the KT Package assembled for handover, so that Connection receives a complete administration/enablement set at go-live. | AC1: Given the components, When assembled, Then the Admin Guide, train-the-trainer materials, and sprint workbook set are bundled. AC2: Given the package, When reviewed, Then it is complete per the SOW. AC3: Given handover, When done, Then KT Certification is issued. | See 'Definition of Done' tab | 2 | 2 - High | Sprint 7 | Solution Architect | KT Package (SOW Sec 11) | Draft
CONN-GL-001 | Go-Live & Cutover | Go-Live | Produce the Go-Live Checklist | As a Engagement Manager, I want the Connection go-live checklist produced, so that go-live readiness is verifiable and signed off. | AC1: Given the library checklist, When tailored, Then it reflects Connection's cutover scope. AC2: Given readiness, When assessed, Then each item is confirmed. AC3: Given the checklist, When complete, Then it supports the go/no-go. | See 'Definition of Done' tab | 2 | 2 - High | Sprint 7 | Engagement Manager | lib CLT-CO-02_Go_Live_Checklist.docx | Draft
CONN-GL-002 | Go-Live & Cutover | Go-Live | Produce the Cutover Runbook | As a Solution Architect, I want the cutover runbook produced, so that the production cutover is sequenced and low-risk. | AC1: Given the cutover plan, When documented, Then steps, owners, timings, and rollback are defined. AC2: Given the runbook, When reviewed, Then it is accepted by the Technical Lead. AC3: Given cutover, When executed, Then the runbook is followed. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 7 | Solution Architect | Cutover Runbook (new) | Draft
CONN-GL-003 | Go-Live & Cutover | Go-Live | Obtain Go-Live Readiness Sign-Off | As a Engagement Manager, I want go-live readiness signed off by Sponsor and Product Owner, so that go-live proceeds only with explicit authorization. | AC1: Given UAT results and open defects, When reviewed, Then a go/no-go recommendation is made. AC2: Given the review, When held, Then the Sponsor and Product Owner sign off. AC3: Given sign-off, When obtained, Then it is recorded. | See 'Definition of Done' tab | 2 | 1 - Critical | Sprint 7 | Engagement Manager | Go-Live Readiness Sign-Off | Draft
CONN-GL-004 | Go-Live & Cutover | Go-Live | Execute the governed production cutover | As a Solution Architect, I want the governed cutover to production executed, so that Connection goes live on the new instance (Week 16). | AC1: Given the runbook, When executed, Then in-scope capabilities are live and verified in production. AC2: Given verification, When complete, Then a clean exit from the legacy environment is confirmed. AC3: Given go-live, When done, Then Hypercare begins. | See 'Definition of Done' tab | 5 | 1 - Critical | Sprint 7 | Solution Architect | Project Plan (Stage 3) | Draft
CONN-CO-001 | Hypercare & Closeout | Hypercare | Provide 2-week Hypercare support | As a Engagement Manager, I want 2 weeks of post-go-live Hypercare provided, so that production stabilizes with ECS L2+ escalation support. | AC1: Given go-live, When Hypercare runs, Then daily standups (Week 1) step down to twice-weekly (Week 2). AC2: Given a P1/P2 production issue, When raised, Then ECS provides L2+ support in business hours. AC3: Given Hypercare, When closing, Then an exit-criteria review is held. | See 'Definition of Done' tab | 3 | 2 - High | Sprint 8 | Engagement Manager | lib CLT-CO-03 Hypercare Support Model | Draft
CONN-CO-002 | Hypercare & Closeout | Hypercare | Produce the Hypercare Exit Report | As a Engagement Manager, I want the Hypercare exit report produced, so that handover to steady-state operations is formal and clean. | AC1: Given the Hypercare window, When closing, Then the exit report summarizes incidents, fixes, and stability. AC2: Given exit criteria, When met, Then handover to operations is approved. AC3: Given the report, When complete, Then it is delivered to Connection. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 8 | Engagement Manager | lib CLT-CO-06 Hypercare Exit Report | Draft
CONN-CO-003 | Hypercare & Closeout | Closeout | Produce the Operational Handoff Pack | As a Engagement Manager, I want the operational handoff pack produced, so that Connection owns ongoing operations with a clear support model. | AC1: Given the operating model, When documented, Then the ownership matrix, support model, and escalation contacts are defined. AC2: Given the pack, When reviewed, Then Connection's team accepts ownership. AC3: Given handover, When done, Then the pack is delivered. | See 'Definition of Done' tab | 2 | 2 - High | Sprint 8 | Engagement Manager | Operational Handoff Pack | Draft
CONN-CO-004 | Hypercare & Closeout | Closeout | Produce Lessons Learned & Project Closeout | As a Engagement Manager, I want the lessons learned and closeout report produced, so that the engagement closes with documented outcomes and learning. | AC1: Given the engagement, When closing, Then final KPIs, OOTB wins, and lessons learned are captured. AC2: Given the report, When reviewed, Then it is accepted by the Sponsor. AC3: Given closeout, When done, Then artifacts are archived. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 8 | Engagement Manager | lib CLT-CO-01 Closeout Summary + Lessons Learned | Draft
CONN-CO-005 | Hypercare & Closeout | Closeout | Produce the 12-month strategic roadmap | As a Solution Architect, I want a 12-month roadmap produced beyond Phase 1, so that Connection has a clear path to Phases 2-4 (UX, ITOM, AI). | AC1: Given Phase 1 outcomes, When planned, Then the roadmap outlines Phase 2-4 priorities. AC2: Given the roadmap, When reviewed, Then leadership aligns on the vision. AC3: Given closeout, When done, Then the roadmap is delivered. | See 'Definition of Done' tab | 2 | 3 - Moderate | Sprint 8 | Solution Architect | 12-month roadmap | Draft

## Definition of Done
DEFINITION OF DONE - delivery work
A delivery story is Done only when all gates pass.
DoD | Produced using the approved ECS brand template/standard (EcsDocument / pptx_brand / pack builder).
DoD | Content complete and accurate to the SOW and the agreed decisions.
DoD | Peer or lead reviewed (Practice Lead for high-stakes items).
DoD | Reviewed and accepted/signed off by the named party (Sponsor / Product Owner / Technical Lead as applicable).
DoD | Stored in the engagement folder (05_Clients/Connection) and referenced in the SOW Deliverables Matrix.
DoD | Reflected in the weekly status report and the Executive Health Dashboard.
DoD | For client-facing items: correct footer (Confidential) and no internal-only content leaked.
DoD | For workshops/sessions: signed-off output captured; deviations logged in the Triage Log.

## Workstream Summary
WORK-STREAM SUMMARY
Story counts and points per work-stream (live COUNTIF/SUMIF over the Delivery Stories tab).
Work-stream | Stories | Story Points
PMO & Governance
Engagement Setup
Onboarding & Enablement
Workshops
Documentation
Training & Knowledge Transfer
Testing & Quality
Go-Live & Cutover
Hypercare & Closeout
TOTAL