CONNECTION EXECUTION LIBRARY - START HERE

Connection Engagement

Execution Guide (Start Here)

What to use, by role and by phase - the navigator for this library

ECS Federal - ServiceNow Practice

Audience: ECS delivery team and Connection - all roles

Companion to: Library Index - every artifact in this package

Document ID: LIB-CONN-GUIDE-01     ·     Version: 1.0     ·     Status: Released

ECS Federal - ServiceNow Practice - Confidential

# How to Use This Library

This is the static, execution-ready library for the Connection engagement. It contains the finished deliverables only - no build files. Find your role or your phase below and it points you to exactly what to use. The full catalog is in the Library Index. Folders: 01_Onboarding, 02_Delivery (with Workshops, Accelerator_Packs, Knowledge_Transfer).

Don't read the whole library. Read your row. Each role and each phase below lists only what you need.

# 1.  By Role

## ECS team

| Role | Start with | Use throughout |
| --- | --- | --- |
| Engagement Manager | Team Onboarding & Vision; Engagement Delivery Guidelines; Project Plan | Status Report; Exec Dashboard; Dependency Tracker; RAID; Deliverables Matrix; Project Controls; Sprint Operating Kit; RACI |
| Solution Architect | Delivery Guidelines; Architecture & CSDM Alignment; Accelerator Packs | Config User Stories; Workshop decks; SIT Scripts; Cutover Runbook |
| Process Consultant / BA (Scrum Master) | Workshop Facilitation Guide; Workshop decks + Pre-Reads; Demo Scripts; Sprint Operating Kit | Config User Stories; Sprint Demo template; Scope Notes; UAT scripts; runs ceremonies + owns velocity/burndown (SM hat) |
| Technical Consultant | Accelerator Packs; Integration & Vonage packs | Config User Stories; SIT Scripts; Demo Scripts |
| Practice Lead | Engagement Delivery Guidelines (trust-but-verify); RACI | Exec Dashboard; Delivery Readiness Audit; Project Controls |

## Connection (client)

| Role | Start with | Use throughout |
| --- | --- | --- |
| Executive Sponsor | Client Onboarding Guide; Kickoff Deck; Governance Charter | Exec Dashboard; Dependency Tracker; Go-Live Readiness; sign-offs |
| Product Owner | Client Onboarding Guide; Governance Charter | Workshop Pre-Reads; Acceptance & Sign-off Log; UAT results |
| Project Manager | Client Onboarding Guide; Dependency Tracker | Status Report; Onboarding Checklist; Workshop schedule |
| Technical Lead | Architecture & CSDM Alignment; Integration packs | Dependency Tracker (env/access/MID/Vonage); Cutover Runbook |
| SMEs / Process Owners | Workshop Pre-Reads for their area; Accelerator Packs | Workshop decks; UAT scripts |
| UAT Testers | UAT Guidebook for End Users | UAT End-to-End Test Scripts |
| Platform Admins | Administrator Guide & KT | Operational Handoff Pack |

# 2.  By Phase

| Phase (Sprint / Weeks) | What's in play | Key artifacts |
| --- | --- | --- |
| Sprint 0 - Setup (Wks 1-2) | Onboard, govern, set dependencies, collect data | Onboarding (client + internal); Governance Charter; Project Plan; Onboarding Checklist; Dependency Tracker; Accelerator Packs (distribute); RACI |
| Stage 1 Build (Sprints 1-2) | Foundation, CSDM, CMDB, Discovery | Workshop decks + Pre-Reads (PF/CSDM/CMDB/Discovery/SGC); Architecture & CSDM Alignment; Config User Stories; Sprint Operating Kit; Demo Scripts |
| Stage 2 Build (Sprints 3-5) | ITSM Core, Change/CAB, Catalog, EX, Integrations | Workshop decks + Pre-Reads; Config User Stories; Accelerator Packs; Vonage CTI pack + workshop; Sprint Demo template |
| Stage 3 Deliver (Sprints 6-7) | HAM, analytics, SIT, UAT, cutover prep | SIT Scripts + Test Data Plan; UAT Test Scripts; UAT Guidebook; Go-Live Readiness Checklist; Cutover Runbook |
| Go-Live (Wk 16) | Governed cutover to production | Cutover Runbook; Go-Live Readiness Checklist; sign-offs |
| Stage 4 Close (Sprints 8) | Hypercare, KT, handover, close | Admin Guide & KT; Train-the-Trainer; Operational Handoff Pack; Lessons Learned (produced at close) |
| Ongoing / Governance | Run the engagement transparently | Status Report; Exec Dashboard; RAID; Project Controls (PCR/acceptance/decisions/assumptions); Deliverables Matrix; Delivery Readiness Audit |

# 3.  The Backlog (everything is a story)

Two workbooks form the complete project backlog - import both to ServiceNow Agile:

Configuration User Stories (141) - the buildable decisions, with Given/When/Then acceptance criteria.

Project Delivery Stories (55) - documentation, training, governance, testing, go-live, hypercare - so the whole project is visible, not just the build.

This library is a snapshot. The live, reproducible baseline lives in the ECS working framework; updates are made there and re-exported - do not edit these files directly.