## Onboarding Tracker
CONNECTION ENGAGEMENT - ONBOARDING & SPRINT 0 READINESS TRACKER
Shared - ECS Team + Connection ¦ Update Status as items complete; any open item at end of Sprint 0 triggers a dependency-slip conversation with the Sponsor.
ID | Task | Side | Owner (role) | Stage / Sprint | Status | Due | Notes
OB-01 | Internal ECS kickoff - SOW review & consultant assignment | ECS | EM | Sprint 0 | Not Started
OB-02 | Team reads onboarding package (Vision, Guidelines, Role Quick-Ref) | ECS | All ECS | Sprint 0 | Not Started
OB-03 | Confirm role assignments & decision rights | ECS | EM | Sprint 0 | Not Started
OB-04 | Stand up backlog tooling + story template | ECS | PC | Sprint 0 | Not Started
OB-05 | Prepare Accelerator Pack workbooks for distribution | ECS | SA / PC | Sprint 0 | Not Started
OB-06 | Establish weekly health reporting to practice management | ECS | EM -> Practice Lead | Sprint 0 | Not Started
OB-07 | Project Sponsor identified (avail. for Council + bi-weekly sync) | Connection | Connection | Sprint 0 | Not Started
OB-08 | ServiceNow instances provisioned (sub-prod + prod) w/ admin access | Connection | Tech Lead | Sprint 0 | Not Started
OB-09 | Access & credentials for ECS team | Connection | Tech Lead | Sprint 0 | Not Started
OB-10 | Foundation Data Pack completed (users, locations, groups, SLAs) | Connection | Connection SMEs | Sprint 0-1 | Not Started
OB-11 | Stakeholder & SME mapping completed | Connection | Connection PM | Sprint 0 | Not Started
OB-12 | Customer kickoff meeting | Joint | EM + Sponsor | Sprint 0 | Not Started
OB-13 | CSDM reference model selected & pre-loaded for Sprint 1 | Joint | SA + Connection | Sprint 0 | Not Started
OB-14 | Definition of Done published & acknowledged by Product Owner | Joint | EM + Product Owner | Sprint 0 | Not Started
OB-15 | Governance & decision-rights workshop | Joint | EM + Sponsor | Sprint 0 | Not Started
OB-16 | Customization Council charter signed | Joint | Sponsor + EM | Sprint 0 | Not Started
OB-17 | Communication plan & cadence established | Joint | EM + Connection PM | Sprint 0 | Not Started
OB-18 | Risk register initialized | Joint | EM + Connection PM | Sprint 0 | Not Started
OB-19 | Sprint 0 readiness validation (ECS checklist) | Joint | EM | Sprint 0 | Not Started
SUMMARY
Total tasks | 19
Complete | 0
In Progress | 0
Blocked | 0
Not Started | 19