## SOW Deliverables Matrix
CONNECTION - SOW DELIVERABLES MATRIX (EM Day-1 Reference)
Every deliverable committed in SOW v2.0 Sections 5, 10-11, mapped to its supporting baseline. Status: Ready (built for Connection) ¦ Adapt from library (pull + tailor when the sprint arrives) ¦ GAP - build.
# | Deliverable | Period | Type | Audience | ECS Owner | Supporting Baseline (path / file) | Status | Notes
1 | Governance Charter Package - Decision Rights + Customization Council Charter | Sprint 0 | Doc | Client | EM/SA | 01_Onboarding/Client_Facing/Customer_Governance_Charter.docx (+ lib INT-S0-04/05) | Ready | Charter built; lib decision-rights/council templates back it
2 | RACI Matrix (part of Governance Package) | Sprint 0 | Doc | Joint | EM | 01_Onboarding/Internal_Team/Connection_Role_and_Accountability_QuickRef.docx | Adapt from library | Quick-ref is RACI-style; produce a client-facing RACI cut
3 | Baseline 18-Week Project Plan | Sprint 0 | Doc | Joint | EM | 02_Delivery/Connection_18Week_Project_Plan.xlsx | Ready | Set start date (B3)
4 | Foundation Data Workbooks (users, locations, groups, SLAs, taxonomy) | Sprint 0 | Doc | Client (fill) | PC | 02_Delivery/Accelerator_Packs/Foundation_Accelerator_Pack/ | Ready | Distribute Sprint 0
5 | Baseline Risk Register | Sprint 0 | Doc | Joint | EM | 02_Delivery/Connection_Governance_Triage_and_RAID.xlsx (RAID tab) / lib INT-S0-06 | Ready | RAID covers it; or use lib risk register template
6 | Plug-ins installed + core configuration | Sprint 0 | Platform Config | - | SA/TC | Workshops/Connection_Platform_Foundation_Workshop.pptx + Foundation pack | Ready | Collateral in place
7 | Platform Architecture & CSDM Alignment Document | Month 1 | Doc | Client | SA | 02_Delivery/Connection_Platform_Architecture_and_CSDM_Alignment.docx | Ready | Template built; SA completes from CSDM/CMDB workshop
8 | Sprint 1-2 Design Documentation (workbooks updated w/ decisions) | Month 1 | Doc | Joint | PC/SA | 03_Shared/04_Sprint_Workbooks (Platform, CSDM, CMDB, Discovery, Incident) | Adapt from library | Copy sprint workbooks into Connection; update with decisions
9 | Active Governance Triage Log | Month 1+ | Doc | Joint | EM | 02_Delivery/Connection_Governance_Triage_and_RAID.xlsx | Ready | Living through Go-Live
10 | ITSM Core v1 - Incident + Problem configured | Month 1 | Platform Config | - | SA/TC | Workshops: Incident, Problem + ITSM pack | Ready | Collateral in place
11 | Sprint 3-4 Design Documentation | Month 2 | Doc | Joint | PC/SA | 03_Shared/04_Sprint_Workbooks (Change, Catalog) | Adapt from library | Copy + update with decisions
12 | ITSM Core v2 - Request, Change, CAB, SLA, assignment rules | Month 2 | Platform Config | - | SA/TC | Workshops: Change + ITSM pack | Ready | Collateral in place
13 | Service Catalog Phase 1 - 5 items | Month 2 | Platform Config | - | PC/TC | Workshops: Service Catalog + Service_Catalog pack | Ready | Collateral in place
14 | Integration Baseline - AD/SSO + SCCM + Intune validated | Month 2 | Platform Config | - | SA/TC | Workshops: Integrations, SGC + Integration pack (AD/SSO/SCCM/Intune) | Ready | Vonage CTI pack also built
15 | Employee Experience - EC, VA, AI Search, KM | Month 3 | Platform Config | - | PC/TC | Workshops: Employee Center, Virtual Agent, Knowledge + packs | Ready | Collateral in place
16 | HAM Foundations - stockrooms, asset classes, CSDM data model | Month 3 | Platform Config | - | SA/TC | Workshops: HAM + ITAM_HAM_Foundations pack | Ready | Collateral in place
17 | Remaining Catalog Items (13-15 total) | Month 3 | Platform Config | - | PC/TC | Workshops: Service Catalog + pack | Ready | Collateral in place
18 | Performance Analytics - baseline dashboard set | Month 3 | Platform Config | - | SA | Workshops: Performance Analytics + PA pack | Ready | Collateral in place
19 | UAT Execution Report (results + P1/P2 defect log) | Go-Live | Doc | Joint | QA/PC | lib 02_Client/06_UAT_Execution (CLT-UAT-02/03) + 01_Internal/08_UAT_Test_Packs | Adapt from library | Strong library coverage; copy into Connection at UAT
20 | Go-Live Readiness Sign-Off | Go-Live | Doc | Client | EM | lib 02_Client/07_Closeout_and_Hypercare/CLT-CO-02_Go_Live_Checklist.docx | Adapt from library | Tailor checklist to Connection
21 | KT Package - Administrator Guide / Admin KT (4 sessions) | Go-Live | Doc | Client | SA | 02_Delivery/Knowledge_Transfer/Connection_Administrator_Guide_and_KT.docx | Ready | Template built - 4-session Admin KT plan + admin reference
22 | KT Package - Train-the-Trainer materials (2 per process area) | Go-Live | Doc | Client | PC | 02_Delivery/Knowledge_Transfer/Connection_Train_the_Trainer_Toolkit.docx | Ready | Template built - 2 sessions/area; demo-script refs
23 | KT Package - Sprint workbook set | Go-Live | Doc | Joint | PC | 03_Shared/04_Sprint_Workbooks (Connection copies) | Adapt from library | Bundle the populated Connection workbooks
24 | Operational Handoff Pack (ownership matrix, support model, escalation) | Go-Live | Doc | Joint | EM | lib CLT-CO-03_Hypercare_Support_Model.docx + RACI | Adapt from library | Add an ownership matrix cut from RACI
25 | Lessons Learned & Project Closeout | Close | Doc | Joint | EM | lib CLT-CO-01_Engagement_Closeout_Summary.docx + 01_Internal/10_Lessons_Learned | Adapt from library | Copy + complete at close
26 | Hypercare (support model + exit report) | Close | Doc | Joint | EM | lib CLT-CO-03 + CLT-CO-06_Hypercare_Exit_Report.docx | Adapt from library | 2-week Hypercare per SOW Sec 11
27 | Production environment live + verified | Go-Live | Platform Config | - | SA/EM | Cutover via project plan Stage 3 | Ready | Governed cutover Wk 16
SUMMARY
Total deliverables | 27
Ready | 18
Adapt from library | 9
GAP - build | 0