## Instructions
01 — CSDM Service Taxonomy
CMDB-CSDM Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the four-layer CSDM service taxonomy the customer will implement in ServiceNow: Foundational Data, Managed Objects, Business Applications, and Business Services. This workbook establishes the vocabulary and hierarchy that underpins every downstream CMDB, Catalog, and AI feature in the engagement.
Who fills this out | Customer-side: Enterprise Architect or IT Service Management Owner, working with the CIO/IT Director to confirm Business Service naming. ECS SA facilitates the first workshop; customer confirms the taxonomy in Weeks 1-2 of Sprint 1.
Sprint window | Sprint 1, Weeks 1–2
Estimated effort | 4–6 hours across two workshops for a typical mid-market customer
Related workbooks | 02 CI Class Selection · 03 Business Service Definitions · 04 Technical Services & Apps · Foundation Data Pack
Success criteria
• | All four CSDM layers are named and the customer team understands how they relate.
• | A complete list of Business Services is agreed, signed off by the IT Director or CIO.
• | The service owner for each Business Service is identified by name and role.
• | The mapping from Business Services down to Technical Services is drafted (can be refined in Sprint 2).
• | OOTB CSDM domain is chosen (IT, HR, Facilities, or scoped subset) and agreed.

## Process Decisions
01 — CSDM Service Taxonomy — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which CSDM domains are in scope for this engagement? | IT domain only. Scope CSDM to the IT service portfolio. HR, Facilities, and Legal domains can be added in a future phase without restructuring what is built here. |  | Including multiple domains in Sprint 1 adds 3–5 weeks of taxonomy work and delays every downstream build. The OOTB CSDM model is designed to layer on new domains incrementally.
2 | Should we use ServiceNow's OOTB CSDM service classifications or define custom ones? | Use OOTB CSDM classifications: Business Service, Technical Service, Application Service, and the standard supporting objects. Do not create custom CI classes to represent service layers. |  | Custom service classification tables require upgrade maintenance and block PI and Virtual Agent from recognising service context. The OOTB model is the AI-readable contract.
3 | How many levels of Business Service hierarchy are appropriate? | Two levels maximum: primary Business Services (e.g., Email, ERP, HR Systems) and sub-services where operationally meaningful. Do not model every application as a top-level Business Service. |  | Customers who model 80+ Business Services cannot maintain ownership, SLA assignment, or service health dashboards. A well-scoped OOTB CSDM has 10–25 Business Services for a mid-market IT portfolio.
4 | Who owns a Business Service record in ServiceNow? | A single named IT manager is the service owner. The IT Director or CIO approves the full list. Service ownership is a governance decision, not a technical one — resolve it before configuration. |  | Shared ownership or committee ownership means nobody responds when the service health degrades. ServiceNow requires a single owner field on the Business Service record for assignment and escalation.
5 | How should legacy application names map to the CSDM service model? | Map legacy applications to Application Services under the appropriate Technical Service. Keep the legacy name in the 'alias' or 'short description' field rather than as the primary CI name. |  | Legacy names are tribal knowledge. OOTB CSDM names services by what they deliver to the business, not by the product that happens to deliver it. The alias field preserves findability.
6 | Should we model services we don't fully manage (e.g., SaaS vendors)? | Yes, but as External Service records with the vendor as service owner. Do not skip SaaS services — they appear in incidents, requests, and outage communications regardless of who manages them. |  | Omitting vendor-managed services creates orphaned incidents and breaks the service map. The External Service classification in OOTB CSDM handles this without requiring CI-level discovery of the vendor environment.

## Dependencies
01 — CSDM Service Taxonomy — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Foundation Data Pack — Departments and Business Units completed | Required | Customer IT Director | End of Sprint 0 | Business Service ownership maps to Departments. Incomplete department data means service owners cannot be named.
2 | ITSM Design Workshop outputs — service categories agreed | Required | ECS SA + Customer ITSM Owner | Sprint 1 Wk 1 | Incident and Request categories must align with the Business Service taxonomy. Misalignment here causes rework in Sprints 3–4.
3 | CIO/IT Director available for Business Service approval session | Required | Customer Project Sponsor | Sprint 1 Wk 2 | Business Service names and owners must be approved by a business stakeholder, not just IT ops.
4 | Existing CMDB or asset register for application inventory | Recommended | Customer IT Ops | Sprint 1 Wk 1 | Even a partial existing list of applications shortens the taxonomy workshop by 2–3 hours.
5 | Vendor list for SaaS/external services | Recommended | Customer Procurement | Sprint 1 Wk 2 | Needed to populate External Service records and identify which services have no discovery data.

## Configuration Data
01 — CSDM Service Taxonomy — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. CSDM Domain Scope
In-scope domain(s) | IT | Start with IT only. Expand to HR/Facilities in a future phase.
CSDM version targeting | CSDM 4.0 (Vancouver+) | Align to the ServiceNow version in use. CSDM 4.0 is the default from Vancouver onward.
Service classification model | OOTB: Business Service > Technical Service > Application Service | Do not create custom tables.
2. Business Service Naming Standards
Naming convention | [Service Verb] + [Business Object] e.g., 'Deliver Email', 'Support ERP' | Keep names outcome-oriented, not technology-oriented.
Maximum number of top-level Business Services (target) | 10–25 | More than 25 requires a service portfolio manager to maintain.
Sub-service levels allowed | 2 maximum | Three or more levels become unmaintainable.
Service owner field | Single named individual (not a group) | Use the 'service owner' field on Business Service CI.
3. External / Vendor Services
Model vendor-managed SaaS? | Yes — as External Service CI type | Examples: Microsoft 365, Salesforce, Workday.
Discovery required for External Services? | No — manually maintained records acceptable at MVP | External Services are excluded from Discovery reconciliation rules.

## R&R
01 — CSDM Service Taxonomy — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Facilitate CSDM taxonomy workshop | R/A | C | ECS SA runs the workshops; customer provides the business knowledge.
Define and name Business Services | C | R/A | Customer IT Director owns the service list; ECS advises on OOTB best practice.
Assign service owners to each Business Service | I | R/A | Pure customer governance decision.
Map legacy applications to CSDM Application Services | R | C | ECS SA leads mapping; customer confirms names and technology ownership.
Identify External / Vendor services | C | R | Customer procurement leads; ECS advises on CI classification.
Load Business Service CIs into ServiceNow | R/A | I | ECS SA performs the configuration.
Validate service hierarchy in ServiceNow Service Map | R | A | ECS validates technically; customer approves visually.
Approve final CSDM taxonomy | I | R/A | Customer IT Director or CIO formally approves.

## Consultant Guide
01 — CSDM Service Taxonomy — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Workshop approach
Run two 90-minute workshops in Sprint 1 Week 1. Workshop 1 is top-down: start with the CSDM model diagram, then ask the customer to list everything IT delivers to the business (not the tools — the outcomes). Workshop 2 maps those outcomes to OOTB CSDM classifications and identifies the service owner for each. A miro/whiteboard is more effective than spreadsheet-first for workshop 1.
Common drift patterns to watch for
Customers frequently try to model every application as a Business Service (too granular) or define Business Services so broadly they have no operational meaning ('All of IT'). Push for the middle ground: a Business Service should map to a distinct SLA, a distinct service owner, and at least one identifiable user population. If you can't name those three things, the service definition isn't ready.
CSDM readiness check before Sprint 2
By end of Sprint 1, the following must be locked: (1) Business Service list approved by IT Director, (2) service owner for each, (3) top-level Technical Service groupings (e.g., Infrastructure, End User Computing, Applications), (4) the Application Service list derived from the existing application inventory. If any of these are missing, Sprint 2 CMDB normalization will lack an anchor and the Discovery team will load CIs with no service relationship.
Handling resistance to OOTB naming
Customers often want to preserve legacy tool names as Business Service names. The counter-argument: 'The CSDM model names services by what the business receives, not the product that delivers it. When we move platforms in the future, the service name stays stable even when the underlying technology changes. Your users search for email, not Exchange.' This usually resolves the objection.

## Adoption vs Re-engineering
01 — CSDM Service Taxonomy — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We have a different service model from our legacy ITSM tool — can we mirror it? | Implement OOTB CSDM service classifications. Migrate the legacy hierarchy into the new taxonomy during Sprint 1 workshops. | OOTB CSDM is the data contract for PI, Virtual Agent, Service Health, and CMDB health. A custom taxonomy breaks all of these and requires upgrade maintenance. | 'Your legacy model was designed for your previous tool, not for AI-powered service management. CSDM lets Virtual Agent understand which service is affected when a user reports a problem — that only works with the standard model. Let's map your existing services into CSDM; the names can stay the same even when the structure is standardized.' | Only if the customer has a mature service portfolio management practice and an enterprise architect who will own the taxonomy for 3+ years. Extremely rare at mid-market.
We want every application to be a separate Business Service for reporting | Application-level reporting belongs on Application Service CIs, not Business Services. Business Services roll up to executive dashboards; application detail stays at the Technical/Application tier. | Forty Business Services means forty SLA definitions, forty service owners, and forty health dashboards. No customer team can maintain that. OOTB reporting surfaces application data from the lower CSDM tiers without elevating everything to Business Service. | 'Business Services are the C-suite view — what IT delivers to the business. Applications are the operational view — what IT teams manage. We can report on both independently without mixing the layers. Let me show you how the OOTB service health dashboard rolls application health up to business service health.' | If the customer has a formal service catalogue managed at application level with SLAs per application, a hybrid model can be considered — but discuss with Practice Lead first.
We don't want to define service owners — IT is collectively responsible | Assign a single named owner to each Business Service. This is a ServiceNow platform requirement for SLA escalation, Major Incident routing, and service health alerting. | Collective ownership means nobody responds. The OOTB Service Health and Major Incident Management modules both require a single accountable owner for escalation. Without it, P1 alerts go unanswered. | 'Service ownership doesn't mean one person does all the work — it means one person is accountable for the service being healthy. We're not changing how your team is organized; we're giving the platform a single escalation point so that when a major incident hits, there's no confusion about who to call.' | Never. This is a ServiceNow platform requirement, not an ECS preference.

## ServiceNow Mapping
01 — CSDM Service Taxonomy — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Primary CMDB Tables
Business Service | cmdb_ci_service | The top-level service classification in CSDM. Represents what IT delivers to the business.
Technical Service | cmdb_ci_service_technical | Mid-tier service — groups the technical components that support a Business Service.
Application Service | cmdb_ci_appl | Represents a deployable application or software service, mapped to Technical Service.
External Service | cmdb_ci_service_auto | Vendor-managed / SaaS services. Not populated by Discovery.
2. Key Fields to Configure
service_classification | Business Service / Technical Service / Application Service / External Service | Set on every Service CI to enable CSDM layer filtering.
owned_by | Named individual (sys_user) | Single service owner. Required for health dashboard and escalation.
support_group | Assignment group | Operational support group, distinct from the business owner.
operational_status | 1 = Operational (default for MVP) | Set all live services to Operational before Sprint 2 discovery begins.
3. OOTB Features Leveraged
Service Map | Now Platform > CMDB > Service Mapping | Visualises service-to-CI relationships. Requires Service Mapping licence or Discovery.
CMDB Health Dashboard | CMDB > CMDB Health | Monitors completeness and staleness. Configure after CI classes are selected (Workbook 02).
Dependency Views | CMDB > CI Relationships | OOTB graph view of service dependencies. No customisation needed.