## Instructions
05 — Service-CI Relationships
CMDB-CSDM Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the relationship mappings between Discovery-found CI records and the CSDM service hierarchy. This workbook drives the service impact analysis capability: when a CI is marked as impacted in an incident, ServiceNow automatically identifies which services are affected. Completing this workbook is what transforms a list of CIs into a functioning service map.
Who fills this out | ECS SA leads the mapping exercise using Discovery results. Customer Infrastructure Lead and Application Owners validate. Complete in Sprint 2 after first Discovery run.
Sprint window | Sprint 2 Weeks 1–2
Estimated effort | 4–6 hours (initial mapping from Discovery results); ongoing as Discovery finds new CIs
Related workbooks | 02 CI Class Selection · 04 Technical Services & Apps · 03 Business Service Definitions
Success criteria
• | Every CI in the in-scope classes (Workbook 02) is related to at least one CSDM service.
• | The CMDB relationship graph shows a complete chain from Business Service to CI for each Business Service.
• | Service Map view in ServiceNow is navigable without broken relationships.
• | CMDB Health — Relationship completeness score is above 80% for in-scope CI classes.

## Process Decisions
05 — Service-CI Relationships — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should every CI be related to a service or only critical CIs? | Every CI in the agreed in-scope class list must have at least one service relationship. CIs with no service relationship do not contribute to service impact analysis and reduce the CMDB health score. |  | The OOTB CMDB health dashboard flags 'orphaned CIs' (no service relationship) as a health problem. Orphaned CIs are also invisible to Virtual Agent and Predictive Intelligence service context. A CI without a service relationship is a CI with no value.
2 | Can a CI be related to multiple services? | Yes. A shared infrastructure CI (e.g., a core network switch) should be related to all services that depend on it. Use the 'Depends on' relationship type. There is no limit on the number of service relationships per CI. |  | Shared infrastructure by definition supports multiple services. Artificially limiting relationships to one service creates incorrect service impact analysis during outages.
3 | How should we handle CIs discovered but not in the agreed class scope? | Do not create service relationships for out-of-scope CI classes. Mark these CIs as 'Out of scope — pending Phase 2' in the notes field and set operational_status to 'Non-operational' if they should not appear in service impact analysis. |  | Creating service relationships for out-of-scope CIs expands the maintenance commitment beyond what was agreed. Keep the scope boundary clean.
4 | What is the process for newly discovered CIs after Sprint 2? | Establish a monthly CI relationship review. New CIs found by Discovery are automatically created; ECS configures an IRE reconciliation rule that assigns new CIs to the correct Technical Service based on subnet/naming pattern. Customer IT Ops reviews and confirms monthly. |  | Discovery runs continuously after Sprint 2. Without a process for relating new CIs to services, the CMDB degrades over time regardless of how well it started.

## Dependencies
05 — Service-CI Relationships — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | First Discovery run completed and CI records created | Required | ECS Architect | Sprint 2 Wk 1 | Cannot map relationships until CIs exist.
2 | Technical Service and Application Service CIs loaded (Workbook 04) | Required | ECS SA | Sprint 1 Wk 2 | Service shells must exist before relationships can be created.
3 | Business Service CIs loaded (Workbook 03) | Required | ECS SA | Sprint 1 Wk 2 | Required for the full relationship chain.
4 | Network diagram or infrastructure topology document | Recommended | Customer Infrastructure Lead | Sprint 2 Wk 1 | Helps identify which CIs support which Technical Services when Discovery data is ambiguous.

## Configuration Data
05 — Service-CI Relationships — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Relationship Mapping Matrix
Business Service → Technical Service relationship type | Used by::Depends on | OOTB relationship type. Do not create custom types.
Technical Service → Server/VM CI relationship type | Used by::Depends on
Application Service → Server CI relationship type | Hosted on::Hosts | Use 'Hosted on' for application-to-server relationships.
CI → CI relationship (peer) | Connected to::Connected to | Use for network/dependency peer relationships.
2. IRE Auto-Relationship Rules (recommended)
cmdb_ci_computer → 'End User Computing' Technical Service | Subnet match or AD OU match | Configure IRE rule to auto-relate endpoint CIs to the EUC Technical Service.
cmdb_ci_server → 'Windows Server Infrastructure' or 'Linux Infrastructure' | OS attribute match | Auto-relate servers to the appropriate infrastructure Technical Service by OS.
cmdb_ci_appl → Application Service CI | Application name match | Match installed application CIs to Application Service CIs by normalised name.

## R&R
05 — Service-CI Relationships — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Map Discovery-found CIs to Technical Services | R/A | C | ECS SA leads mapping; customer confirms infrastructure groupings.
Configure IRE auto-relationship rules | R/A | I | ECS Architect configures IRE; this is a technical configuration step.
Validate service map completeness (relationship view) | R | A | ECS validates technically; customer confirms service map is meaningful.
Review and confirm orphaned CI list | R | A | ECS identifies orphans; customer decides classification.
Establish monthly CI relationship review process | C | R/A | Customer IT Ops owns the ongoing review; ECS advises on tooling.
Document relationship standards for future CI types | R/A | I | ECS SA documents the relationship standards for customer runbook.

## Consultant Guide
05 — Service-CI Relationships — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
IRE auto-relationship rules
The most efficient way to relate hundreds of CIs to services is through IRE (Identification and Reconciliation Engine) relationship rules. Configure rules that automatically relate CIs to services based on observable attributes (subnet, OS, application name). This means every new CI found by Discovery is automatically placed in the service hierarchy without manual intervention. Spend an extra hour in Sprint 2 getting IRE rules right — it saves 10+ hours of manual mapping and prevents CMDB drift.
Service Map walkthrough with the customer
Before Sprint 2 ends, run a 30-minute Service Map walkthrough with the IT Operations Lead. Show them: (1) a Business Service and its downstream Technical Services, (2) click into a Technical Service and show the CI list, (3) simulate a CI outage and show the service impact pop-up. This walkthrough converts CMDB sceptics. The visual payoff of a complete service map is the most effective tool for sustaining customer engagement with CMDB data quality.
Orphaned CI triage
After the first Discovery run, export the list of CIs with no service relationship (CMDB Health report — orphaned CIs). Work through this list with the customer in Sprint 2 Week 2: most orphaned CIs either belong to an existing Technical Service (easy fix) or are out-of-scope CIs that Discovery found but shouldn't be tracked (set operational_status = Non-operational). Aim for zero orphaned in-scope CIs before Sprint 2 closes.

## Adoption vs Re-engineering
05 — Service-CI Relationships — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to manually maintain all CI-to-service relationships | Configure IRE auto-relationship rules for relationship maintenance. Manual-only maintenance degrades within 60 days as Discovery continuously finds and creates new CI records. | IRE auto-relationship rules are OOTB functionality specifically designed for this purpose. Manual maintenance of CI relationships is not scalable and is the leading cause of CMDB health degradation. | 'Manual relationship maintenance works for the first sprint, but Discovery runs every day and creates new CIs constantly. IRE rules mean every new CI is automatically placed in the right service — you only need to review exceptions, not manage every individual record.' | Only for very small, static environments (<100 CIs total). Still document the process so it can be automated later.

## ServiceNow Mapping
05 — Service-CI Relationships — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Relationship Table
cmdb_rel_ci | CI Relationship | All CI-to-CI and CI-to-Service relationships. Primary relationship table.
cmdb_rel_type | CI Relationship Type | OOTB relationship types. 'Depends on::Used by' and 'Hosted on::Hosts' are most commonly used.
2. IRE Configuration
IRE Rule | Identification Rules > Relationship Rules | Configure in CMDB > Identification/Reconciliation > Relationship Rules.
Pattern match | Attribute-based (subnet, OS, app name) | Use existing CI attributes to drive automatic relationship assignment.
3. OOTB Reporting
Service Map | CMDB > Dependency Views > Services | Visual service map driven by cmdb_rel_ci.
CMDB Health — Relationship completeness | CMDB > CMDB Health Dashboard | Measures % of in-scope CIs with at least one service relationship.
Orphaned CI report | CMDB > CMDB Health > Orphaned CIs | CIs with no service relationship. Target: 0 for in-scope classes.