## Instructions
03 — Credential Management
Discovery Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Discovery credential strategy: which credential types are needed, how they are stored in ServiceNow, and what permissions each credential requires. Credential gaps are the primary cause of incomplete Discovery — a CI that cannot be authenticated produces only a stub record with no meaningful attributes.
Who fills this out | Customer-side: IT Operations Lead and Active Directory admin provide credentials. ECS Architect configures the credential store in ServiceNow.
Sprint window | Sprint 1 Week 2 (must be ready before Sprint 2 Discovery runs)
Estimated effort | 2–4 hours to gather credentials and configure credential store
Related workbooks | 01 Discovery Scope · 02 MID Server Configuration
Success criteria
• | Windows/WMI credentials are stored in ServiceNow credential store and validated.
• | Linux/SSH credentials are stored and validated (if Linux hosts are in scope).
• | SCCM/Intune API credentials are stored for SGC configuration.
• | VMware vCenter credentials are stored (if virtualised environment).
• | Credential rotation plan is documented.

## Process Decisions
03 — Credential Management — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should Discovery use a dedicated service account or existing admin accounts? | Dedicated Discovery service account with the minimum permissions required. Never use a named admin account for Discovery — it ties Discovery availability to an individual's account status. |  | Named admin accounts get disabled when the person leaves, locked when the password expires, and audited in ways that create noise. A dedicated service account with a documented rotation schedule is the OOTB best practice.
2 | What permissions does the Windows Discovery account need? | Local administrator on target Windows devices (for WMI access). Domain-joined — member of the local Administrators group via GPO, not a domain admin. Specifically needs: WMI namespace access, Remote Registry access, and Service Control Manager access. |  | Domain admin for Discovery is the most common over-privilege request from customers. WMI Discovery does not require domain admin. Document the exact permissions to support the security team's approval process.
3 | How should credentials be stored and secured in ServiceNow? | Use the OOTB Credential Store (Discovery > Credentials). Passwords are encrypted at rest using the instance encryption key. Do not store credentials in Discovery schedule notes or configuration fields. |  | The OOTB Credential Store is the only security-compliant method for storing Discovery credentials in ServiceNow. Any other storage method creates an audit finding.
4 | How often should Discovery credentials be rotated? | Align to the organisation's password policy — typically every 90 days. Configure a calendar reminder for the ECS SA and the customer IT Ops Lead. ServiceNow must be updated on each rotation. |  | Expired Discovery credentials cause Discovery to fail silently — CIs are not updated but no alert is generated unless CMDB Health staleness rules are in place. A rotation calendar prevents this.

## Dependencies
03 — Credential Management — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Active Directory service account created with minimum permissions | Required | Customer AD Admin | Sprint 1 Wk 2
2 | Linux service account with SSH key (if Linux in scope) | Required | Customer Linux Admin | Sprint 1 Wk 2 | SSH key authentication is preferred over password for Linux Discovery.
3 | VMware vCenter read-only account (if virtualised) | Required | Customer VMware Admin | Sprint 1 Wk 2
4 | SCCM API account for Service Graph Connector | Required | Customer SCCM Admin | Sprint 1 Wk 2
5 | Intune API credentials (Azure AD app registration) | Required | Customer Azure Admin | Sprint 1 Wk 2 | Intune SGC uses OAuth — requires Azure AD app registration with Device.Read.All permission.

## Configuration Data
03 — Credential Management — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Credential Store Entries
Windows/WMI credential name | ECS_Discovery_Windows | Named in ServiceNow Credential Store.
Windows account format | DOMAIN\svc_discovery (or svc_discovery@domain.com)
Linux/SSH credential type | SSH Private Key (preferred) or Username/Password
VMware credential name | ECS_Discovery_VMware | Read-only vCenter account.
SCCM SGC credential | ECS_SGC_SCCM | SCCM service account with Read access to SCCM WMI namespace.
Intune SGC credential | ECS_SGC_Intune | Azure AD app registration — Client ID, Client Secret, Tenant ID.
2. Minimum Permission Requirements
Windows Discovery — required groups/permissions | Local Administrators (via GPO); WMI namespace root\cimv2 read; Remote Registry read
Linux Discovery — required permissions | SSH login; sudo for specific commands (lshw, dmidecode, ifconfig)
VMware vCenter — required role | Read-Only (OOTB vCenter role)
SCCM — required permissions | Read access to SMS WMI namespace; Collection Read
Intune Azure AD app — required API permissions | Device.Read.All; DeviceManagementManagedDevices.Read.All
3. Credential Rotation
Rotation frequency | [Customer to complete — align to password policy]
Rotation owner | [Customer to complete] | IT Ops Lead or AD Admin.
ServiceNow update process | Update credential in Discovery > Credentials > [credential record] | ECS SA or customer admin updates the record on each rotation.

## R&R
03 — Credential Management — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Create Discovery service accounts with minimum permissions | C | R/A | Customer AD/Linux/VMware admins create accounts.
Configure credentials in ServiceNow Credential Store | R/A | I | ECS Architect configures the Credential Store.
Test credential against target devices | R/A | C | ECS Architect tests; customer confirms access is correct.
Document credential rotation calendar | R/A | C | ECS SA documents; customer IT Ops owns ongoing rotation.
Configure Intune Azure AD app registration | C | R/A | Customer Azure Admin creates the app registration.

## Consultant Guide
03 — Credential Management — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The domain admin pushback
Security teams sometimes push back on providing any account for Discovery, asking for justification of each permission. Prepare a one-page permission justification document: WMI requires Local Admin on the target because Microsoft's WMI security model does not support a 'WMI read-only' role. Remote Registry is needed for software inventory. Service Control Manager is needed for service state. Having this document ready prevents a 2-week security review delay.
SSH key vs password for Linux
Always request SSH key authentication for Linux Discovery, not a password. SSH keys are more secure, do not expire, and are easier to audit. If the customer insists on password authentication, configure the credential with the password and document the rotation requirement. Key rotation for SSH keys is still recommended annually.

## Adoption vs Re-engineering
03 — Credential Management — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We don't want to give Discovery full local admin — can we use a limited account? | Local admin is the minimum required for WMI Discovery on Windows. There is no lower-privilege option for full Discovery. | WMI's security model requires local admin for remote access. Microsoft does not provide a 'WMI read-only' role. The account is dedicated to Discovery and monitored — it cannot be used interactively. | 'The local admin requirement is a Microsoft constraint, not an ECS choice. The Discovery account cannot log in interactively, cannot make changes — it only reads data via WMI. Your SIEM will show it as a service account with read activity only. We document this for your audit record.' | If the security team absolutely refuses local admin, Discovery can run with limited scope using SNMP (network devices) and agent-based discovery (ServiceNow agent installed on each device). Both produce inferior data compared to WMI Discovery.

## ServiceNow Mapping
03 — Credential Management — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Credential Configuration
Credential Store | Discovery > Credentials | All Discovery credentials stored here. Encrypted at rest.
Credential Affinity | Discovery > Credential Affinity | Map specific credentials to specific IP ranges for multi-credential environments.