## Instructions
06 — Reconciliation & IRE Rules
Discovery Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Identification and Reconciliation Engine (IRE) rules that prevent duplicate CI creation and control which data source wins when multiple sources report conflicting attribute values. IRE is the governance layer that keeps the CMDB accurate when Discovery, SCCM SGC, and Intune SGC all run simultaneously.
Who fills this out | ECS Architect designs the IRE rules; customer validates the deduplication results after first Discovery + SGC runs.
Sprint window | Sprint 2 Weeks 1–2 (configure before first combined Discovery + SGC run)
Estimated effort | 3–4 hours to configure and validate IRE rules
Related workbooks | 04 Discovery Schedules · 05 SGC Configuration
Success criteria
• | IRE identification rules are configured for each in-scope CI class.
• | No duplicate CI records exist after combined Discovery + SGC run.
• | Source precedence rules are configured (which data source wins conflicts).
• | IRE auto-relationship rules are configured (links CIs to CSDM services).
• | IRE reconciliation log is reviewed and any conflicts are resolved.

## Process Decisions
06 — Reconciliation & IRE Rules — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What should be the primary CI identifier for Windows computers? | Serial number as the primary identifier, with hostname as a secondary fallback. Never use IP address as a CI identifier — IP addresses change. |  | Serial numbers are stable hardware identifiers that do not change when devices are reimaged, renamed, or moved. IP addresses change with DHCP and network moves. A serial-number-based IRE rule prevents duplicate CIs when a device appears in multiple data sources.
2 | Which data source should win when attributes conflict? | SCCM SGC wins for endpoint attributes (hardware, OS, software). Discovery wins for server attributes (IP, services, running processes). Intune SGC wins for modern management attributes (compliance state, MDM enrollment). Configure source precedence per CI class. |  | Without explicit source precedence, IRE uses a first-in rule that produces unpredictable results when sources conflict. Explicit precedence ensures the most authoritative source always wins for each attribute type.
3 | Should IRE auto-create new CI classes when Discovery finds unexpected device types? | No. Configure IRE to only create CI records for the agreed in-scope classes. For out-of-scope device types, IRE should log the discovery without creating a CI record. |  | Auto-creating CI records for out-of-scope classes undermines the MVP scope boundary agreed in the CMDB-CSDM pack. IRE class restrictions are the enforcement mechanism for the CI class governance gate.

## Dependencies
06 — Reconciliation & IRE Rules — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | CI Class Selection (CMDB-CSDM Workbook 02) confirmed | Required | ECS SA | Sprint 1 Wk 2 | IRE rules are scoped to agreed CI classes.
2 | Discovery schedules configured (Workbook 04) | Required | ECS Architect | Sprint 2 Wk 1
3 | SGC configured (Workbook 05) | Required | ECS Architect | Sprint 2 Wk 1

## Configuration Data
06 — Reconciliation & IRE Rules — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Identification Rules per CI Class
cmdb_ci_computer — primary identifier | Serial number (serial_number) | Fallback: hostname + OS + MAC address.
cmdb_ci_server — primary identifier | Serial number; fallback: hostname + IP
cmdb_ci_vm_instance — primary identifier | VM UUID (vm_inst_uuid from hypervisor) | Never use hostname alone for VMs.
cmdb_ci_appl — primary identifier | Application name + version + host CI sys_id
2. Source Precedence Rules
Endpoint CIs (cmdb_ci_computer) — source priority | SCCM SGC > Intune SGC > Discovery
Server CIs (cmdb_ci_server) — source priority | Discovery > manual
VM CIs (cmdb_ci_vm_instance) — source priority | VMware Discovery > manual
Application CIs (cmdb_ci_appl) — source priority | SCCM SGC > Discovery Software pattern
3. Auto-Relationship Rules
cmdb_ci_computer → End User Computing Technical Service | Subnet or OU match | Configured per CMDB-CSDM Service-CI Relationships workbook.
cmdb_ci_server → Server Infrastructure Technical Service | OS attribute match
New CI class auto-creation | Disabled for out-of-scope classes | IRE will log but not create records for out-of-scope CI types.

## R&R
06 — Reconciliation & IRE Rules — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Design IRE identification rules per CI class | R/A | I | ECS Architect.
Configure source precedence rules | R/A | I | ECS Architect.
Configure auto-relationship rules | R/A | I | ECS Architect.
Review IRE reconciliation log after first combined run | R/A | C | ECS reviews; customer validates deduplication results.
Resolve any IRE conflicts from first run | R/A | C | ECS resolves technical conflicts; customer confirms correct data source.

## Consultant Guide
06 — Reconciliation & IRE Rules — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
IRE is not optional
Some customers ask to defer IRE configuration until after Discovery runs. Never agree — running Discovery without IRE configured creates duplicate CIs that are extremely difficult to clean up after the fact. IRE must be configured before the first Discovery run and the first SGC sync.
Post-run reconciliation review
After the first combined Discovery + SGC run, export the IRE reconciliation log and look for: (1) duplicate matches resolved — confirm the right record was kept, (2) unresolved duplicates — investigate and resolve manually, (3) out-of-scope CI types found — confirm they were not created. This review takes 1 hour and is the most important quality gate in the Discovery sprint.

## Adoption vs Re-engineering
06 — Reconciliation & IRE Rules — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to migrate all our legacy CI records first, then run Discovery | Run Discovery first. Use legacy data as a reconciliation reference, not a migration source. | Migrating legacy CIs before Discovery creates a polluted baseline that IRE must reconcile against. Discovery-first means every CI is authoritative from day one. | 'Your legacy data has value as a checklist — we use it to confirm Discovery found everything. But if we load it into ServiceNow first, Discovery creates duplicates and IRE has to choose which one to keep. Starting clean and validating against your legacy list gives you a trustworthy CMDB from day one.' | Never migrate legacy CIs as a bulk load. Small, strategic manual entries (critical servers not reachable by Discovery) are acceptable with documented rationale.

## ServiceNow Mapping
06 — Reconciliation & IRE Rules — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. IRE Tables
Identification Rule | cmdb_identifier_entry | Defines the CI identifier per class.
Source Precedence | cmdb_source_precedence | Controls which data source wins per attribute.
Reconciliation Log | cmdb_reconciliation_log | Logs all IRE decisions for audit.