## Instructions
05 — Vonage CTI & Interactions
Integration Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Capture requirements, dependencies, configuration, and developer instructions to stand up the Vonage telephony (CTI) integration through ServiceNow Interactions. Phase 1 scope is inbound voice only (chat/email deferred).
Who fills this out | Customer-side: Vonage Contact Center administrator + service desk lead. ECS-side: Solution Architect / senior developer.
Sprint window | Connection + tenant details by end of Sprint 1; build alongside Incident/Request in Stage 2 (Sprints 3-4); validate before Go-Live.
Estimated effort | ~8-12 hours across Sprints 1-4, including porting the legacy Vonage config and test calls.
Where the data comes from | Vonage Contact Center admin (tenant, queues, agents) and the existing Vonage-ServiceNow integration on the legacy instance (for porting).
Related workbooks | 01 Active Directory · 02 Single Sign-On · 03 SCCM · 04 Intune
Success criteria
• | Inbound Vonage call opens/creates an Interaction with caller context (screen-pop).
• | Agent creates or links an Incident/Request from the Interaction (OOTB).
• | Vonage queues map to ServiceNow assignment groups for routing context.
• | No custom telephony middleware - OOTB OpenFrame + Vonage connector only.
• | Parity with the legacy phone experience validated before Go-Live.

## Requirements
Vonage CTI — Integration Requirements
Customer fills the Answer column. Phase 1 = inbound voice only.
# | Requirement Question | Answer | Notes
1 | Which Vonage product is in use (Vonage Contact Center / VCC, or VBC)? Region/data center?
2 | Approximate number of agents and peak concurrent inbound calls in scope?
3 | Confirm Phase 1 channels = inbound voice only (chat, email, SMS deferred)?
4 | CTI mode: OpenFrame softphone embedded in the Agent / Service Operations Workspace?
5 | Screen-pop behavior on inbound call: open/create an Interaction with caller match?
6 | Caller identification: match on sys_user phone/mobile; behavior when no match (guest)?
7 | From the Interaction, agents create or link an Incident and/or Request (RITM)?
8 | Vonage queues/skills - how should they map to ServiceNow assignment groups?
9 | Is click-to-dial (outbound) in scope for Phase 1, or inbound only?
10 | Call recording in scope? Where stored (Vonage vs. link in ServiceNow)? Retention?
11 | Compliance constraints (call recording consent, PII, PCI on IVR)?
12 | Is there an existing Vonage-ServiceNow integration on the legacy instance to port?

## Dependencies
Vonage CTI — Dependencies & Prerequisites
Confirm before integration build begins.
# | Dependency | Status | Owner | Due | Notes
1 | ITSM Core (Incident/Request) available in sub-production | In Progress | ECS |  | Interactions link to incident / sc_req_item
2 | Interaction capability + Agent/Service Operations Workspace available | Not Started | ECS
3 | OpenFrame plugin (com.glide.openframe) activated | Not Started | ECS
4 | Vonage CTI / OpenFrame adapter installed (Vonage / ServiceNow Store) | Not Started | ECS
5 | Vonage tenant admin access + API credentials | Not Started | Customer |  | Vaulted in ServiceNow Credentials by ECS
6 | Agent roles assigned (sn_openframe_user / interaction roles) | Not Started | ECS
7 | SSO configured for agents (see 02 Single Sign-On) | In Progress | ECS
8 | Network allowlist for Vonage CTI domain from agent browsers | Not Started | Customer
9 | Test phone number + test agent provisioned | Not Started | Customer
10 | Legacy Vonage integration inventory captured (for porting) | Not Started | Customer |  | See Port from Legacy tab

## Configuration Data
Vonage CTI — Configuration Data
Customer fills the Value column. Yellow examples = replace with your values.
Field | Value | Notes
1. Vonage Tenant
Vonage product / edition | Vonage Contact Center (VCC) | VBC if business comms only
Region / data center | US | Match agent location
API key / application ID | [customer] | Vaulted by ECS
Credential reference | [ECS will populate] | ServiceNow Credential store
2. OpenFrame
OpenFrame config name | Vonage CTI | Appears in Agent Workspace
Adapter URL | https://<vonage-cti-adapter> | From Vonage/Store adapter
Frame width x height | 400 x 600 | px
Roles with access | sn_openframe_user | Assigned to service desk agents
3. Agent Mapping
Agent -> Vonage extension/agent ID | [customer list] | One row per agent at build
Default agent state on login | Available
4. Queue / Routing Mapping
Vonage queue/skill -> assignment group | [customer mapping] | Drives routing context on the Interaction
Unknown-caller handling | Open Interaction as guest | No sys_user match
5. Recording
Recording in scope (Y/N) | [customer]
Storage / link location | Vonage; link on Interaction | Avoid storing media in ServiceNow
Retention | [customer policy] | Compliance-driven

## R&R
Vonage CTI — Roles & Responsibilities
R=Responsible, A=Accountable, C=Consulted, I=Informed.
Activity | ECS | Customer | Notes
Vonage tenant configuration (queues, agents, numbers) | C | R | Customer's Vonage admin owns; ECS specifies needs
Vonage API credentials creation | C | R | Customer provides; ECS vaults
OpenFrame configuration in ServiceNow | R | C | ECS-managed
Vonage CTI adapter install from Store | R | I | ECS-managed
Agent provisioning + extension mapping | C | R | Customer maps agents to extensions
Queue -> assignment group mapping | R | C | ECS configures; Customer confirms routing
Interaction -> Incident/Request flow configuration | R | C | ECS configures OOTB Interaction behavior
Network allowlist for the CTI domain | I | R | Customer's network team
Call recording compliance / consent | I | A | Customer owns the policy decision
Test calls + UAT | R | C | ECS executes; Customer validates
Long-term ownership of CTI operations | I | R | Customer owns post-Hypercare

## Developer Notes
Vonage CTI — Developer Notes
Internal reference for the ECS Solution Architect / senior developer.
OOTB-First Approach
Use OOTB OpenFrame + the Vonage CTI adapter + the OOTB Interaction record. No custom telephony middleware or scripted softphone.
Interactions is the OOTB omnichannel entry point; Phase 1 implements the voice channel only.
• Caller matching and routing context belong in OOTB CTI config / Decision Tables - not Script Includes.
Implementation Pattern
• Activate OpenFrame (com.glide.openframe) and the Interaction features; confirm Agent/SO Workspace.
• Install the Vonage CTI/OpenFrame adapter (Vonage-provided or ServiceNow Store).
• Configure OpenFrame: name, adapter URL, frame size, and roles (sn_openframe_user) per the Configuration Data tab.
• Configure the Vonage connection (API key, region); vault credentials in the Credential store.
• Map agents to Vonage extensions; assign OpenFrame + interaction roles.
• Configure inbound screen-pop: on call, create/open an Interaction and match the caller by phone (caller number -> sys_user.phone/mobile_phone).
• Configure Interaction -> Incident/Request: agents use the OOTB Create Incident / Create Request action; interaction_related_record links them.
• Map Vonage queues/skills to assignment groups for routing context.
• Validate in sub-prod with a test number + agent: screen-pop, Interaction creation, record linkage, and (if in scope) the recording link.
• Promote via update set; re-point the CTI connection to the production Vonage tenant.
Guardrails
• Any custom click-to-dial or screen-pop logic beyond OOTB CTI capability is a customization - route it to the Customization Council.
• Do not persist call media in ServiceNow; store in Vonage and link from the Interaction.

## Port from Legacy
Vonage CTI — Port from Legacy Instance
Use the existing Vonage integration as the spec; rebuild on OOTB OpenFrame + connector.
Porting Approach
The existing Vonage integration on the legacy domain-separated instance is the reference. Take the existing setup/config and use it to build the new integration - like SCCM, the OOTB connector replaces bespoke pipelines. Lift the configuration and intent, not the custom code.
# | Step | Disposition / Notes
1 | Inventory the legacy Vonage integration: OpenFrame config, adapter URL, API creds, click-to-dial and screen-pop scripts, call-logging business rules. | Customer + ECS
2 | Capture the legacy caller-match logic and the screen-pop target (what record opened, what fields populated). | Reference for OOTB config
3 | Export Vonage tenant settings: queues/skills, numbers, agent roster, business hours. | Reuse as-is
4 | Categorize each item: OpenFrame/connector config = rebuild OOTB; custom screen-pop = evaluate vs OOTB CTI; bespoke middleware = Council. | Most = config, not code
5 | Rebuild on the new instance using OOTB OpenFrame + Vonage adapter; apply the exported tenant settings. | Do NOT port custom pipelines
6 | Carry forward only customizations with a documented business need, via the two-key decision. | Logged in Triage Log
7 | Validate parity: inbound call -> screen-pop -> Interaction -> Incident/Request matches the legacy experience. | UAT sign-off

## ServiceNow Mapping
ServiceNow Mapping (ECS Solution Architect reference)
OOTB tables, fields, and features used.
Element | Table / Object | Notes
Interaction record | interaction | The entry point created on an inbound call
Interaction <-> task link | interaction_related_record | Links the Interaction to incident / sc_req_item
Incident | incident | Created/linked from the Interaction
Request item | sc_req_item | Created/linked from the Interaction
OpenFrame configuration | sys_cti_openframe (OpenFrame config) | Hosts the Vonage softphone in the workspace
Agent | sys_user + sn_openframe_user role | CTI-enabled service desk agents
Caller match | sys_user.phone / mobile_phone | Screen-pop identification
Assignment routing | sys_user_group | Vonage queue/skill -> assignment group