## Instructions
04 — Change Management & CAB
ITSM Process Pack · ECS Federal · ServiceNow Practice
Purpose | Change Management governs how changes are introduced to the production environment. This workbook captures change types, risk calculation, CAB membership and cadence, approval policies, and standard change templates — all aligned to OOTB Change Management with CI-driven risk scoring.
Who fills this out | Customer-side: Change Manager, CAB Chair, IT Operations leads. ECS-side: Solution Architect, Process Consultant.
When it's due | Process Decisions in Sprint 1 or 2; configuration in Sprint 3-4.
How long it takes | 5–7 hours of decision-making — Change has more decisions than other processes.
Where the data comes from | Existing Change SOPs, CAB charter, change-history reports, blackout calendar.
How to use this workbook | Same workflow. Change has the most decisions because it touches every workstream.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-populated; customer confirms or proposes alternative with rationale.
Dependencies | Other Packs and source data that must be in place before this process can be configured.
Configuration Data | The final OOTB-aligned configuration parameters — used by the consultant to build in ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant building the configuration.
Adoption vs Re-engineering | Pushback scenarios — when the customer asks for legacy patterns, how to redirect to OOTB.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.
Common pitfalls
• | Custom change types beyond Standard / Normal / Emergency — almost always solvable via field categorization.
• | Custom risk calculation script instead of OOTB Change Risk Assessment.
• | CAB membership without rotation or alternates — single point of failure.
• | Standard change templates without owner — they go stale and become a security risk.
Who to ask | Your engagement's ECS Solution Architect.

## Process Decisions
Change Management & CAB — Process Decisions
Decisions to make collectively. ECS recommendation pre-populated; customer confirms or proposes alternative with rationale.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Number of change types | 3 (Standard, Normal, Emergency) — OOTB
2 | Standard change templates — initial set | 5–10 high-frequency, low-risk changes (e.g., Security patches, Printer install, AD group add)
3 | Risk calculation method | OOTB Change Risk Assessment with CI-driven scoring
4 | Approval policy — Standard | Auto-approved (template pre-approved)
5 | Approval policy — Normal | Manager + CAB review
6 | Approval policy — Emergency | Emergency CAB (eCAB): Change Manager + on-call CAB member
7 | CAB cadence | Weekly: Tuesdays 2pm ET, 60 min
8 | CAB membership | Standing members: IT Director, Service Desk Lead, Network Lead, Security Lead, App Dev Lead, Change Manager (chair)
9 | CAB voting threshold | Simple majority of attending members
10 | Blackout windows | Q-end weeks (last week of March, June, Sep, Dec); major holidays; event-driven (announce in advance)
11 | Change Calendar visibility | All ServiceNow users (read); Change Manager (write); CAB members (write own)
12 | Conflict detection | OOTB conflict detection on overlapping CI + time
13 | Implementation window enforcement | OOTB — change cannot be implemented outside its scheduled window without override
14 | Post-implementation review (PIR) | Required for failed Normal/Emergency changes; optional for successful changes
15 | CMDB requirement | Change must reference at least one CI; auto-populates impacted services

## Dependencies
Change Management & CAB — Dependencies
Other Packs and source data that must be in place before this process can be configured.
# | Dependency | Status | Owner | Due | Notes
1 | CSDM with Business/Technical/Application Services and CIs | In Progress | ECS
2 | Foundation Data Pack — Schedules (for blackout windows) | Complete | Customer
3 | Foundation Data Pack — Groups (CAB members, fulfillment) | Complete | Customer
4 | Integration Pack — AD/Entra ID (for approver hierarchy) | Complete | ECS
5 | CAB charter document signed | In Progress | Customer
6 | CAB Workbench plugin activated | Complete | ECS
7 | Change Risk Assessment plugin activated | Complete | ECS
8 | Standard change templates drafted (5-10 initial) | Not Started | Customer
9 | Blackout calendar documented | Not Started | Customer

## Configuration Data
Change Management & CAB — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are recommendations; replace with customer-confirmed values.
Field / Setting | Value | Notes
1. Change Types
Type 1 | Standard — pre-approved, low-risk, repeatable | OOTB
Type 2 | Normal — standard approval workflow + CAB | OOTB
Type 3 | Emergency — eCAB, post-implementation review required | OOTB
2. Risk Calculation
Risk Assessment plugin | Activated | OOTB
Risk factors | Impact (CI criticality), Affected user count, Implementation time, Rollback complexity | OOTB Risk Assessment
Risk levels | Low, Moderate, High | OOTB
3. CAB
CAB schedule | Weekly: Tuesdays 2pm ET, 60 min
CAB Workbench enabled | Yes | OOTB
eCAB on-call rotation | Weekly rotation from CAB members; 7-day rotation, 7am Mon to 7am next Mon
4. Approval Policies
Standard change approval | Auto-approved on submission (template pre-approved)
Normal change approval | Manager → Group manager → CAB review
Emergency change approval | eCAB on-call + Change Manager (concurrent)
5. Standard Change Templates (initial)
Template 1 | Security patch — non-disruptive | 5 templates initial
Template 2 | Printer install / replacement
Template 3 | AD group membership add
Template 4 | Network port enable
Template 5 | Application restart (named apps)
6. Blackout Windows
Q-end blackouts | Last week of March, June, September, December
Holiday blackouts | December 23 – January 2; Thanksgiving week
Event-driven blackouts | Announced in CAB; tracked in Change Calendar
7. Conflict Detection
Conflict detection enabled | Yes — OOTB on CI + time overlap | OOTB

## R&R
Change Management & CAB — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Process Decisions facilitation | R | C | ECS facilitates.
CAB charter design | C | R | Customer owns; ECS provides template.
Standard change template authoring | C | R | Customer subject-matter experts; ECS reviews for OOTB alignment.
Risk Assessment configuration | R | C | ECS configures OOTB.
CAB Workbench configuration | R | I | ECS-managed.
Approval policy configuration | R | C | ECS configures.
Blackout calendar configuration | R | C | ECS configures from Customer-provided list.
CAB member training on Workbench | R | C
eCAB rotation setup and training | C | R | Customer manages rotation.
UAT for change workflows | R | R | Joint.
Production cutover | R | A
Long-term ownership | I | R | Customer's Change Manager.

## Consultant Guide
Change Management & CAB — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Step-by-step ServiceNow updates.
OOTB Change Foundations
Use OOTB Change Management plugin (com.snc.change_management) and CAB Workbench (com.snc.cab.workbench). The OOTB three-type model (Standard, Normal, Emergency) handles 95% of customer scenarios.
Implementation Sequence
• Activate Change Management, Change Risk Assessment, and CAB Workbench plugins.
• Configure change types per Process Decisions (typically OOTB three).
• Configure Risk Assessment factors and levels per Process Decisions.
• Configure approval policies via OOTB Approval Definitions (no custom Business Rules).
• Configure CAB schedule and members; set up CAB Workbench rotation.
• Configure eCAB on-call group and rotation schedule.
• Author standard change templates with pre-approval; assign owners.
• Configure blackout windows in Change Calendar (System > Calendar).
• Configure conflict detection rules (OOTB).
• Configure Performance Analytics Change dashboard (success rate, lead time, blackout violations, eCAB volume).
Common Pitfalls to Avoid
• Custom change_type field with 5+ values — almost always reverts to the OOTB three after operational pain.
• Custom risk-calculation Script Include — OOTB Risk Assessment is configurable enough.
• CAB Workbench bypassed in favor of email approvals — loses audit trail and Workbench efficiency.
• Standard change templates without owners — they become security risks as conditions drift.
• Blackout windows without conflict detection — changes get scheduled in blackout and noticed too late.
References
• ServiceNow Docs: Change Management
• ServiceNow Docs: CAB Workbench
• ServiceNow Docs: Change Risk Assessment

## Adoption vs Re-engineering
Change Management & CAB — Adoption vs Re-engineering
When the customer says "but our old system did X." Use these scenarios to redirect the conversation toward OOTB adoption rather than re-engineering legacy patterns.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"We need 5 change types: Standard, Normal, Emergency, Project, Vendor." | OOTB three (Standard, Normal, Emergency); use category or sub-type for Project/Vendor distinction. | More change types = more approval complexity and broken reporting. The three OOTB types map to ITIL and integrate with all OOTB analytics. | "Project and Vendor are typically Normal changes with extra documentation. Sub-categorize via field, keep the three types. What specifically does Project type need that Normal can't accommodate?" | Multi-tenant scenarios with regulatory separation requirements.
"Custom risk calculation that uses our own scoring formula." | OOTB Change Risk Assessment with CI-driven factors. | Custom risk scripts need maintenance, don't update with CSDM changes, and break upgrade paths. OOTB Risk Assessment is configurable. | "OOTB Risk Assessment is configurable. Walk me through your scoring — most customer formulas can be expressed via OOTB factors. If genuinely needed, the OOTB risk_level can be overridden via Decision Table without custom Script Include." | Compliance frameworks with non-standard risk dimensions (rare; usually solved by Decision Table override).
"CAB approves via email — easier than logging into ServiceNow." | OOTB CAB Workbench with mobile-friendly voting. | Email approvals lose audit trail, lose conflict context, and don't show CI impact at vote time. | "CAB Workbench shows conflict, CI impact, risk score, and lets vote happen in 30 seconds — same time as email reply, with full audit. Mobile-friendly. After two weeks of using it, the team won't go back." | Air-gapped environments without ServiceNow access — rare.
"Standard change templates managed in a Wiki; we copy/paste into change tickets." | OOTB Standard Change Catalog — template defines pre-approval, fields, workflow. | Copy/paste defeats the purpose of standard changes (template integrity, pre-approval, automation). | "Standard change templates ARE the pre-approval. Wiki templates require manual review every time, which defeats the standard-change concept. Migrating into the OOTB catalog takes 2 hours per template and you get pre-approval, conflict detection, and analytics." | Don't customize.
"Change calendar in Outlook — that's where everyone looks." | OOTB Change Calendar with Outlook integration. | Outlook calendar loses conflict detection, doesn't show CI impact, and has no audit trail. | "OOTB Change Calendar feeds Outlook for visibility but adds conflict detection and CI-impact view. People still see it in Outlook; you gain the conflict math." | Don't customize.
"Custom approval workflow per CI category." | OOTB Approval Definitions with conditions on CI fields. | Custom approval workflows fragment the approval logic and break with CI category changes. | "Approval Definitions support conditions per CI attribute. The OOTB pattern handles per-category routing without code. Walk through your conditions — most of them fit Approval Definition rules." | Genuinely complex scenarios (multi-stage, dynamic) — solvable with Flow Designer flows, still no code required.
"Custom field for 'change reason' beyond OOTB description." | OOTB description + justification + risk_reason fields cover this. | Custom fields without business-need justification are upgrade burden. | "Description, justification, risk_reason — three OOTB fields. Walk me through what change reason captures that these don't." | Compliance frameworks requiring specific labeled fields (rare; usually solved by relabeling OOTB).

## ServiceNow Mapping
ServiceNow Mapping (for ECS Solution Architect reference)
Primary table: change_request. Standard change templates: std_change_proposal, std_change_record_producer. Risk: change_request.risk_assessment + Risk Assessment plugin. CAB: cab_meeting, cab_agenda_item, cab_workbench. Approval: sysapproval_approver, sysapproval_group. Calendar: cmn_calendar_blackout. Plugins: com.snc.change_management, com.snc.change.risk, com.snc.cab.workbench.