## Instructions
06 — Catalog Item Configuration Data
Service Catalog Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | The configuration-ready data sheet for every catalog item in the Sprint 4 build list. This workbook is the single source of truth that ECS SA uses to build each item in ServiceNow — containing all agreed fields, variables, fulfillment routing, and approval settings in one place. Customer fills the data; ECS SA loads it.
Who fills this out | Customer-side: ITSM Process Owner completes the per-item data fields, drawing from decisions made in Workbooks 01-05. ECS SA reviews for completeness before building each item. One section per catalog item.
Sprint window | Sprint 4 Weeks 1–2
Estimated effort | 30-60 minutes per catalog item for the customer to complete
Related workbooks | 01 Category Rationalization · 02 Catalog Item Inventory · 03 Item Template Standards · 04 Fulfillment Workflow Decisions · 05 Approval Matrix
Success criteria
• | Every Sprint 4 catalog item has a complete configuration data section in this workbook.
• | All fields are customer-completed and ECS SA-reviewed before the item is built.
• | Item descriptions follow the 3-element template from Workbook 03.
• | Variable sets are documented with type, label, mandatory status, and OOTB choices (for Choice variables).
• | No item is built in ServiceNow until its configuration data section is complete and approved.

## Process Decisions
06 — Catalog Item Configuration Data — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Who is accountable for completing the configuration data for each item? | The item owner (the fulfillment group lead or process owner for that item) completes the configuration data. ECS SA provides the template and reviews for compliance with the item template standards (Workbook 03). |  | Configuration data that is written by ECS SA without customer input frequently contains inaccurate descriptions, wrong delivery times, and missing variables. The item owner is the only person who knows what the item actually delivers and what data is needed to fulfill it.
2 | What happens if a customer submits configuration data that doesn't meet the template standards? | ECS SA returns the section to the item owner with specific feedback. The item is not built until the configuration data meets the standards. This is the quality gate. |  | Building items from non-compliant configuration data creates rework — the item must be rebuilt after go-live when issues surface. The quality gate at configuration data review is cheaper than fixing items in production.
3 | Should all Sprint 4 items be built simultaneously or sequentially? | Build sequentially — one or two items at a time. Build, test, and validate each item before starting the next. This surfaces variable design issues and workflow problems early, allowing course correction before the pattern is replicated across all items. |  | Building all items simultaneously and testing at the end means a design flaw discovered in item 10 has already been replicated in items 1–9. Sequential build and test is slower per item but faster overall.

## Dependencies
06 — Catalog Item Configuration Data — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Workbooks 01–05 complete and approved | Required | Customer ITSM Owner + ECS SA | Sprint 4 Wk 1 | Configuration data must reference approved decisions from all prior workbooks.
2 | ServiceNow non-production environment available for build and test | Required | ECS Architect | Sprint 4 Wk 1 | Items are built and tested in non-prod before promotion to production.
3 | Fulfillment group assignment groups configured in ServiceNow | Required | ECS SA | Sprint 0 | Assignment groups must exist before catalog items can reference them.

## Configuration Data
06 — Catalog Item Configuration Data — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Catalog Item Configuration Template (repeat per item)
Item Name (display name) | [Customer to complete] | What the user sees on the catalog. Plain language.
Short Description (search index) | [Customer to complete — 1 sentence] | Used by Employee Center search. Include keywords users would search.
Full Description (3-element template) | [Customer to complete — what / who / how long] | Follow the 3-element template from Workbook 03.
Category (from Workbook 01) | [Customer to complete] | Must be from the approved category structure.
Fulfillment Group | [Customer to complete] | Must be an existing assignment group.
Delivery Time (business days) | [Customer to complete] | Realistic estimate. This appears on the item and drives SLA.
Approval Required? (from Workbook 05) | [Yes / No]
Approver Role (if Yes) | [Manager / Security Team / Other — specify]
Available To | [All employees / Named group / Department] | Use 'All employees' by default. Restrict only with documented policy.
2. Item Variables (complete per item — up to 5 item-specific)
Variable 1 — Label | [Customer to complete] | Plain language field label.
Variable 1 — Type | [Single Line / Multi-Line / Reference / Choice / Date / Yes/No] | OOTB types only.
Variable 1 — Mandatory? | [Yes / No] | Mandatory only if empty prevents fulfillment.
Variable 1 — Choices (if Choice type) | [List the choices, comma-separated] | Keep choices to 5 or fewer options.
Variable 2 — Label | [Customer to complete or N/A]
Variable 2 — Type | [Type or N/A]
Variable 2 — Mandatory? | [Yes / No / N/A]
Variable 2 — Choices (if applicable) | [Choices or N/A]
Variable 3 — Label | [Customer to complete or N/A]
Variable 3 — Type | [Type or N/A]
Variable 3 — Mandatory? | [Yes / No / N/A]
Variable 3 — Choices (if applicable) | [Choices or N/A]
Additional variables 4–5 | [Repeat pattern above or mark N/A]
3. Fulfillment Workflow (from Workbook 04)
Workflow Model | [Simple / Approval-then-Fulfill / Multi-stage] | From Workbook 04 decisions.
Catalog Task 1 — Group (if Multi-stage) | [Group or N/A]
Catalog Task 1 — Description | [What does this team do? or N/A]
Catalog Task 2 — Group (if Multi-stage) | [Group or N/A]
Catalog Task 2 — Description | [What does this team do? or N/A]
Completion Criteria | [Customer to complete — specific observable outcome] | What does 'done' look like for this item?
4. ECS SA Build Quality Gate
Description follows 3-element template | [ECS to validate — Yes / No / Returned for revision]
Variable count ≤ 5 item-specific | [ECS to validate]
All variables use OOTB types | [ECS to validate]
Shared variable set applied | [ECS to validate]
Built and tested in non-prod | [ECS to validate]
Promoted to production and validated | [ECS to validate]
Build sign-off (ECS SA) | [ECS SA name and date]
Customer acceptance | [Customer ITSM PO name and date]

## R&R
06 — Catalog Item Configuration Data — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Complete configuration data for each Sprint 4 item | I | R/A | Customer item owners complete; ECS SA reviews.
Review configuration data against template standards | R/A | C | ECS SA quality gate. Returns non-compliant sections for revision.
Build each catalog item in non-production ServiceNow | R/A | I | ECS SA builds; sequential order.
Test each item with a test submission in non-prod | R/A | C | ECS SA tests; customer fulfillment lead validates the test RITM.
Promote tested items to production | R/A | C | ECS SA promotes; customer ITSM PO approves promotion.
Customer acceptance sign-off per item | I | R/A | Customer ITSM PO signs off each item before go-live.
Communicate catalog launch to users | I | R/A | Customer Communications team handles user communication.

## Consultant Guide
06 — Catalog Item Configuration Data — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Sequential build discipline
Build one item, test it, get customer sign-off, then build the next. The temptation to build all 15 items simultaneously and test at the end is strong — resist it. A design flaw in item 1 (e.g., wrong variable type, incorrect fulfillment group) caught after all 15 are built means fixing it 15 times. Caught after item 1, you fix it once and the remaining 14 items are built correctly.
Description quality review
The most common quality issue is item descriptions written by IT staff that use IT jargon. Review every description as if you are a business user who has never talked to IT. Common red flags: team names ('AD team', 'ServiceNow admin'), process codes, acronyms without definitions, and passive voice. A good description test: read it to someone outside IT and ask 'do you know what you'd receive if you submitted this request?' If they hesitate, rewrite.
Non-prod to production promotion checklist
Before promoting any item to production: (1) test RITM submitted and fulfilled in non-prod, (2) approval flow tested if approval is required, (3) fulfillment group assignment validated, (4) delivery time set, (5) description reviewed and approved, (6) customer ITSM PO sign-off on the item record. Do not batch-promote. Promote one item at a time so any production issue can be traced to a specific item.
Setting launch expectations
Catalog adoption does not happen automatically at go-live. Coach the customer to: (1) communicate the new catalog to all employees via email or intranet, (2) brief the helpdesk to direct callers to the catalog, (3) add the Employee Center link to the intranet homepage. The first 30 days of adoption data (search terms, most-submitted items, abandoned submissions) is the best input for the Sprint 6 catalog build prioritisation.

## Adoption vs Re-engineering
06 — Catalog Item Configuration Data — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to go live with all items at once rather than sequentially | Build and test sequentially. All items go live at the same time, but they are built and validated one by one before the simultaneous launch. | Sequential build does not prevent a simultaneous launch date. It prevents rework by catching design issues early. The launch date can be fixed; the build approach must be sequential. | 'We can absolutely launch all 15 items on the same day — that's the plan. What we're controlling is the build sequence: build one, test it, fix any issues, then build the next. By the time we reach item 15, we've validated the approach 14 times. All 15 go live together, all tested.' | No exception. Build sequentially; launch simultaneously.

## ServiceNow Mapping
06 — Catalog Item Configuration Data — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Build Sequence
1. Create catalog item record | sc_cat_item | Set name, category, fulfillment group, delivery time, active=false.
2. Apply shared variable set | io_set_item | Link ECS_Catalog_Common to the item.
3. Add item-specific variables | item_option_new | Add in order: first visible to user, last internal.
4. Configure Flow Designer trigger | Flow Designer > Catalog Trigger | Set up fulfillment workflow (simple, approval, or task chain).
5. Set approval policy (if required) | sc_cat_item_approval_policy | Link to the appropriate approval policy from Workbook 05.
6. Test in non-prod | Submit test request | Validate RITM creation, routing, approval (if applicable), and closure.
7. Set active=true | sc_cat_item.active | Activate only after passing quality checklist.
8. Promote to production | Update set or ATF | Promote using standard change management process.